## Office Renovation Timeline
OFFICE RENOVATION TIMELINE TEMPLATE
PROJECT NAME |  | PROJECT MANAGER |  |  | START DATE
[5 empty] | 2017-09-18 | <--Enter date of Monday of first week.
PRIORITY | TASK NAME | START DATE | END DATE | DURATION | STATUS | PERCENTAGE COMPLETE | ASSIGNED TO | COMMENTS | PRIORITY | STATUS | 2017-09-18 |  |  |  |  | 2017-09-25 |  |  |  |  | 2017-10-02 |  |  |  |  | 2017-10-09 |  |  |  |  | 2017-10-16 |  |  |  |  | 2017-10-23 |  |  |  |  | 2017-10-30 |  |  |  |  | 2017-11-06 |  |  |  |  | 2017-11-13 |  |  |  |  | 2017-11-20 |  |  |  |  | 2017-11-27 |  |  |  |  | 2017-12-04 |  |  |  |  | 2017-12-11 |  |  |  |  | 2017-12-18 |  |  |  |  | 2017-12-25 |  |  |  |  | 2018-01-01 |  |  |  |  | 2018-01-08 |  |  |  |  | 2018-01-15 |  |  |  |  | 2018-01-22 |  |  |  |  | 2018-01-29 |  |  |  |  | 2018-02-05 |  |  |  |  | 2018-02-12 |  |  |  |  | 2018-02-19 |  |  |  |  | 2018-02-26 |  |  |  |  | 2018-03-05 |  |  |  |  | 2018-03-12 |  |  |  |  | 2018-03-19 |  |  |  |  | 2018-03-26
| Office Remodel | 2017-09-21 | 2018-03-30 | 191 |  | 1% |  |  | KEY | KEY | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
| Start Date | 2017-09-21 | 2017-10-02 | 12 |  | 46% |  |  | Low | Not Started
Medium | Final Estimate Complete | 2017-09-21 | 2017-09-21 | 1 | Complete | 100% |  |  | Medium | In Progress
High | Contract Signed | 2017-09-22 | 2017-09-29 | 8 | Complete | 100% |  |  | High | Complete
Low | Permission to Schedule Work? | 2017-10-02 | 2017-10-02 | 1 | In Progress | 40%
| Demo Prep | 2017-10-03 | 2017-10-06 | 4 |  | 0%
High | Appliance, Fixture and, Salvage | 2017-10-03 | 2017-10-03 | 1 | Complete | 100%
High | Electrical - Cut Power and Install Temp Service | 2017-10-04 | 2017-10-04 | 1 | Not Started | 0%
Medium | Safety Fence Delivery/Setup | 2017-10-05 | 2017-10-05 | 1 | In Progress | 30%
Low | Install Office/Safety Area (Plans Desk, First Aid, Phone) | 2017-10-06 | 2017-10-06 | 1 |  | 0%
Low | Install Site Camera(s) | 2017-10-06 | 2017-10-06 | 1 |  | 0%
| Demolition | 2017-10-06 | 2017-10-25 | 20 |  | 0%
| Walls | 2017-10-06 | 2017-10-20 | 15 |  | 0%
| Floors | 2017-10-18 | 2017-10-25 | 8 |  | 0%
| Framing | 2017-10-25 | 2017-10-29 | 5
| Level/True Basement and Main Floor | 2017-10-25 | 2017-10-27 | 3
| Frame New Home and Addition | 2017-10-25 | 2017-10-27 | 3
| Plumbing | 2017-10-29 | 2017-10-29 | 1
| Ground Work | 2017-11-01 | 2017-11-15 | 15
| Rough In | 2017-11-01 | 2017-11-08 | 8
| Windows | 2017-11-10 | 2017-11-15 | 6
| Order Windows | 2017-11-13 | 2017-11-18 | 6
| Wrap Sills | 2017-11-18 | 2017-11-18 | 1
| Install Windows | 2017-11-13 | 2017-11-13 | 1
| HVAC | 2017-10-25 | 2017-12-08 | 45
| Ducting and Gas Piping | 2017-10-25 | 2017-10-27 | 3
| Fire System for Drywall | 2017-11-18 | 2017-12-08 | 21
| Electrical | 2017-11-19 | 2017-12-08 | 20
| Electrical-Rough In | 2017-11-29 | 2017-11-29 | 1
| Walkthrough | 2017-11-26 | 2017-12-08 | 13
| A/V | 2017-11-19 | 2017-11-24 | 6
| Low Voltage- CATV, CAT6, Tele | 2017-10-29 | 2017-12-08 | 41
| Speaker Pre-Wire | 2017-10-29 | 2017-11-01 | 4
| Alarm/Security Wiring | 2017-11-29 | 2017-12-08 | 10
| Insulation | 2017-11-22 | 2017-12-15 | 24
| Blow In | 2017-11-22 | 2017-11-24 | 3
| Bats | 2017-11-29 | 2017-12-01 | 3
| Rigid | 2017-12-08 | 2017-12-15 | 8
| Drywall | 2017-11-29 | 2017-12-20 | 22
| Delivery | 2017-11-29 | 2017-12-06 | 8
| Hang and Scrap | 2017-12-20 | 2017-12-20 | 1
| Tape | 2017-12-10 | 2017-12-20 | 11
| Prime | 2017-12-10 | 2017-12-20 | 11
| Touch Up If Needed | 2017-12-17 | 2017-12-17 | 1
| Hardwoods | 2017-12-10 | 2017-12-18 | 9
| Deliver/Acclimate | 2017-12-10 | 2017-12-13 | 4
| Install Hardwoods | 2017-12-18 | 2017-12-18 | 1
High | Stain | 2017-12-13 | 2017-12-13 | 1
High | Finish | 2017-12-27 | 2017-12-29 | 3
| Cure and Protect | 2017-12-27 | 2017-12-29 | 3
| Tile | 2017-12-03 | 2017-12-21 | 19
| Prep | 2017-12-03 | 2017-12-03 | 1
| Install | 2017-12-21 | 2017-12-21 | 1
| Install | 2017-12-21 | 2017-12-21 | 1
| Cabinets | 2018-01-03 | 2018-12-23 | 355
| Shared Space | 2018-01-03 | 2018-01-03 | 1
| Offices | 2018-12-21 | 2018-12-21 | 1
| Kitchenettes | 2018-12-21 | 2018-12-21 | 1
| Conference Rooms | 2018-12-23 | 2018-12-23 | 1
| Bath | 2018-12-23 | 2018-12-23 | 1
| Plumbing Hang Sinks | 2018-01-03 | 2018-01-17 | 15
| Install under Mount Sinks | 2018-01-03 | 2018-01-12 | 10
| Interior Doors | 2018-01-17 | 2018-01-17 | 1
| Delivery-Hang | 2018-01-04 | 2018-01-15 | 12
| Ship to Pre-Fin | 2018-01-04 | 2018-01-15 | 12
| Millwork | 2018-01-04 | 2018-01-15 | 12
| Millwork Material Delivery | 2018-02-16 | 2018-03-13 | 26
| Millwork Install | 2018-02-16 | 2018-03-13 | 26
| Interior Painting | 2018-01-19 | 2018-03-09 | 50
| Millwork Prep | 2018-02-28 | 2018-03-09 | 10
| Cleaning and Masking | 2018-01-25 | 2018-01-29 | 5
| Millwork Painting and Curing (Oil) | 2018-01-25 | 2018-01-29 | 5
| Interior Walls and Ceilings | 2018-01-19 | 2018-02-16 | 29
| Interior doors Hang and Hardware | 2018-01-19 | 2018-01-19 | 1
| Return from Pre-Fin Shop | 2018-02-03 | 2018-02-17 | 15
| Hang | 2018-02-03 | 2018-02-05 | 3
| Install Hardware | 2018-02-07 | 2018-02-09 | 3
| Appliances | 2018-02-17 | 2018-02-17 | 1
| Delivery | 2018-01-18 | 2018-03-09 | 51
| Install | 2018-01-18 | 2018-01-22 | 5
| Plumbing | 2018-01-19 | 2018-02-02 | 15
| Set Toilets, Sinks, etc. | 2018-02-16 | 2018-02-23 | 8
| Electrical | 2018-02-18 | 2018-03-09 | 20
| Trim Cans | 2018-02-21 | 2018-02-21 | 1
| Outlets and Switches | 2018-02-23 | 2018-02-23 | 1
| Surface Mount Fixtures | 2018-02-18 | 2018-02-18 | 1
| Bathroom Glass | 2018-02-16 | 2018-02-23 | 8
| Mirrors | 2018-02-16 | 2018-02-23 | 8
| Shower Doors | 2018-02-25 | 2018-03-08 | 12
| Final Inspections | 2018-03-03 | 2018-03-08 | 6
| Plumbing, Electrical, Mechanical | 2018-02-25 | 2018-02-25 | 1
| Final Inspection | 2018-02-18 | 2018-02-20 | 3
| Wrap Up | 2018-02-18 | 2018-02-20 | 3
| Punch List and Touch Up | 2018-02-18 | 2018-02-18 | 1
| Bath Accessories | 2018-02-28 | 2018-04-17 | 49
| Remove Tools | 2018-02-28 | 2018-03-16 | 17
| Remove Materials | 2018-02-28 | 2018-02-28 | 1
| Deliver Job Book (Sub List, Warranty/Install Paperwork, etc.) | 2018-02-28 | 2018-03-16 | 17
| Deliver Keys | 2018-03-18 | 2018-04-17 | 31
| Complete | 2018-03-21 | 2018-03-30 | 10
CLICK HERE TO CREATE AN OFFICE RENOVATION TIMELINE TEMPLATE IN SMARTSHEET | bar: 2017-09-18 M to 2017-09-18 T
TODAY