**CONSTRUCTION PROJECT PLAN TEMPLATE**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **TASK NAME** | **START DATE** | **END DATE** | **DURATION** in days | **ASSIGNED TO** | **% DONE** |
| Project Prep | 09/21 | 09/30 | 10 |  | 45% |
| Demo Prep | 10/01 | 10/06 | 6 |  | 100% |
| Demolition | 10/06 | 10/24 | 19 |  | 40% |
| Excavation | 10/25 | 10/29 | 5 |  | 30% |
| Concrete | 11/01 | 11/13 | 13 |  |  |
| Pre Backfill | 11/13 | 11/15 | 3 |  |  |
| Framing | 10/25 | 12/05 | 42 |  |  |
| Roof | 11/19 | 12/10 | 22 |  |  |
| Plumbing | 10/29 | 12/09 | 42 |  |  |
| Windows | 11/22 | 12/15 | 24 |  |  |
| HVAC | 11/29 | 12/20 | 22 |  |  |
| Electrical | 12/10 | 12/22 | 13 |  |  |
| A/V | 12/10 | 12/15 | 6 |  |  |
| House Wrap | 12/27 | 12/30 | 4 |  |  |
| Insulation | 12/03 | 12/21 | 19 |  |  |
| Drywall | 01/03 | 01/23 | 21 |  |  |
| Exterior Stone | 01/03 | 01/17 | 15 |  |  |
| Exterior Case Work | 01/04 | 01/13 | 10 |  |  |
| Laundry/Furnace Room Flooring | 02/16 | 03/11 | 24 |  |  |
| Hardwoods | 01/19 | 03/10 | 51 |  |  |
| Tile | 02/03 | 02/14 | 12 |  |  |
| Cabinets | 01/18 | 03/06 | 48 |  |  |
| Plumbing -Hang Sinks | 02/16 | 02/23 | 8 |  |  |
| Interior Doors | 02/25 | 03/09 | 13 |  |  |
| Millwork | 02/15 | 02/17 | 3 |  |  |
| Interior Painting | 02/28 | 04/14 | 46 |  |  |
| Stone Counters | 03/21 | 03/31 | 11 |  |  |
| Schedule Buffer | 02/28 | 03/10 | 11 |  |  |
| Decks | 02/28 | 03/18 | 19 |  |  |
| Interior Doors- Hang & Hardware | 05/03 | 05/13 | 11 |  |  |
| Appliances | 05/02 | 05/03 | 2 |  |  |
| Plumbing | 05/02 | 05/05 | 4 |  |  |
| Electrical | 05/03 | 05/11 | 9 |  |  |
| Bathroom Glass | 05/09 | 05/13 | 5 |  |  |
| Garage Door Dress Up | 05/13 | 05/18 | 6 |  |  |
| Final Inspections | 05/02 | 05/02 | 1 |  |  |
| Wrap-Up | 05/09 | 06/05 | 28 |  |  |
| House Cleaning | 05/29 | 06/10 | 13 |  |  |
| Project Close | 06/01 | 06/01 | 1 |  |  |

**CONSTRUCTION PROJECT PLAN TEMPLATE**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **TASK NAME** | **START DATE** | **END DATE** | **DURATION** in days | **ASSIGNED TO** | **% DONE** |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |

|  |
| --- |
| **DISCLAIMER**Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk. |