## Kaizen Event Checklist
KAIZEN EVENT CHECKLIST TEMPLATE
PROCESS / SYSTEM |  |  | EVENT DATES
FACILITATOR |  |  | TEAM LEADER
TEAM MEMBERS
TIME | ACTIVITY | TEAM MEMBER RESPONSIBLE | COMPLETE / IN PROGRESS | DATE COMPLETED | COMPLETE / IN PROGRESS
Pre-Event | Identify potential problems for shareholders. |  |  |  | COMPLETE
Pre-Event | Present problematic situations. |  |  |  | IN PROGRESS
Pre-Event | Get sponsorship approval. Delegate team leadership delegation.
Pre-Event | Group teams together.
Pre-Event | Schedule pre-planning meeting with team.
Pre-Event | Schedule pre-planning meeting. Outline charter.
Pre-Event | Collect process data/statistics.
Pre-Event | Schedule Kaizen event dates. Reserve room/equipment.
Pre-Event | Schedule date for presentation to management.
Pre-Event | Notify all staff of event (open-door policy).
Pre-Event | Gather supplies (the day before the event).
DAY1 | Review lean elements, rules, tools.
DAY1 | Review project charter.
DAY1 | Do warm-up activities.
DAY1 | Review team rules.
DAY1 | Develop current state map. Take photo.
DAY1 | Identify values. Conduct value discussion session.
DAY1 | Calculate values.
DAY2 | Identify inefficiencies in current map.
DAY2 | Create future state map. Take photo.
DAY2 | Develop standard work & single-piece flow (reduce batching).
DAY2 | Develop visual workplace.
DAY3 | Determine if all goals have been met.
DAY3 | Identify outcomes (performance measures).
DAY3 | Start development implementation.
DAY3 | Finalize presentations.
DAY3 | Identify presenters' roles for management presentation.
DAY3 | Closing: Discuss future business.
DAY3 | Take photographs.
Post-Event | Present event & outcomes to management.
Post-Event | Post event details and photos on bulletin board or common area.
Post-Event | Complete implementation plan.
Post-Event | Train staff.
CLICK HERE TO CREATE IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.