## Portfolio Planning Template
PORTFOLIO PLANNING TEMPLATE
|  | DEPARTMENT |  |  | PORTFOLIO FINANCIAL HEALTH
|  | DEPARTMENT LEAD |  |  | 1085000 | BUDGET
|  | NUMBER OF PROJECTS | 10 |  | 812000 | ACTUAL
|  | DATE OF LAST UPDATE |  |  | 273000 | BALANCE | [13 empty] | CHART BUILDING DATA
PROJECT HEALTH LEVEL | PRIORITY | PROJECT ID | PROJECT NAME | STATUS | PROJECT SUMMARY | PROJECT MANAGER | BUDGET | ACTUAL | BUDGET LESS ACTUAL | EXPECTED DATE OF COMPLETION | NUMBER OF DAYS REMAINING | PERCENT OF PROJECT COMPLETE | ASSOCIATED RISKS | COST BENEFIT ANALYSIS OUTCOME | COMMENTARY | ATTACHMENTS / LINKS | PROJECT HEALTH LEVEL KEY | STATUS KEY | PRIORITY KEY | PROJECT HEALTH LEVEL CT | QTY | STATUS COUNT | QTY | PRIORITY KEY | QTY
1 | LOW |  |  | OTHER |  |  | 800000 | 500000 | 300000 | 2021-09-30 | 33 | 10% |  |  |  |  | 1 | REQUEST PLACED | LOW | 1 | 2 | REQUEST PLACED | 1 | LOW | 4
2 | MEDIUM |  |  | MONITOR |  |  | 285000 | 312000 | -27000 | 2022-05-05 | 250 | 30% |  |  |  |  | 2 | APPROVED | MEDIUM | 2 | 2 | APPROVED | 1 | MEDIUM | 3
3 | HIGH |  |  | COMPLETE |  |  | 0 | 0 | 0 | 2022-09-30 | 398 | 50% |  |  |  |  | 3 | PLANNING PHASE | HIGH | 3 | 1 | PLANNING PHASE | 1 | HIGH | 2
4 | EXTREME |  |  | ON HOLD |  |  | 0 | 0 | 0 | 2022-10-11 | 409 | 25% |  |  |  |  | 4 | ON HOLD | EXTREME | 4 | 4 | ON HOLD | 1 | EXTREME | 1
5 | LOW |  |  | PLANNING PHASE |  |  | 0 | 0 | 0 | 2023-12-12 | 836 | 11% |  |  |  |  | 5 | COMPLETE |  | 5 | 1 | COMPLETE | 3
4 | LOW |  |  | APPROVED |  |  | 0 | 0 | 0 |  |  | 90% | [5 empty] | MONITOR |  |  |  | MONITOR | 2
4 | LOW |  |  | REQUEST PLACED |  |  | 0 | 0 | 0 |  |  | 60% | [5 empty] | OTHER |  |  |  | OTHER | 1
2 | MEDIUM |  |  | MONITOR |  |  | 0 | 0 | 0 |  |  | 30%
1 | MEDIUM |  |  | COMPLETE |  |  | 0 | 0 | 0 |  |  | 100%
4 | HIGH |  |  | COMPLETE |  |  | 0 | 0 | 0 |  |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
NUMBER OF DAYS REMAINING = (([EXPECTED DATE OF COMPLETION]-TODAY())-900)

## BLANK - Portfolio Planning
PORTFOLIO PLANNING TEMPLATE |  |  |  |  | Enter project data below; charts, graphs, and summary info will populate automatically.
|  | DEPARTMENT |  |  | PORTFOLIO FINANCIAL HEALTH
|  | DEPARTMENT LEAD |  |  | 0 | BUDGET
|  | NUMBER OF PROJECTS | 0 |  | 0 | ACTUAL
|  | DATE OF LAST UPDATE |  |  | 0 | BALANCE | [13 empty] | CHART BUILDING DATA
PROJECT HEALTH LEVEL | PRIORITY | PROJECT ID | PROJECT NAME | STATUS | PROJECT SUMMARY | PROJECT MANAGER | BUDGET | ACTUAL | BUDGET LESS ACTUAL | EXPECTED DATE OF COMPLETION | NUMBER OF DAYS REMAINING | PERCENT OF PROJECT COMPLETE | ASSOCIATED RISKS | COST BENEFIT ANALYSIS OUTCOME | COMMENTARY | ATTACHMENTS / LINKS | PROJECT HEALTH LEVEL KEY | STATUS KEY | PRIORITY KEY | PROJECT HEALTH LEVEL CT | QTY | STATUS COUNT | QTY | PRIORITY KEY | QTY
[7 empty] | 0 | 0 | 0 |  | -43536 | 0% |  |  |  |  | 1 | REQUEST PLACED | LOW | 1 | 0 | REQUEST PLACED | 0 | LOW | 0
[7 empty] | 0 | 0 | 0 |  | -43536 | 0% |  |  |  |  | 2 | APPROVED | MEDIUM | 2 | 0 | APPROVED | 0 | MEDIUM | 0
[7 empty] | 0 | 0 | 0 |  | -43536 | 0% |  |  |  |  | 3 | PLANNING PHASE | HIGH | 3 | 0 | PLANNING PHASE | 0 | HIGH | 0
[7 empty] | 0 | 0 | 0 |  | -43536 | 0% |  |  |  |  | 4 | ON HOLD | EXTREME | 4 | 0 | ON HOLD | 0 | EXTREME | 0
[7 empty] | 0 | 0 | 0 |  | -43536 | 0% |  |  |  |  | 5 | COMPLETE |  | 5 | 0 | COMPLETE | 0
[7 empty] | 0 | 0 | 0 |  | -43536 | 0% | [5 empty] | MONITOR |  |  |  | MONITOR | 0
[7 empty] | 0 | 0 | 0 |  | -43536 | 0% | [5 empty] | OTHER |  |  |  | OTHER | 0
[7 empty] | 0 | 0 | 0 |  | -43536 | 0%
[7 empty] | 0 | 0 | 0 |  | -43536 | 0%
[7 empty] | 0 | 0 | 0 |  | -43536 | 0%
[7 empty] | 0 | 0 | 0 |  | -43536 | 0%
[7 empty] | 0 | 0 | 0 |  | -43536 | 0%
[7 empty] | 0 | 0 | 0 |  | -43536 | 0%
[7 empty] | 0 | 0 | 0 |  | -43536 | 0%
[7 empty] | 0 | 0 | 0 |  | -43536 | 0%
[7 empty] | 0 | 0 | 0 |  | -43536 | 0%
[7 empty] | 0 | 0 | 0 |  | -43536 | 0%
[7 empty] | 0 | 0 | 0 |  | -43536 | 0%
Formulas:
NUMBER OF DAYS REMAINING = [EXPECTED DATE OF COMPLETION]-TODAY()

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.