## Sheet1
Project Closeout Checklist
Category | Description | Quantity Requested | Specific Requirement | Comments
Close-out per Specification
Contract Close-out | Submit warranties
Contract Close-out | Submit workmanship bonds
Contract Close-out | Submit maintenance agreements
Contract Close-out | Obtain certificate of Conditional Occupancy
Contract Close-out | Submit final project photos
Contract Close-out | Submit damage or settlements surveys
Contract Close-out | Submit property surveys
Contract Close-out | Submit final record information
Required Testing
Structural Steel | Inspect or test shop bolted connections
Warranties/Guarantees
Wood Doors | Manufacturer's standard warranty
Sprinkler Systems | Mfg warranty w/ forms completed in owner's name
Certificates
Structural Steel | Mill certificates
Hoist/ Trolley | Load tested
Final Submittal
Punch list - Signed off
Mfg warranty w/ forms completed in owner's name