## Recruiting Plan
RECRUITING PLAN TEMPLATE
Recruiting Source | Budget | Hire Goal | Funded | Status | Assigned To | Comments | Start | Finish | Lessons Learned
2015 Recruiting Plan | 460400 | 155 | . |  |  |  | 2015-09-01 | 2016-12-30
Online Recruiting | 7800 | 30 | YES | In Progress | Alex Bright |  | 2016-01-01 | 2016-12-30
www.Monster.com | 1000 | 10 | YES | On Track |  | relationship established ready for postings | 2016-01-16 | 2016-09-06 | Great Hires!! Senior and Technical.
www.careerbuilder.com | 1000 | 10 | YES | On Track |  | relationship established ready for postings | 2016-01-01 | 2016-10-17 | Great place to get management candidates.
LinkedIn | 4800 | 5 | YES | On Track |  | all positions get posted here | 2016-04-04 | 2016-08-17
www.hotjobs.com | 1000 | 5 | YES | In Progress |  | not funded yet this calendar year, finding funding | 2016-01-01 | 2016-12-30
Vendor Agencies | 15600 | 60 | YES | In Progress | Jacob Senmark |  | 2015-09-14 | 2016-06-29
<<List agency 1>> | 25000 | 5 | YES | On Track |  |  | 2015-09-14 | 2016-02-12
<<List agency 2>> | 30000 | 8 | YES | At Risk |  | not funded yet this calendar year, finding funding | 2016-01-01 | 2016-06-29
<<List agency 3>> | 10000 | 3 | YES | On Track |  |  | 2016-03-01 | 2016-05-30 | Slow at delivering, look for new agency.
Campus Recruiting | 52000 | 13 | YES | In Progress | Anthony Gruenelli |  | 2015-09-01 | 2016-03-30
Targeted In-State Colleges | 7000 | 7 | YES | On Track | Sheila Erickson |  | 2015-09-01 | 2016-03-30
National Schools | 15000 | 3 | YES | In Progress | Derek Brown | potentially add one additional hi-pro shool | 2015-09-01 | 2016-03-30
International School | 30000 | 3 | YES | In Progress | Derek Brown | Working with Legal department to fix issues
Job Fairs | 10000 | 10 | YES |  | Anthony Gruenelli |  | 2016-01-10 | 2016-06-24
<<enter job fair location>> | 5000 | 5 | YES | In Progress |  | participating in June fair. finalizing contract | 2016-06-15 | 2016-06-24
<<enter job fair location>> | 5000 | 5 | YES | On Track |  | January event all lined up with participants | 2016-01-10 | 2016-01-22
University Partnerships | 5000 | 4 | YES |  | Anthony Gruenelli |  | 2015-09-01 | 2016-03-30
Central | 2500 | 2 | YES | Not Started | Sheila Erickson |  | 2015-09-01 | 2016-03-30
Eastern | 2500 | 2 | YES | On Track | Derek Brown |  | 2015-09-01 | 2016-03-30
Targeted Recruitment | 20000 | 7 | YES |  | Shari Wise |  | 2016-01-01 | 2016-12-30
Diversity Recruiting | 10000 | 5 | YES | On Track |  |  | 2016-01-01 | 2016-12-30
Executive Recruiting | 10000 | 2 | YES | On Track |  |  | 2016-01-01 | 2016-12-30
Internships | 325000 | 6 | YES |  | Kennedy Kerrigan |  | 2016-06-01 | 2016-08-30
10 Engineering Positions | 250000 | 5 | YES | In Progress | Sheila Erickson |  | 2016-06-01 | 2016-08-30
3 Marketing Positions | 75000 | 1 | YES | On Track | Derek Brown |  | 2016-06-01 | 2016-08-30
Recruiting Events | 15000 | 15 | YES |  | Frank Carlson |  | 2015-09-15 | 2016-05-04
Silicon Valley | 5000 | 5 | YES | On Track |  |  | 2015-09-15 | 2015-09-16
Seattle | 5000 | 5 | YES | On Track |  |  | 2016-02-22 | 2016-02-23
Vancouver | 5000 | 5 | YES | At Risk |  | not funded yet this calendar year, finding funding | 2016-05-03 | 2016-05-04
Employee Referrals | 10000 | 10 | YES | On Track | Kennedy Kerrigan |  | 2016-01-01 | 2016-12-30
Employee Referral Program | 10000 | 10 | YES | On Track |  |  | 2016-01-01 | 2016-12-30
CLICK HERE TO CREATE IN SMARTSHEET

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.