## EXAMPLE Compliance Risk Reg
Compliance Risk Register Template Example
Auto-calculates
Risk ID | Risk Description | Impact Description | Impact Level Rate 1 (LOW) to 5 (HIGH) | Probability Level Rate 1 (LOW) to 5 (HIGH) | Priority Level Impact x Probability Address the highest first. | Compliance Area | Control Gap | Mitigation Plan | Status | Owner | Date Identified | Last Reviewed | Date Closed | Document Link / Reference
C-001 | Improper handling of personal data | Legal penalties, loss of trust | 5 | 4 | 20 | Data Privacy | No staff training on data handling | Conduct mandatory training sessions | In Remediation | Brian Gorman | MM/DD/YY | MM/DD/YY | MM/DD/YY | Policy-DP-101
C-002 | Incomplete injury logs | OSHA non-compliance, fines | 4 | 3 | 12 | Workplace Safety | Manual tracking is prone to errors | Implement digital incident logging | Monitoring | Carmen Robertson | MM/DD/YY | MM/DD/YY | MM/DD/YY | Safety-Reg-WS-204
C-003 | Misstated quarterly revenue | Financial misreporting risk | 5 | 3 | 15 | Financial Reporting | Weak review process | Add second-level approval before submission | In Remediation | Everett Crosse | MM/DD/YY | MM/DD/YY | MM/DD/YY | Audit-FR-309
C-004 | Unsafe material storage | Worker injury risk, liability | 3 | 4 | 12 | Workplace Safety | Outdated safety signage | Replace signage, retrain team leads | Response in Progress | Fiorella Fitzgerald | MM/DD/YY | MM/DD/YY | MM/DD/YY | Safety-Pro-WS-110
C-005 | Delayed financial disclosures | Investor concern, SEC issues | 4 | 2 | 8 | Financial Reporting | Disconnected reporting calendar | Align team deadlines to the compliance schedule | Monitoring | Diana Kennedy | MM/DD/YY | MM/DD/YY | MM/DD/YY | Report-FR-423
C-006 | Unethical sales behavior | Damaged reputation, lost clients | 5 | 3 | 15 | Ethics | No whistleblower process | Establish an anonymous reporting hotline | In Remediation | Alexandra Mattson | MM/DD/YY | MM/DD/YY | MM/DD/YY | Code-ETH-118
C-007 | Expired vendor safety certificates | Contractor risk liability | 3 | 3 | 9 | Workplace Safety | No active tracking system | Automate vendor compliance checks | Response in Progress | Aviv Perez | MM/DD/YY | MM/DD/YY | MM/DD/YY | Vendor-WS-317
C-008 | Unauthorized access to HR files | Data breach, legal exposure | 5 | 4 | 20 | Data Privacy | Weak file permission controls | Apply role-based access to records | Monitoring | Hazel Christensen | MM/DD/YY | MM/DD/YY | MM/DD/YY | AccessPolicy-DP-221
C-009 | Missing recycling program | Environmental compliance gap | 2 | 3 | 6 | Environmental | No policy in place | Launch recycling and waste policy | Response in Progress | Devon Gomez | MM/DD/YY | MM/DD/YY | MM/DD/YY | Env-Sus-ENV-001
C-010 | Unreported expense fraud | Audit risk, financial loss | 4 | 2 | 8 | Financial Reporting | Lax expense approval process | Require pre-approval above threshold | In Remediation | Henry McNeal | MM/DD/YY | MM/DD/YY | MM/DD/YY | Audit-FR-507
C-011 | Untrained forklift operators | Safety violations, injury risk | 5 | 2 | 10 | Workplace Safety | No certification checks | Implement a license validation system | Monitoring | Brooklyn Jansen | MM/DD/YY | MM/DD/YY | MM/DD/YY | Safety-WS-009
C-012 | Ignored harassment complaints | Legal action, culture damage | 5 | 3 | 15 | Ethics | No response protocol | Train managers on incident escalation | In Remediation | Guadalupe Garcia | MM/DD/YY | MM/DD/YY | MM/DD/YY | HR-ETH-013
C-013 | Use of unlicensed software | Copyright violations, fines | 4 | 2 | 8 | Data Privacy | No software inventory | Conduct a software compliance audit | In Remediation | Fiorella Fitzgerald | MM/DD/YY | MM/DD/YY | MM/DD/YY | Policy-DP-502
C-014 | Untested backup process | Risk of data loss | 4 | 3 | 12 | Data Privacy | No routine disaster recovery drills | Schedule and track DR tests quarterly | Response in Progress | Diana Kennedy | MM/DD/YY | MM/DD/YY | MM/DD/YY | DRPlan-DP-114
C-015 | Hazardous waste mislabeling | Environmental penalty | 3 | 4 | 12 | Environmental | Improper disposal records | Retrain facilities staff, add signage | Monitoring | Carmen Robertson | MM/DD/YY | MM/DD/YY | MM/DD/YY | Env-Haz-ENV-075
C-016 | Fraudulent timesheet entries | Financial exposure, HR violations | 4 | 4 | 16 | Ethics | No system alerts | Use automated timekeeping + alerts | Response in Progress | Hazel Christensen | MM/DD/YY | MM/DD/YY | MM/DD/YY | Audit-ETH-311
C-017 | Delayed conflict minerals reporting | SEC compliance issue | 3 | 2 | 6 | Financial Reporting | No update from the supplier | Assign vendor follow-up lead | In Remediation | Everett Crosse | MM/DD/YY | MM/DD/YY | MM/DD/YY | Report-FR-401
C-018 | Insecure customer database | Privacy violation risk | 5 | 3 | 15 | Data Privacy | Outdated encryption methods | Upgrade security protocols | Closed | Fiorella Fitzgerald | MM/DD/YY | MM/DD/YY | MM/DD/YY | DataSec-DP-006
C-019 | Lack of diversity reporting | Reputational harm, legal scrutiny | 3 | 3 | 9 | Ethics | No tracking mechanism | Develop standard DEI metrics reporting | Response in Progress | Brian Gorman | MM/DD/YY | MM/DD/YY | MM/DD/YY | HR-ETH-405
C-020 | Blocked emergency exits | Fire code violation | 5 | 4 | 20 | Workplace Safety | No regular exit inspections | Create a weekly safety checklist | In Remediation | Guadalupe Garcia | MM/DD/YY | MM/DD/YY | MM/DD/YY | Safety-WS-700
C-021 | Incomplete CO₂ emission log | Non-compliance with ESG policy | 3 | 3 | 9 | Environmental | No emissions tracking SOP | Assign owner, create reporting cadence | Response in Progress | Alexandra Mattson | MM/DD/YY | MM/DD/YY | MM/DD/YY | Env-Rep-ENV-502
C-022 | Insider trading rumor | SEC inquiry risk | 4 | 4 | 16 | Ethics | No internal controls for blackout periods | Reinforce disclosure policy, notify staff | In Remediation | Henry McNeal | MM/DD/YY | MM/DD/YY | MM/DD/YY | Code-ETH-092
C-023 | Poor PPE compliance | Workplace injury risk | 3 | 3 | 9 | Workplace Safety | No tracking or enforcement | Assign site supervisor inspections | Under Review | Aviv Perez | MM/DD/YY | MM/DD/YY | MM/DD/YY | Safety-WS-214
C-024 | Failure to retain records | Audit failure risk | 3 | 4 | 12 | Financial Reporting | No retention policy | Create a file retention schedule | Closed | Brooklyn Jansen | MM/DD/YY | MM/DD/YY | MM/DD/YY | Policy-FR-800
C-025 | Incomplete ethics training logs | Internal policy breach | 3 | 3 | 9 | Data Privacy | The training tracker is manual and incomplete | Automate LMS tracking + reports | In Remediation | Carmen Robertson | MM/DD/YY | MM/DD/YY | MM/DD/YY | HR-ETH-614
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Compliance Risk Reg
Compliance Risk Register Template
Auto-calculates
Risk ID | Risk Description | Impact Description | Impact Level Rate 1 (LOW) to 5 (HIGH) | Probability Level Rate 1 (LOW) to 5 (HIGH) | Priority Level Impact x Probability Address the highest first. | Compliance Area | Control Gap | Mitigation Plan | Status | Owner | Date Identified | Last Reviewed | Date Closed | Document Link / Reference
|  |  | 1 | 1 | 1 | Data Privacy |  |  | In Remediation

## Scale and Key
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25 | Status | Compliance Area | LEVEL
| 4 | 4 | 8 | 12 | 16 | 20 | Identified | Data Privacy | 1
| 3 | 3 | 6 | 9 | 12 | 15 | Response in Progress | Workplace Safety | 2
| 2 | 2 | 4 | 6 | 8 | 10 | In Remediation | Financial Reporting | 3
| 1 | 1 | 2 | 3 | 4 | 5 | Monitoring | Ethics | 4
|  | 1 | 2 | 3 | 4 | 5 | Escalated | Environmental | 5
|  | I M P A C T |  |  |  |  | Closed
Under Review

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.