## EXAMPLE Mutual Action Plan Fdbk
MUTUAL ACTION PLAN TEMPLATE WITH FEEDBACK
VALUE SUMMARY
TARGET START | EST. COMPLETION | DATE COMPLETED | OVERALL STATUS
2025-09-02 | 2025-10-09 | 2025-10-10 | ON TRACK
CUSTOMER AND SELLER TEAMS
SELLER TEAM
NAME |  | ROLE |  |  |  | ADDITIONAL INFO
CUSTOMER TEAM
NAME |  | ROLE |  |  |  | ADDITIONAL INFO
MUTUAL ACTION PLAN
MILESTONES | TASK NAME | DESCRIPTION | OWNER (SELLER) | OWNER (CUSTOMER) | STATUS | START DATE | END DATE | DUE DATE | COMPLETE? Yes / No | DURATION in days | OUTCOME | CUSTOMER FEEDBACK
PHASE 1 | [5 empty] | 2025-01-16 | 2025-02-15 |  |  | 31
| Task #1 |  |  |  | Complete | 2025-01-16 | 2025-02-02 |  |  | 18
| Task #2 |  |  |  | In Progress | 2025-01-31 | 2025-02-05 |  |  | 6
| Task #3 |  |  |  | Not Started | 2025-02-05 | 2025-02-15 |  |  | 11
PHASE 2 | [5 empty] | 2025-01-22 | 2025-02-25 |  |  | 35
| Task #1 |  |  |  | Overdue | 2025-01-22 | 2025-01-29 |  |  | 8
| Task #2 |  |  |  | On Hold | 2025-01-28 | 2025-01-31 |  |  | 4
| Task #3 |  |  |  |  | 2025-01-29 | 2025-02-25 |  |  | 28
PHASE 3 | [5 empty] | 2025-02-28 | 2025-03-16 |  |  | 17
| Task #1 |  |  |  |  | 2025-02-28 | 2025-03-01 |  |  | 2
| Task #2 |  |  |  |  | 2025-02-28 | 2025-03-04 |  |  | 5
| Task #3 |  |  |  |  | 2025-03-01 | 2025-03-16 |  |  | 16
PHASE 4 | [5 empty] | 2025-03-16 | 2025-04-16 |  |  | 32
| Task #1 |  |  |  |  | 2025-03-16 | 2025-03-17 |  |  | 2
| Task #2 |  |  |  |  | 2025-03-18 | 2025-03-20 |  |  | 3
| Task #3 |  |  |  |  | 2025-03-24 | 2025-04-16 |  |  | 24
PHASE 5 | [5 empty] | 2025-03-24 | 2025-04-21 |  |  | 29
| Task #1 |  |  |  |  | 2025-03-24 | 2025-03-26 |  |  | 3
| Task #2 |  |  |  |  | 2025-03-26 | 2025-04-05 |  |  | 11
| Task #3 |  |  |  |  | 2025-04-06 | 2025-04-21 |  |  | 16
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Mutual Action Plan Fdbk
MUTUAL ACTION PLAN TEMPLATE WITH FEEDBACK
VALUE SUMMARY
TARGET START | EST. COMPLETION | DATE COMPLETED | OVERALL STATUS
00/00/00 | 00/00/00 | 00/00/00 | ON TRACK
CUSTOMER AND SELLER TEAMS
SELLER TEAM
NAME |  | ROLE |  |  |  | ADDITIONAL INFO
CUSTOMER TEAM
NAME |  | ROLE |  |  |  | ADDITIONAL INFO
MUTUAL ACTION PLAN
MILESTONES | TASK NAME | DESCRIPTION | OWNER (SELLER) | OWNER (CUSTOMER) | STATUS | START DATE | END DATE | DUE DATE | COMPLETE? Yes / No | DURATION in days | OUTCOME | CUSTOMER FEEDBACK
PHASE 1
Task #1
Task #2
Task #3
PHASE 2
Task #1
Task #2
Task #3
PHASE 3
Task #1
Task #2
Task #3
PHASE 4
Task #1
Task #2
Task #3
PHASE 5
Task #1
Task #2
Task #3

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.