## EXAMPLE PDCA Project Template
PDCA Project Template Example
Fill in the non-shaded cells only. Data will populate in the shaded cells.
Project Name | Reduce Software Bug Resolution Time |  |  | Act | Plan
Process | Bug Tracking and Resolution Workflow |  |  | 1.5% | 63.33%
Team Leader | Mateus Tobin |  |  | 3.333% | 60%
Cycle No. | 1 |  |  | Check | Do
Project Manager |  |  | Expected Hours | Progress | Updated
Sarah Goodwin |  |  | 128 | 37.41% | MM/DD/YY
PDCA Stage | Actions | Responsible | Due Date | Duration (in hours) | Percent Complete | Status | Takeaways / Notes
Plan | Analyze current bug resolution process | Team | MM/DD/YY | 6 | 100% | Completed | Developers have varied interpretation of severity.
Plan | Brainstorm solutions for faster resolution | Team | MM/DD/YY | 8 | 80% | In Progress | Automating bug categorization can save time.
Plan | Select optimal solution for bug tracking | Team | MM/DD/YY | 4 | 100% | Completed | Implement automatic severity tagging in software.
Plan | Develop action plan for process changes | Lead Dev | MM/DD/YY | 4 | 100% | Completed | Clear ownership reduces confusion in execution.
Do | Implement the new bug categorization system | DevOps | MM/DD/YY | 24 | 100% | Completed | Initial hiccups in integration, but solved quickly.
Do | Test the new system on a pilot project | QA Team | MM/DD/YY | 12 | 90% | In Progress | QA feedback loops were slower than expected.
Do | Gather feedback from developers and testers | QA Lead | MM/DD/YY | 8 | 50% | In Progress | Mixed feedback; system needs minor adjustments.
Check | Analyze bug resolution data post-implementation | QA Lead | MM/DD/YY | 8 | 10% | In Progress
Check | Evaluate whether resolution time meets targets | Team | MM/DD/YY | 6 | 0% | Not Started
Check | Share results with stakeholders | Manager | MM/DD/YY | 2 | 0% | Not Started
Act | Adjust categorization algorithm based on feedback | Lead Dev | MM/DD/YY | 6 | 6% | In Progress
Act | Update bug tracking documentation | Team Lead | MM/DD/YY | 4 | 0% | Not Started
Act | Roll out system-wide implementation | IT Manager | MM/DD/YY | 24 | 0% | Not Started
Act | Train team on updated process | QA Lead | MM/DD/YY | 12 | 0% | Not Started
Plan | Action | Name | MM/DD/YY | 0 | 0% | Not Started
Plan | Action | Name | MM/DD/YY | 0 | 0% | Not Started
Do | Action | Name | MM/DD/YY | 0 | 0% | Not Started
Dashboard by Stage
Plan |  | Completion | Do |  | Completion
Analyze current bug resolution process |  | 100%
Brainstorm solutions for faster resolution |  | 80%
Select optimal solution for bug tracking |  | 100%
Develop action plan for process changes |  | 100%
|  |  | Implement the new bug categorization system |  | 100%
|  |  | Test the new system on a pilot project |  | 90%
|  |  | Gather feedback from developers and testers |  | 50%
Action |  | 0%
Action |  | 0%
|  |  | Action |  | 0%
Check |  | Completion | Act |  | Completion
Analyze bug resolution data post-implementation |  | 10%
Evaluate whether resolution time meets targets |  | 0%
Share results with stakeholders |  | 0%
|  |  | Adjust categorization algorithm based on feedback |  | 6%
|  |  | Update bug tracking documentation |  | 0%
|  |  | Roll out system-wide implementation |  | 0%
|  |  | Train team on updated process |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET
37%

## PDCA Project Template
PDCA Project Template
Fill in the non-shaded cells only. Data will populate in the shaded cells.
Project Name |  |  |  | Act | Plan
Process |  |  |  | 0% | 0%
Team Leader |  |  |  | 0% | 0%
Cycle No. |  |  |  | Check | Do
Project Manager |  |  | Expected Hours | Progress | Updated
|  |  |  | 0% | MM/DD/YY
PDCA Stage | Actions | Responsible | Due Date | Duration (in hours) | Percent Complete | Status | Takeaways / Notes
Plan |  |  | MM/DD/YY | 0 | 0% | Completed
Plan |  |  | MM/DD/YY | 0 | 0% | In Progress
Plan |  |  | MM/DD/YY | 0 | 0% | Completed
Plan |  |  | MM/DD/YY | 0 | 0% | Completed
Do |  |  | MM/DD/YY |  | 0% | Completed
Do |  |  | MM/DD/YY |  |  | In Progress
Do |  |  | MM/DD/YY |  |  | In Progress
Check |  |  | MM/DD/YY |  | 0% | In Progress
Check |  |  | MM/DD/YY |  |  | Not Started
Check |  |  | MM/DD/YY |  |  | Not Started
Act |  |  | MM/DD/YY |  | 0% | In Progress
Act |  |  | MM/DD/YY |  |  | Not Started
Act |  |  | MM/DD/YY |  |  | Not Started
Act |  |  | MM/DD/YY |  |  | Not Started
Plan |  |  | MM/DD/YY |  |  | Not Started
Plan |  |  | MM/DD/YY |  |  | Not Started
Do |  |  | MM/DD/YY |  |  | Not Started
Dashboard by Stage
Plan |  | Completion | Do |  | Completion
0 |  | 0%
0 |  | 0%
0 |  | 0%
0 |  | 0%
|  |  | 0 |  | 0%
|  |  | 0 |  | 0%
|  |  | 0 |  | 0%
0 |  | 0%
0 |  | 0%
|  |  | 0 |  | 0%
Check |  | Completion | Act |  | Completion
0 |  | 0%
0 |  | 0%
0 |  | 0%
|  |  | 0 |  | 0%
|  |  | 0 |  | 0%
|  |  | 0 |  | 0%
|  |  | 0 |  | 0%
0%

## Dropdown Keys - DO NOT DELETE
KEY DROPDOWNS - DO NOT DELETE
CATEGORY | PRIORITY
Act | Completed
Plan | In Progress
Do | Not Started
Check

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.