## Example - Project Action Plan
Project Action Plan Template Example
Project Name
Website Redesign Project
Project Manager |  |  | Today's Date
Diana Kennedy |  |  | 2025-05-20
Project Goals
Improve user experience, increase mobile responsiveness, and reduce bounce rate by 20% within three months of launch.
Phase 1: Discovery & Planning
Priority | Action Item | KPIs | Status | Start Date | Due Date | Duration (in days) | Owner | Resources | Estimated Cost | Notes
High | Conduct stakeholder interviews | Interview completion rate | Complete | 2025-04-01 | 2025-04-07 | 6 | Project Manager | Stakeholder list | 0 | All interviews completed
Medium | Analyze current site traffic | Traffic analysis report | Complete | 2025-04-05 | 2025-04-10 | 5 | Data Analyst | Google Analytics | 0 | Bounce rate 58% baseline
High | Define project scope | Approved scope document | In Progress | 2025-04-10 | 2025-04-20 | 10 | Diana Kennedy | Scope draft template | 0 | Awaiting leadership feedback
0
0
0
0
Phase 2: Design & Prototyping
Priority | Action Item | KPIs | Status | Start Date | Due Date | Duration (in days) | Owner | Resources | Estimated Cost | Notes
High | Create wireframes | Wireframe approval rate | In Progress | 2025-04-22 | 2025-04-29 | 7 | UX Designer | Figma, style guide | 1500 | Desktop and mobile complete
High | Design high-fidelity mockups | Stakeholder approval score | Not Started | 2025-05-01 | 2025-05-10 | 9 | Design Team | Adobe XD, brand assets | 3000 | Scheduled for review on May 6
Medium | Conduct usability testing | Task completion rate | Not Started | 2025-05-12 | 2025-05-16 | 4 | UX Researcher | UserTesting.com | 2000 | Recruit 5-7 testers
0
0
0
0
Phase 3: Development & Testing
Priority | Action Item | KPIs | Status | Start Date | Due Date | Duration (in days) | Owner | Resources | Estimated Cost | Notes
High | Develop site framework | Page speed, mobile scores | Not Started | 2025-05-20 | 2025-06-10 | 21 | Dev Team Lead | GitHub, VS Code | 8000 | Framework first, then features
Medium | QA testing across devices | Bug count, test pass rate | Not Started | 2025-06-11 | 2025-06-20 | 9 | QA Analyst | BrowserStack | 12000 | Focus on mobile issues first
[6 empty] | 0 |  |  | 0
0
0
0
Phase 4: Launch & Evaluation
Priority | Action Item | KPIs | Status | Start Date | Due Date | Duration (in days) | Owner | Resources | Estimated Cost | Notes
High | Launch new website | Go-live success | Not Started | 2025-06-25 | 2025-06-27 | 2 | Project Manager | Hosting platform | 0 | Weekend soft launch preferred
Medium | Post-launch traffic review | Bounce rate, session length | Not Started | 2025-06-28 | 2025-07-05 | 7 | Marketing Analyst | Google Analytics | 0 | Compare 30 days pre/post launch
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Action Plan
Project Action Plan Template
Project Name
Project Manager |  |  | Today's Date
Project Goals
Phase 1: Discovery & Planning
Priority | Action Item | KPIs | Status | Start Date | Due Date | Duration (in days) | Owner | Resources | Estimated Cost | Notes
High | [5 empty] | 0 |  |  | 0
Medium | [5 empty] | 0 |  |  | 0
Low | [5 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
Phase 2: Design & Prototyping
Priority | Action Item | KPIs | Status | Start Date | Due Date | Duration (in days) | Owner | Resources | Estimated Cost | Notes
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
Phase 3: Development & Testing
Priority | Action Item | KPIs | Status | Start Date | Due Date | Duration (in days) | Owner | Resources | Estimated Cost | Notes
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
Phase 4: Launch & Evaluation
Priority | Action Item | KPIs | Status | Start Date | Due Date | Duration (in days) | Owner | Resources | Estimated Cost | Notes
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
[6 empty] | 0 |  |  | 0
CLICK HERE TO CREATE IN SMARTSHEET

## Dropdown Key - Do Not Delete
DROPDOWN KEY - DO NOT DELETE
PRIORITY KEY | STATUS KEY
Low | Complete
Medium | Not Started
High | In Progress
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.