## EXAMPLE Risk Register
Simple Risk Register Template Example
Auto-calculates
Risk ID | Risk Description | Impact Description | Impact Level Rate 1 (LOW) to 5 (HIGH) | Probability Level Rate 1 (LOW) to 5 (HIGH) | Priority Level Impact x Probability Address the highest first. | Mitigation Notes | Status | Owner | Date Identified | Last Reviewed | Notes
SAF-001 | Wet floor near the loading bay | Slip, minor injury | 2 | 1 | 2 | Post signage, mop the area daily | Open | Lori Garcia | 2031-01-05 | 2031-01-08 | Near door 2
SAF-002 | Low overhead beam | Head bump hazard | 3 | 2 | 6 | Foam padding, warning tape | In Progress | Makara McLean | 2031-01-06 | 2031-01-10 | Truck crew flagged
SAF-003 | Broken step on scaffolding | Fall from height | 2 | 3 | 6 | Replace the damaged plank | Escalated | Marta Hicks | 2031-01-07 | 2031-01-09 | Reported by the safety audit
SAF-004 | Loose cables near the control room | Trip hazard | 1 | 4 | 4 | Cable matting ordered | In Progress | Mateus Tobin | 2031-01-09 | 2031-01-11 | Short-term fix used
SAF-005 | Forklift blind corner | Collision potential | 1 | 5 | 5 | Add a convex mirror | Open | Olivia Carter | 2031-01-10 | 2031-01-12 | High-traffic zone
SAF-006 | Chemical storage mislabeled | Exposure risk | 2 | 4 | 8 | Relabel, safety training refresh | Open | Petrus Nishimura | 2031-01-11 | 2031-01-12 | Two bins affected
SAF-007 | Ventilation fan not working | Heat buildup in the work area | 5 | 3 | 15 | Temp fan in use, part on order | In Progress | Raghu Prakash | 2031-01-12 | 2031-01-13 | Summer risk
SAF-008 | Broken PPE dispenser | Access delay for gloves | 6 | 2 | 12 | Order a new unit | Closed | Romy Bailey | 2031-01-13 | 2031-01-15 | Resolved 01/14
SAF-009 | Unsecured ladder during setup | Fall potential | 2 | 1 | 2 | Locking base added | Closed | Sarah Goodwin | 2031-01-14 | 2031-01-17 | Training reminder sent
SAF-010 | Dust accumulation near vents | Respiratory irritation | 4 | 2 | 8 | Scheduled deep clean | In Progress | Sasha Petrov | 2031-01-15 | 2031-01-18 | Vendor scheduled 01/20
SAF-011 | Noise levels exceed 85 dB | Hearing loss over time | 3 | 3 | 9 | Enforce ear protection | Open | Lori Garcia | 2031-01-16 | 2031-01-19 | Random spot checks
SAF-012 | Power tool left plugged in | Electrocution risk | 2 | 4 | 8 | Daily end-of-shift checks | Open | Makara McLean | 2031-01-17 | 2031-01-18 | Reminder signage added
SAF-013 | Untrained temp worker | Incorrect machine use | 2 | 5 | 10 | Shadow shifts added | In Progress | Marta Hicks | 2031-01-18 | 2031-01-20 | Onboarding revised
SAF-014 | Oil spill on the walkway | Slip, twisted ankle | 2 | 5 | 10 | Immediate cleanup protocol | Closed | Mateus Tobin | 2031-01-19 | 2031-01-21 | Logged in site report
SAF-015 | No emergency light in storage | Navigation issue in blackout | 1 | 4 | 4 | Install a backup light | Open | Olivia Carter | 2031-01-20 | 2031-01-23 | Checked wiring
SAF-016 | Loose handrail on stairs | Loss of balance risk | 2 | 4 | 8 | Tightened and retested | Closed | Petrus Nishimura | 2031-01-21 | 2031-01-22 | QA sign-off complete
SAF-017 | Leaking pipe above walkway | Slip, fall hazard | 3 | 3 | 9 | Leak patched, floor mat placed | In Progress | Raghu Prakash | 2031-01-22 | 2031-01-25 | Monitor for recurrence
SAF-018 | Faulty fire alarm sensor | Delayed alert in an emergency | 4 | 2 | 8 | Vendor notified | Escalated | Romy Bailey | 2031-01-23 | 2031-01-26 | Recheck 01/28
SAF-019 | The stack of pallets is unstable | Tip-over hazard | 2 | 1 | 2 | Re-stack, add safety straps | Open | Sarah Goodwin | 2031-01-24 | 2031-01-27 | Observed near dock B
SAF-020 | Debris near the forklift route | Obstruction hazard | 2 | 4 | 8 | Assign cleanup daily | In Progress | Sasha Petrov | 2031-01-25 | 2031-01-27 | End-of-day checklist updated
SAF-021 | Exit sign flickering | Visibility issue | 1 | 4 | 4 | Replace the LED unit | Closed | Lori Garcia | 2031-01-26 | 2031-01-27 | Completed 01/26
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Risk Register
Simple Risk Register Template
Auto-calculates
Risk ID | Risk Description | Impact Description | Impact Level Rate 1 (LOW) to 5 (HIGH) | Probability Level Rate 1 (LOW) to 5 (HIGH) | Priority Level Impact x Probability Address the highest first. | Mitigation Notes | Status | Owner | Date Identified | Last Reviewed | Notes | KEY
|  |  | 1 | 1 | 1 | [6 empty] | LEVEL
|  |  | 2 | 2 | 4 | [6 empty] | 1
2
3
4
5

## Scale and Key
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25 | Status
| 4 | 4 | 8 | 12 | 16 | 20 | Open
| 3 | 3 | 6 | 9 | 12 | 15 | In Progress
| 2 | 2 | 4 | 6 | 8 | 10 | Closed
| 1 | 1 | 2 | 3 | 4 | 5 | Escalated
|  | 1 | 2 | 3 | 4 | 5
I M P A C T

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.