## Construction Project Timeline
CONSTRUCTION PROJECT TIMELINE TEMPLATE
PROJECT TITLE |  |  | START
|  |  | 2025-09-21 |  | PROJECT DURATION
PROJECT MANAGER |  |  | END |  | in days
|  |  | 2026-06-01 |  | 254
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
Planning | Complete |  | 2025-09-21 | 2025-09-30 | 10 |  | Not Started
Demo Prep | Complete |  | 2025-10-01 | 2025-10-06 | 6 |  | In Progress
Demolition | Complete |  | 2025-10-06 | 2025-10-24 | 19 |  | Complete
Excavation | Complete |  | 2025-10-25 | 2025-10-29 | 5 |  | On Hold
Concrete | Complete |  | 2025-11-01 | 2025-11-13 | 13
Pre backfill | Complete |  | 2025-11-13 | 2025-11-15 | 3
Framing | In Progress |  | 2025-10-25 | 2025-12-05 | 42
Roof | In Progress |  | 2025-11-19 | 2025-12-10 | 22
Plumbing | In Progress |  | 2025-10-29 | 2025-12-09 | 42
Windows | On Hold |  | 2025-11-22 | 2025-12-15 | 24
HVAC | In Progress |  | 2025-11-29 | 2025-12-20 | 22
Electrical | In Progress |  | 2025-12-10 | 2025-12-22 | 13
A/V | Complete |  | 2025-12-10 | 2025-12-15 | 6
House wrap | Complete |  | 2025-12-27 | 2025-12-30 | 4
Insulation | In Progress |  | 2025-12-03 | 2025-12-21 | 19
Drywall | In Progress |  | 2026-01-03 | 2026-01-23 | 21
Exterior stone | In Progress |  | 2026-01-03 | 2026-01-17 | 15
Exterior case work | Not Started |  | 2026-01-04 | 2026-01-13 | 10
Laundry/furnace room flooring | In Progress |  | 2026-02-16 | 2026-03-11 | 24
Hardwoods | In Progress |  | 2026-01-19 | 2026-03-10 | 51
Tile | On Hold |  | 2026-02-03 | 2026-02-14 | 12
Cabinets | In Progress |  | 2026-01-18 | 2026-03-06 | 48
Plumbing -hang sinks | In Progress |  | 2026-02-16 | 2026-02-23 | 8
Interior doors | Complete |  | 2026-02-25 | 2026-03-09 | 13
Millwork | Complete |  | 2026-02-15 | 2026-02-17 | 3
Interior painting | In Progress |  | 2026-02-28 | 2026-04-14 | 46
Stone Counters | In Progress |  | 2026-03-21 | 2026-03-31 | 11
Schedule Buffer | In Progress |  | 2026-02-28 | 2026-03-10 | 11
Decks | In Progress |  | 2026-02-28 | 2026-03-18 | 19
Interior doors- hang & hardware | Complete |  | 2026-05-03 | 2026-05-13 | 11
Appliances | Complete |  | 2026-05-02 | 2026-05-03 | 2
Plumbing | In Progress |  | 2026-05-02 | 2026-05-05 | 4
Electrical | In Progress |  | 2026-05-03 | 2026-05-11 | 9
Bathroom Glass | In Progress |  | 2026-05-09 | 2026-05-13 | 5
Garage Door dress up | Not Started |  | 2026-05-13 | 2026-05-18 | 6
FINAL Inspections | In Progress |  | 2026-05-02 | 2026-05-02 | 1
Wrap up | In Progress |  | 2026-05-09 | 2026-06-05 | 28
House Cleaning | On Hold |  | 2026-05-29 | 2026-06-10 | 13
Complete | In Progress |  | 2026-06-10 | 2026-06-10 | 1
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Constr Project Timeline
CONSTRUCTION PROJECT TIMELINE TEMPLATE
PROJECT TITLE |  |  | START
PROJECT DURATION
PROJECT MANAGER |  |  | END |  | in days
1
TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
Planning |  |  |  |  | 1 |  | Not Started
Demo Prep |  |  |  |  | 1 |  | In Progress
Demolition |  |  |  |  | 1 |  | Complete
Excavation |  |  |  |  | 1 |  | On Hold
Concrete |  |  |  |  | 1
Pre backfill |  |  |  |  | 1
Framing |  |  |  |  | 1
Roof |  |  |  |  | 1
Plumbing |  |  |  |  | 1
Windows |  |  |  |  | 1
HVAC |  |  |  |  | 1
Electrical |  |  |  |  | 1
A/V |  |  |  |  | 1
House wrap |  |  |  |  | 1
Insulation |  |  |  |  | 1
Drywall |  |  |  |  | 1
Exterior stone |  |  |  |  | 1
Exterior case work |  |  |  |  | 1
Laundry/furnace room flooring |  |  |  |  | 1
Hardwoods |  |  |  |  | 1
Tile |  |  |  |  | 1
Cabinets |  |  |  |  | 1
Plumbing -hang sinks |  |  |  |  | 1
Interior doors |  |  |  |  | 1
Millwork |  |  |  |  | 1
Interior painting |  |  |  |  | 1
Stone Counters |  |  |  |  | 1
Schedule Buffer |  |  |  |  | 1
Decks |  |  |  |  | 1
Interior doors- hang & hardware |  |  |  |  | 1
Appliances |  |  |  |  | 1
Plumbing |  |  |  |  | 1
Electrical |  |  |  |  | 1
Bathroom Glass |  |  |  |  | 1
Garage Door dress up |  |  |  |  | 1
FINAL Inspections |  |  |  |  | 1
Wrap up |  |  |  |  | 1
House Cleaning |  |  |  |  | 1
Complete |  |  |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.