## Design Milestone Checklist
DESIGN MILESTONE BREAKOUT CHECKLIST
DESIGN MILESTONES
NOTES
This Design Milestones Review Checklist contains four worksheets: "Design Milestones" lists the major design tasks and milestones during specific stages; the other worksheets (“High-Level Pre-Design,” "Technical Requirements,” and "Documentation and User Interface,”) list actual design activities. You can customize this template to include any other design activities that are relevant to your project.
TASK | RESULT | STATUS | ASSIGNED TO | COMMENTS | STATUS
SCOPING |  |  |  |  | Not Started
Preliminary Model QA |  | Complete |  |  | In Progress
Review Analysis Documentation |  | Overdue |  |  | Complete
Incorporate Analysis Changes |  | In Progress |  |  | On Hold
Plan/Conduct Sub-System Specific Training |  | On Hold |  |  | Overdue
Develop Sub-System Context Diagram |  | Not Started
Develop Preliminary Workflow |  | Complete
Prepare Preliminary Sub-System Architecture Diagram
Identify Third-Party Software Needs
Identify Hardware Needs
Prepare for First Milestone
FIRST MILESTONE | Issue Report for Teams
ONLINE PROTOTYPING
Develop First Prototype | First Prototype; Session Notes
SECOND ONLINE MILESTONE | Issue Report for Teams
Develop Second Prototype (Navigation)
Prepare Preliminary Data Access Paths
Develop Third Prototype
Third Milestone Preparation
THIRD ONLINE MILESTONE | Issue Report for Teams
Perform Code Review
Develop Preliminary Online Help Requirements
Develop User Help Text
CROSS TEAM TASKS
Prepare Data Requirements
Prepare Detail Interface Design
Define Internal Dependencies
Prepare Final Data Access Path Requirements
DETAIL DESIGN
Identify Security Requirements
Identify Audit Requirements
Identify Controls Requirements
Develop Program Specs for Complex Processing
Identify Transaction Recovery
Develop Detail Transaction Volumetrics
Develop System Operating Expectations
Refine Scoping Work Products
MAJOR MILESTONE
Confirm Scope/Deliverables; Signoff Required | Check List
CLICK HERE TO CREATE IN SMARTSHEET

## High-Level Pre-Design Checklist
HIGH-LEVEL PRE-DESIGN CHECKLIST
DESIGN FACTOR | VERIFIED? | COMMENTS | SEE DOCUMENT | VERIFIED?
DESIGN REQUIREMENTS COMPLIANCE |  |  |  | YES
The design review should clearly identify all assumptions and problems with the requirements, such as missing functions, extraneous functions, and imprecise, ambiguous, or incorrect functions. | YES |  |  | NO
Deviations and other major design decisions from the requirements have been documented and approved. | NO |  |  | N/A
The design adequately addresses the following:
Security and Privacy Issues | YES
Real-Time Requirements | NO
Performance Issues (memory and timing) | N/A
Spare Capacity (CPU and memory) | N/A
Maintainability
Understandability
Database Requirements
Loading and Initialization
Error Handling and Recovery
User Interface Issues
Software Upgrades
Functional Dependencies
Design Constraints
Requirements for Error Checking
PRE-DESIGN CONSIDERATIONS
Ensure that the following system specifications are documented:
System Spec 1
System Spec 2
System Spec 3
System Spec 4
System Spec 5
System Spec 6
System Spec 7
System Spec 8
System Spec 9
System Spec 10
System Spec 11
System Spec 12
System Spec 13
System Spec 14
System Spec 15
COST AND BUSINESS CONCERNS
Estimated costs and cost constraints effectively comply with the main purpose of the system.
Metrics are designed and built consistently, with the expected results of implementing the designs directly into the system.
The following business considerations are accurately determined:
Desired Delivery Date or Proposed Project Schedule
Success and Failure Criteria
Use Cases - clearly describes how each group of users will be using the system.
General Business Process - web user will buy a product, add a customer, add contact information, etc.
Input / Output
Frequency of Activity
Cycles of Activity

## Technical Requirements
TECHNICAL REQUIREMENTS DESIGN CHECKLIST
DESIGN FACTOR | VERIFIED? | COMMENTS | SEE DOCUMENT | VERIFIED?
DESIGN LOGIC |  |  |  | YES
The design has been verified for the presence of logic errors. | YES |  |  | NO
All unique and positional values have been tested. | NO |  |  | N/A
FUNCTIONAL SPECIFICATIONS
The documented specifications for each process are accurate and complete. These specifications are written in precise, unambiguous terms.
Human factors are properly addressed in functions that provide the user interface.
DESIGN REQUIREMENTS TRACEABILITY
The detailed design matches its high level-design requirements, and all functions and interfaces are described completely, accurately, and in sufficient detail.
The detailed design of each module or interface fulfills its part of the requirements and is identified in the System Requirement Specifications (SRS) document.
The designed data contains logic. All internal data is defined and there is no extraneous data.
ERROR HANDLING AND RECOVERY
The design has been verified to ensure adequate error condition testing.
The error conditions are tested.
The program allows for successful error recovery across module or process failures.

## Documentation + User Interface
DOCUMENTATION + USER INTERFACE
DESIGN FACTOR | VERIFIED? | COMMENTS | SEE DOCUMENT | VERIFIED?
HELP DOCUMENTS + USER INTERFACE |  |  |  | YES
The design is flexible. | YES |  |  | NO
The system has been designed for easy access and maintenance. | NO |  |  | N/A
All components or modules at a system and sub-system level have been identified on a System Architecture Model. | N/A
The level of decomposition is sufficient to identify all modules.
The user’s interactions with the system should enhance the quality of their work life.
The design is aesthetically pleasing.
The system will always keep the user informed about what is going on by suppling appropriate feedback within a reasonable amount of time.
Users should be free to select and sequence tasks (when appropriate), rather than having the system do this for them.
The design consistently follows industry or company formatting standards across all screens.
The error messages are expressed in plain language (i.e., not in codes).
Message prompts are stated constructively, without overt or implied criticism of the user.
The design interfaces include a level of detail that allows quick and easy verification.
The layout of the menu facilitates visual scanning by the user.
To facilitate search, lists are ordered in such a way as to reveal the structure and relationships among items.
KNOWLEDGE TRANSFER
The system design capitalizes on the prior learning and experience of the intended users.
The system is designed to facilitate the transfer of learning from one area (e.g., application) to another.
The system promotes the learning of the location of items in the menu structure.
SEARCH FACILITIES
The designed menu system allows for a variety of user search styles.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.