## Event Management Critical Path
EVENT MANAGEMENT CRITICAL PATH TEMPLATE
Complete non-shaded fields and Activity Descriptions, only. |  | START DATE | [5 empty] | 2021-01-17
|  | FINISH DATE excluding wknds & holidays | [5 empty] | 2021-07-29 | DURATION in days | 136.6667
| – CRITICAL ACTIVITIES | [6 empty] | DURATION in days
|  | PREDECESSOR ACTIVITIES | [5 empty] | OPTIMISTIC | MOST LIKELY | PESSIMISTIC | EXPECTED | EARLY START | EARLY FINISH | LATE START | LATE FINISH
ID | ACTIVITY DESCRIPTION | PA – enter separately in columns | [5 empty] | MIN | AVG | MAX | DURATION | ES | EF | LS | LF | SLACK
1 | START | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
2 | Define event objectives | 1 | [5 empty] | 3 | 5 | 7 | 5 | 0 | 5 | 0 | 0 | 0
3 | Select team leaders | 2 | [5 empty] | 3 | 5 | 7 | 5 | 5 | 10 | 0 | 0 | 0
4 | Prepare event budget | 3 | [5 empty] | 10 | 15 | 30 | 18.3333 | 10 | 28.3333 | 0 | 0 | 0
5 | Book a venue | 4 | [5 empty] | 10 | 20 | 6 | 12 | 28.3333 | 40.3333 | 0 | 0 | 0
6 | Develop marketing plan | 3 | 4 |  |  |  |  | 20 | 30 | 40 | 30 | 28.3333 | 58.3333 | 50 | 80 | 21.6667
7 | Research vendors | 4 | [5 empty] | 15 | 20 | 30 | 21.6667 | 28.3333 | 50 | 0 | 0 | 0
8 | Obtain permits | 7 | [5 empty] | 55 | 60 | 80 | 65 | 50 | 115 | 0 | 0 | 0
9 | Secure accommodations for staff | 3 | 4 |  |  |  |  | 5 | 7 | 10 | 7.3333 | 28.3333 | 35.6667 | 0 | 0 | 0
10 | Confirm suppliers | 7 | [5 empty] | 15 | 20 | 30 | 21.6667 | 50 | 71.6667 | 50 | 71.6667 | 0
11 | Review contracts | 10 | [5 empty] | 20 | 30 | 40 | 30 | 71.6667 | 101.6667 | 71.6667 | 101.6667 | 0
12 | Create and distribute invitations | 6 | 10 |  |  |  |  | 25 | 30 | 40 | 31.6667 | 71.6667 | 103.3333 | 80 | 111.6667 | 8.3333
13 | Task 13 | 11 | [5 empty] | 5 | 10 | 15 | 10 | 101.6667 | 111.6667 | 101.6667 | 111.6667 | 0
14 | Task 14 | 11 | 12 | 13 |  |  |  | 1 | 3 | 5 | 3 | 111.6667 | 114.6667 | 111.6667 | 114.6667 | 0
15 | Task 15 | 11 | 14 |  |  |  |  | 5 | 10 | 15 | 10 | 114.6667 | 124.6667 | 114.6667 | 124.6667 | 0
16 | Task 16 | 14 | 15 |  |  |  |  | 1 | 3 | 5 | 3 | 124.6667 | 127.6667 | 124.6667 | 127.6667 | 0
17 | Task 17 | 13 | 15 | 16 |  |  |  | 1 | 3 | 5 | 3 | 127.6667 | 130.6667 | 127.6667 | 130.6667 | 0
18 | Task 18 | 11 | 12 | 13 | 14 | 16 | 17 | 1 | 3 | 5 | 3 | 130.6667 | 133.6667 | 130.6667 | 133.6667 | 0
19 | Task 19 | 12 | 18 |  |  |  |  | 1 | 3 | 5 | 3 | 133.6667 | 136.6667 | 133.6667 | 136.6667 | 0
20 | FINISH | 18 | 19 | [7 empty] | 0 | 136.6667 | 136.6667 | 136.6667 | 136.6667 | 0
CLICK HERE TO CREATE IN SMARTSHEET
CALCULATIONS FOR CHART AREA
[17 empty] | PA EF | [5 empty] | SA | [19 empty] | SA LS | [19 empty] | ES | C | over | under | DURATION | over | under | SLACK | EVENTS | EVENTS | AXIS
[17 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | [19 empty] | 0 | [18 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | -0.5
[17 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | [19 empty] | 0 | [17 empty] | 0 | 5 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 0.5
[17 empty] | 5 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 |  | 6 |  |  | 9 | [14 empty] | 0 |  | 50 |  |  | 0 | [11 empty] | 5 | 5 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 1.5
[17 empty] | 10 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 5 | 6 | 7 |  | 9 | [15 empty] | 0 | 50 | 0 |  | 0 | [11 empty] | 10 | 18.3333 | 11.6667 | 8.3333 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 2.5
[17 empty] | 28.3333 | 0 | 0 | 0 | 0 | 0 | [40 empty] | 28.3333 | 12 | -6 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 3.5
[17 empty] | 10 | 28.3333 | 0 | 0 | 0 | 0 | [11 empty] | 12 | [19 empty] | 80 | [8 empty] | 28.3333 | #N/A | #N/A | #N/A | 30 | 10 | 10 | 21.6667 | #N/A | #N/A | 4.5
[17 empty] | 28.3333 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  | 10 | [17 empty] | 0 |  | 50 | [10 empty] | 28.3333 | 21.6667 | 8.3333 | 6.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 5.5
[17 empty] | 50 | 0 | 0 | 0 | 0 | 0 | [40 empty] | 50 | 65 | 15 | 10 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 6.5
[17 empty] | 10 | 28.3333 | 0 | 0 | 0 | 0 | [40 empty] | 28.3333 | 7.3333 | 2.6667 | 2.3333 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 7.5
[17 empty] | 50 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 11 | 12 | [18 empty] | 71.6667 | 80 | [8 empty] | 50 | 21.6667 | 8.3333 | 6.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 8.5
[17 empty] | 71.6667 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 13 | 14 | 15 |  |  | 18 | [14 empty] | 101.6667 | 111.6667 | 114.6667 |  |  | 130.6667 |  |  | 71.6667 | 30 | 10 | 10 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 9.5
[17 empty] | 58.3333 | 71.6667 | 0 | 0 | 0 | 0 | [13 empty] | 14 |  |  |  | 18 | 19 | [14 empty] | 111.6667 |  |  |  | 130.6667 | 133.6667 |  | 71.6667 | #N/A | #N/A | #N/A | 31.6667 | 8.3333 | 6.6667 | 8.3333 | #N/A | #N/A | 10.5
[17 empty] | 101.6667 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 14 |  |  | 17 | 18 | [15 empty] | 111.6667 |  |  | 127.6667 | 130.6667 |  |  | 101.6667 | 10 | 5 | 5 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 11.5
[17 empty] | 101.6667 | 103.3333 | 111.6667 | 0 | 0 | 0 | [14 empty] | 15 | 16 |  | 18 | [16 empty] | 114.6667 | 124.6667 |  | 130.6667 |  |  | 111.6667 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 12.5
[17 empty] | 101.6667 | 114.6667 | 0 | 0 | 0 | 0 | [15 empty] | 16 | 17 | [18 empty] | 124.6667 | 127.6667 |  |  |  | 114.6667 | 10 | 5 | 5 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 13.5
[17 empty] | 114.6667 | 124.6667 | 0 | 0 | 0 | 0 | [16 empty] | 17 | 18 | [18 empty] | 127.6667 | 130.6667 |  |  | 124.6667 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 14.5
[17 empty] | 111.6667 | 124.6667 | 127.6667 | 0 | 0 | 0 | [17 empty] | 18 | [19 empty] | 130.6667 |  |  | 127.6667 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 15.5
[17 empty] | 101.6667 | 103.3333 | 111.6667 | 114.6667 | 127.6667 | 130.6667 | [18 empty] | 19 | 20 | [18 empty] | 133.6667 | 136.6667 | 130.6667 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 16.5
[17 empty] | 103.3333 | 133.6667 | 0 | 0 | 0 | 0 | [19 empty] | 20 | [19 empty] | 136.6667 | 133.6667 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 17.5
[17 empty] | 133.6667 | 136.6667 | 0 | 0 | 0 | 0 | [40 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 27.3333 | 136.6667 | 18.5

## BLANK- Event Mgmt Critical Path
EVENT MANAGEMENT CRITICAL PATH TEMPLATE
Complete non-shaded fields and Activity Descriptions, only. |  | START DATE
|  | FINISH DATE excluding wknds & holidays | 0 | DURATION in days | 0
| – CRITICAL ACTIVITIES |  | DURATION in days
|  | PREDECESSOR ACTIVITIES | OPTIMISTIC | MOST LIKELY | PESSIMISTIC | EXPECTED | EARLY START | EARLY FINISH | LATE START | LATE FINISH
ID | ACTIVITY DESCRIPTION | PA – enter separately in columns | MIN | AVG | MAX | DURATION | ES | EF | LS | LF | SLACK
1 | START |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
6 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
7 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
9 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
10 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
11 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
12 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
13 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
14 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
17 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
18 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
19 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
20 | FINISH |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
CALCULATIONS FOR CHART AREA
[12 empty] | PA EF | [5 empty] | SA | SA LS | ES | C | over | under | DURATION | over | under | SLACK | EVENTS | EVENTS | AXIS
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | -0.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 12.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 14.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 17.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 18.5

## Holidays - customize
Enter Non-Working Holidays, below.
DATE | DESCRIPTION
2020-01-01 | New Year's Day
2020-01-20 | Martin Luther King Jr.'s Birthday
2020-02-17 | Washington's Birthday
2020-05-25 | Memorial Day
2020-07-04 | Independence Day
2020-09-07 | Labor Day
2020-10-12 | Columbus Day
2020-11-11 | Veterans Day
2020-11-26 | Thanksgiving Day
2020-12-25 | Christmas Day
2021-01-01 | New Year's Day
2021-01-18 | Martin Luther King Jr.'s Birthday
2021-02-15 | Washington's Birthday
2021-05-31 | Memorial Day
2021-07-04 | Independence Day
2021-09-06 | Labor Day
2021-10-11 | Columbus Day
2021-11-11 | Veterans Day
2021-11-25 | Thanksgiving Day
2021-12-25 | Christmas Day
2022-01-01 | New Year's Day
2022-01-17 | Martin Luther King Jr.'s Birthday
2022-02-21 | Washington's Birthday
2022-05-30 | Memorial Day
2022-07-04 | Independence Day
2022-09-05 | Labor Day
2022-10-10 | Columbus Day
2022-11-11 | Veterans Day
2022-11-24 | Thanksgiving Day
2022-12-26 | Christmas Day observed
2023-01-02 | New Year's Day observed
2023-01-16 | Martin Luther King Jr.'s Birthday
2023-02-20 | Washington's Birthday
2023-05-29 | Memorial Day
2023-07-04 | Independence Day
2023-09-04 | Labor Day
2023-10-09 | Columbus Day
2023-11-11 | Veterans Day
2023-11-23 | Thanksgiving Day
2023-12-25 | Christmas Day
2024-01-01 | New Year's Day
2024-01-15 | Martin Luther King Jr.'s Birthday
2024-02-19 | Washington's Birthday
2024-05-27 | Memorial Day
2024-07-04 | Independence Day
2024-09-02 | Labor Day
2024-10-14 | Columbus Day
2024-11-11 | Veterans Day
2024-11-28 | Thanksgiving Day
2024-12-25 | Christmas Day
2025-01-01 | New Year's Day
2025-01-20 | Martin Luther King Jr.'s Birthday
2025-02-17 | Washington's Birthday
2025-05-26 | Memorial Day
2025-07-04 | Independence Day
2025-09-01 | Labor Day
2025-10-13 | Columbus Day
2025-11-11 | Veterans Day
2025-11-27 | Thanksgiving Day
2025-12-25 | Christmas Day

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.