## Project Mgmt Critical Path
PROJECT MANAGEMENT CRITICAL PATH TEMPLATE
Complete non-shaded fields, only. |  |  |  | START DATE | [5 empty] | 2021-01-17
| – CRITICAL ACTIVITIES |  |  | FINISH DATE excluding wknds & holidays | [5 empty] | 2021-05-26 | DURATION in days | 91.3333
DURATION in days
|  |  |  | PREDECESSOR ACTIVITIES | [5 empty] | OPTIMISTIC | MOST LIKELY | PESSIMISTIC | EXPECTED | EARLY START | EARLY FINISH | LATE START | LATE FINISH
ID | TASK NAME | ASSIGNED TO | STATUS | PA – enter separately in columns | [5 empty] | MIN | AVG | MAX | DURATION | ES | EF | LS | LF | SLACK | STATUS
1 | PROJECT CONCEPTION AND INITIATION |  | In Progress | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
2 | Project Charter |  | Complete | 1 | [5 empty] | 8 | 10 | 12 | 10 | 0 | 10 | 0 | 0 | 0 | In Progress
3 | Project Charter Revisions |  | Not Started | 1 | 2 |  |  |  |  | 2 | 5 | 8 | 5 | 10 | 15 | 0 | 0 | 0 | Complete
4 | Research |  | Overdue | 2 | 3 |  |  |  |  | 30 | 45 | 60 | 45 | 15 | 60 | 0 | 0 | 0 | On Hold
5 | Projections |  | On Hold | 2 | 3 |  |  |  |  | 8 | 11 | 14 | 11 | 15 | 26 | 0 | 0 | 0 | Overdue
6 | Stakeholders |  | Needs Review | 1 | [5 empty] | 10 | 14 | 18 | 14 | 0 | 14 | 0 | 0 | 0 | Needs Review
7 | Guidelines |  | Needs Update | 6 | [5 empty] | 12 | 14 | 16 | 14 | 14 | 28 | 0 | 0 | 0 | Needs Update
8 | Project Initiation |  |  | 7 | [5 empty] | 15 | 19 | 25 | 19.6667 | 28 | 47.6667 | 0 | 0 | 0
9 | PROJECT DEFINITION AND PLANNING | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0
10 | Scope & Goal Setting |  |  | 2 | 3 |  |  |  |  | 8 | 10 | 20 | 12.6667 | 15 | 27.6667 | 0 | 0 | 0
11 | Budget |  |  | 4 | 5 | 6 |  |  |  | 1 | 3 | 5 | 3 | 60 | 63 | 0 | 0 | 0
12 | Communication Plan |  |  | 4 | 5 | 6 |  |  |  | 5 | 9 | 15 | 9.6667 | 60 | 69.6667 | 0 | 0 | 0
13 | Risk Management |  |  | 3 | [5 empty] | 4 | 9 | 13 | 8.6667 | 15 | 23.6667 | 0 | 0 | 0
14 | PROJECT LAUNCH & EXECUTION | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0
15 | Status & Tracking |  |  | 10 | [5 empty] | 1 | 3 | 5 | 3 | 27.6667 | 30.6667 | 0 | 0 | 0
16 | KPIs |  |  | 9 | 10 |  |  |  |  | 3 | 6 | 7 | 5.3333 | 27.6667 | 33 | 0 | 0 | 0
17 | Monitoring |  |  | 16 | [5 empty] | 5 | 9 | 12 | 8.6667 | 33 | 41.6667 | 71.6667 | 80.3333 | 38.6667
18 | Forecasts |  |  | 16 | [5 empty] | 1 | 3 | 5 | 3 | 33 | 36 | 66.6667 | 69.6667 | 33.6667
19 | Project Updates |  |  | 11 | 12 | 13 |  |  |  | 1 | 2 | 5 | 2.6667 | 69.6667 | 72.3333 | 0 | 0 | 0
20 | Chart Updates |  |  | 11 | 14 |  |  |  |  | 2 | 4 | 6 | 4 | 63 | 67 | 0 | 0 | 0
21 | PROJECT PERFORMANCE / MONITORING | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0
22 | Project Objectives |  |  | 13 | 15 | 16 |  |  |  | 3 | 7 | 10 | 6.6667 | 33 | 39.6667 | 0 | 0 | 0
23 | Quality Deliverables |  |  | 11 | 12 | 13 | 14 | 16 | 17 | 7 | 11 | 15 | 11 | 69.6667 | 80.6667 | 80.3333 | 91.3333 | 10.6667
24 | Effort & Cost Tracking |  |  | 12 | 18 |  |  |  |  | 20 | 20 | 25 | 21.6667 | 69.6667 | 91.3333 | 69.6667 | 91.3333 | 0
25 | Project Performance |  |  | 23 | 24 | [7 empty] | 0 | 91.3333 | 91.3333 | 91.3333 | 91.3333 | 0
CLICK HERE TO CREATE IN SMARTSHEET
CALCULATIONS FOR CHART AREA
[19 empty] | PA EF | [5 empty] | SA | [21 empty] | SA LS | [21 empty] | ES | C | over | under | DURATION | over | under | SLACK | EVENTS | EVENTS | AXIS
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 3 |  |  | 6 | [17 empty] | 0 | 0 |  |  | 0 | [16 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | -0.5
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3 | 4 | 5 |  |  |  | 10 | [15 empty] | 0 | 0 | 0 |  |  |  | 0 | [13 empty] | 0 | 10 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 0.5
[19 empty] | 0 | 10 | 0 | 0 | 0 | 0 |  |  |  | 4 | 5 |  |  |  | 10 |  |  | 13 | [13 empty] | 0 | 0 |  |  |  | 0 |  |  | 0 | [10 empty] | 10 | 5 | 3 | 3 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 1.5
[19 empty] | 10 | 15 | 0 | 0 | 0 | 0 | [9 empty] | 11 | 12 | [20 empty] | 0 | 0 | [11 empty] | 15 | 45 | 15 | 15 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 2.5
[19 empty] | 10 | 15 | 0 | 0 | 0 | 0 | [9 empty] | 11 | 12 | [20 empty] | 0 | 0 | [11 empty] | 15 | 11 | 3 | 3 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 3.5
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 7 |  |  | 11 | 12 | [17 empty] | 0 |  |  | 0 | 0 | [11 empty] | 0 | 14 | 4 | 4 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 4.5
[19 empty] | 14 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 | [21 empty] | 0 | [14 empty] | 14 | 14 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 5.5
[19 empty] | 28 | 0 | 0 | 0 | 0 | 0 | [44 empty] | 28 | 19.6667 | 5.3333 | 4.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 6.5
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 16 | [21 empty] | 0 | [8 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 7.5
[19 empty] | 10 | 15 | 0 | 0 | 0 | 0 | [12 empty] | 15 | 16 | [20 empty] | 0 | 0 | [8 empty] | 15 | 12.6667 | 7.3333 | 4.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 8.5
[19 empty] | 60 | 26 | 14 | 0 | 0 | 0 | [16 empty] | 19 | 20 |  | 23 | [18 empty] | 0 | 0 |  | 80.3333 |  |  | 60 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 9.5
[19 empty] | 60 | 26 | 14 | 0 | 0 | 0 | [16 empty] | 19 |  |  | 23 | 24 | [17 empty] | 0 |  |  | 80.3333 | 69.6667 |  | 60 | 9.6667 | 5.3333 | 4.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 10.5
[19 empty] | 15 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 19 |  | 22 | 23 | [18 empty] | 0 |  | 0 | 80.3333 |  |  | 15 | 8.6667 | 4.3333 | 4.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 11.5
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [17 empty] | 20 |  | 23 | [19 empty] | 0 |  | 80.3333 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 12.5
[19 empty] | 27.6667 | 0 | 0 | 0 | 0 | 0 | [18 empty] | 22 | [21 empty] | 0 |  |  |  | 27.6667 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 13.5
[19 empty] | 0 | 27.6667 | 0 | 0 | 0 | 0 | [14 empty] | 17 | 18 |  |  | 22 | 23 | [16 empty] | 71.6667 | 66.6667 |  |  | 0 | 80.3333 |  |  | 27.6667 | 5.3333 | 1.6667 | 2.3333 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 14.5
[19 empty] | 33 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 23 | [21 empty] | 80.3333 |  |  | 33 | #N/A | #N/A | #N/A | 8.6667 | 3.3333 | 3.6667 | 38.6667 | #N/A | #N/A | 15.5
[19 empty] | 33 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 24 | [21 empty] | 69.6667 |  | 33 | #N/A | #N/A | #N/A | 3 | 2 | 2 | 33.6667 | #N/A | #N/A | 16.5
[19 empty] | 63 | 69.6667 | 23.6667 | 0 | 0 | 0 | [44 empty] | 69.6667 | 2.6667 | 2.3333 | 1.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 17.5
[19 empty] | 63 | 0 | 0 | 0 | 0 | 0 | [44 empty] | 63 | 4 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 18.5
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [44 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 19.5
[19 empty] | 23.6667 | 30.6667 | 33 | 0 | 0 | 0 | [44 empty] | 33 | 6.6667 | 3.3333 | 3.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 20.5
[19 empty] | 63 | 69.6667 | 23.6667 | 0 | 33 | 41.6667 | [21 empty] | 25 | [21 empty] | 91.3333 | 69.6667 | #N/A | #N/A | #N/A | 11 | 4 | 4 | 10.6667 | #N/A | #N/A | 21.5
[19 empty] | 69.6667 | 36 | 0 | 0 | 0 | 0 | [21 empty] | 25 | [21 empty] | 91.3333 | 69.6667 | 21.6667 | 3.3333 | 1.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 22.5
[19 empty] | 80.6667 | 91.3333 | 0 | 0 | 0 | 0 | [44 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 18.2667 | 91.3333 | 23.5

## BLANK - Proj Mgmt Critical Path
PROJECT MANAGEMENT CRITICAL PATH TEMPLATE
Complete non-shaded fields, only. |  |  |  | START DATE
| – CRITICAL ACTIVITIES |  |  | FINISH DATE excluding wknds & holidays | 0 | DURATION in days | 0
DURATION in days
|  |  |  | PREDECESSOR ACTIVITIES | OPTIMISTIC | MOST LIKELY | PESSIMISTIC | EXPECTED | EARLY START | EARLY FINISH | LATE START | LATE FINISH
ID | TASK NAME | ASSIGNED TO | STATUS | PA – enter separately in columns | MIN | AVG | MAX | DURATION | ES | EF | LS | LF | SLACK | STATUS
1 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
2 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | In Progress
3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Complete
4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | On Hold
5 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Overdue
6 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Needs Review
7 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Needs Update
8 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
9 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
10 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
11 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
12 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
13 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
15 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
16 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
17 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
18 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
19 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
21 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
22 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
23 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
24 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
25 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
CALCULATIONS FOR CHART AREA
[14 empty] | PA EF | [5 empty] | SA | SA LS | ES | C | over | under | DURATION | over | under | SLACK | EVENTS | EVENTS | AXIS
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -0.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 12.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 14.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 17.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 18.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 19.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 20.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 21.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 22.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 23.5

## Holidays - customize
Enter Non-Working Holidays, below.
DATE | DESCRIPTION
2020-01-01 | New Year's Day
2020-01-20 | Martin Luther King Jr.'s Birthday
2020-02-17 | Washington's Birthday
2020-05-25 | Memorial Day
2020-07-04 | Independence Day
2020-09-07 | Labor Day
2020-10-12 | Columbus Day
2020-11-11 | Veterans Day
2020-11-26 | Thanksgiving Day
2020-12-25 | Christmas Day
2021-01-01 | New Year's Day
2021-01-18 | Martin Luther King Jr.'s Birthday
2021-02-15 | Washington's Birthday
2021-05-31 | Memorial Day
2021-07-04 | Independence Day
2021-09-06 | Labor Day
2021-10-11 | Columbus Day
2021-11-11 | Veterans Day
2021-11-25 | Thanksgiving Day
2021-12-25 | Christmas Day
2022-01-01 | New Year's Day
2022-01-17 | Martin Luther King Jr.'s Birthday
2022-02-21 | Washington's Birthday
2022-05-30 | Memorial Day
2022-07-04 | Independence Day
2022-09-05 | Labor Day
2022-10-10 | Columbus Day
2022-11-11 | Veterans Day
2022-11-24 | Thanksgiving Day
2022-12-26 | Christmas Day observed
2023-01-02 | New Year's Day observed
2023-01-16 | Martin Luther King Jr.'s Birthday
2023-02-20 | Washington's Birthday
2023-05-29 | Memorial Day
2023-07-04 | Independence Day
2023-09-04 | Labor Day
2023-10-09 | Columbus Day
2023-11-11 | Veterans Day
2023-11-23 | Thanksgiving Day
2023-12-25 | Christmas Day
2024-01-01 | New Year's Day
2024-01-15 | Martin Luther King Jr.'s Birthday
2024-02-19 | Washington's Birthday
2024-05-27 | Memorial Day
2024-07-04 | Independence Day
2024-09-02 | Labor Day
2024-10-14 | Columbus Day
2024-11-11 | Veterans Day
2024-11-28 | Thanksgiving Day
2024-12-25 | Christmas Day
2025-01-01 | New Year's Day
2025-01-20 | Martin Luther King Jr.'s Birthday
2025-02-17 | Washington's Birthday
2025-05-26 | Memorial Day
2025-07-04 | Independence Day
2025-09-01 | Labor Day
2025-10-13 | Columbus Day
2025-11-11 | Veterans Day
2025-11-27 | Thanksgiving Day
2025-12-25 | Christmas Day

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.