## EXAMPLE - 30-60-90 Day Plan
30-60-90 DAY BUSINESS PLAN TO INCREASE SALES WITH GANTT CHART
PLAN TITLE |  |  | START
|  |  | 2025-07-21 |  | PLAN DURATION
PREPARED BY |  |  | END |  | in days
|  |  | 2025-10-18 |  | 90
PLAN DESCRIPTION (PURPOSE AND GOALS)
TASK NAME | STATUS | OWNER | START DATE | END DATE | DURATION in days | COMMENTS | STATUS KEY
DAY 1-30 | In Progress |  | 2025-07-21 | 2025-08-19 | 30 |  | Not Started
Clearly define and prioritize goals | Complete |  | 2025-07-21 | 2025-07-22 | 2 |  | In Progress
Ensure goals align with strategy | Complete |  | 2025-07-22 | 2025-07-23 | 2 |  | Complete
Ensure goals align with business objectives | Complete |  | 2025-07-23 | 2025-07-25 | 3 |  | On Hold
Conduct Market Research | Complete |  | 2025-07-25 | 2025-07-30 | 6 |  | Overdue
a. Market size | Complete |  | 2025-07-25 | 2025-07-28 | 4
b. Market share | Complete |  | 2025-07-25 | 2025-07-30 | 6
Get feedback from customer base | Complete |  | 2025-07-30 | 2025-08-10 | 12
a. Send surveys | Complete |  | 2025-07-30 | 2025-08-10 | 12
b. Conduct interviews | Complete |  | 2025-07-31 | 2025-08-10 | 11
Research competitors | Overdue |  | 2025-07-31 | 2025-08-15 | 16
Conduct SWOT Analysis | In Progress |  | 2025-08-15 | 2025-08-16 | 2
Assess competitive advantage | In Progress |  | 2025-08-16 | 2025-08-16 | 1
Evaluate KPIs | In Progress |  | 2025-08-17 | 2025-08-17 | 1
Evaluate current process | In Progress |  | 2025-08-18 | 2025-08-18 | 1
Find gaps and opportunities | In Progress |  | 2025-08-16 | 2025-08-19 | 4
Other | On Hold |  | 2025-08-19 | 2025-08-19 | 1
DAY 30-60 | In Progress |  | 2025-08-20 | 2025-09-18 | 30
Evaluate criteria for target market segments | Not Started |  | 2025-08-20 | 2025-08-20 | 1
Analyze leads | Not Started |  | 2025-08-21 | 2025-08-22 | 2
Find opportunities for untapped market | On Hold |  | 2025-08-22 | 2025-08-29 | 8
Evaluate strategic partnerships | In Progress |  | 2025-08-23 | 2025-08-30 | 8
Get feedback from sales team | In Progress |  | 2025-08-30 | 2025-09-01 | 3
Refine marketing strategy | In Progress |  | 2025-09-01 | 2025-09-05 | 5
Refine sales plan | In Progress |  | 2025-09-05 | 2025-09-08 | 4
Evaluate success metrics | In Progress |  | 2025-09-08 | 2025-09-09 | 2
Create sales forecast | In Progress |  | 2025-09-10 | 2025-09-10 | 1
Determine systems to put in place to meet sales goals | In Progress |  | 2025-09-11 | 2025-09-14 | 4
Determine and evaluate resources required | In Progress |  | 2025-09-15 | 2025-09-17 | 3
Develop action plan to train sales team | In Progress |  | 2025-09-17 | 2025-09-17 | 1
Develop plan to align cross-functional teams | In Progress |  | 2025-09-18 | 2025-09-19 | 2
Other | In Progress |  | 2025-09-18 | 2025-09-19 | 2
Other | In Progress |  | 2025-09-18 | 2025-09-19 | 2
DAY 60-90 | Not Started |  | 2025-09-20 | 2025-10-19 | 30
Plan promotional activities | Not Started |  | 2025-09-20 | 2025-09-22 | 3
Create promotional materials | Not Started |  | 2025-09-23 | 2025-09-26 | 4
Update website | Not Started |  | 2025-09-27 | 2025-09-27 | 1
Ensure systems are in place to support sales team | Not Started |  | 2025-09-28 | 2025-10-03 | 6
Develop launch plan | Not Started |  | 2025-10-03 | 2025-10-04 | 2
Schedule meeting to review performance and get feedback | Not Started |  | 2025-10-05 | 2025-10-05 | 1
Other | Not Started |  | 2025-10-06 | 2025-10-12 | 7
Other | Not Started |  | 2025-10-13 | 2025-10-19 | 7
Complete | Not Started |  | 2025-10-19 | 2025-10-19 | 1
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - 30-60-90 Day Plan
30-60-90 DAY BUSINESS PLAN TO INCREASE SALES WITH GANTT CHART
PLAN TITLE |  |  | START
PLAN DURATION
PREPARED BY |  |  | END |  | in days
1
PLAN DESCRIPTION (PURPOSE AND GOALS)
TASK NAME | STATUS | OWNER | START DATE | END DATE | DURATION in days | COMMENTS | STATUS KEY
DAY 1-30 |  |  |  |  | 1 |  | Not Started
Clearly define and prioritize goals |  |  |  |  | 1 |  | In Progress
Ensure goals align with strategy |  |  |  |  | 1 |  | Complete
Ensure goals align with business objectives |  |  |  |  | 1 |  | On Hold
Conduct Market Research |  |  |  |  | 1 |  | Overdue
a. Market size |  |  |  |  | 1
b. Market share |  |  |  |  | 1
Get feedback from customer base |  |  |  |  | 1
a. Send surveys |  |  |  |  | 1
b. Conduct interviews |  |  |  |  | 1
Research competitors |  |  |  |  | 1
Conduct SWOT Analysis |  |  |  |  | 1
Assess competitive advantage |  |  |  |  | 1
Evaluate KPIs |  |  |  |  | 1
Evaluate current process |  |  |  |  | 1
Find gaps and opportunities |  |  |  |  | 1
Other |  |  |  |  | 1
DAY 30-60 |  |  |  |  | 1
Evaluate criteria for target market segments |  |  |  |  | 1
Analyze leads |  |  |  |  | 1
Find opportunities for untapped market |  |  |  |  | 1
Evaluate strategic partnerships |  |  |  |  | 1
Get feedback from sales team |  |  |  |  | 1
Refine marketing strategy |  |  |  |  | 1
Refine sales plan |  |  |  |  | 1
Evaluate success metrics |  |  |  |  | 1
Create sales forecast |  |  |  |  | 1
Determine systems to put in place to meet sales goals |  |  |  |  | 1
Determine and evaluate resources required |  |  |  |  | 1
Develop action plan to train sales team |  |  |  |  | 1
Develop plan to align cross-functional teams |  |  |  |  | 1
Other |  |  |  |  | 1
Other |  |  |  |  | 1
DAY 60-90 |  |  |  |  | 1
Plan promotional activities |  |  |  |  | 1
Create promotional materials |  |  |  |  | 1
Update website |  |  |  |  | 1
Ensure systems are in place to support sales team |  |  |  |  | 1
Develop launch plan |  |  |  |  | 1
Schedule meeting to review performance and get feedback |  |  |  |  | 1
Other |  |  |  |  | 1
Other |  |  |  |  | 1
Complete |  |  |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.