## Data Gov Implementation Plan
DATA GOVERNANCE IMPLEMENTATION PLAN TEMPLATE
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | % COMPLETE
PROJECT DELIVERABLE
TASKS | RESPONSIBLE | START | END | DAYS | STATUS | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | STATUS KEY
DISCOVERY | [35 empty] | COMPLETE
Identify stakeholders |  |  |  | 0 | [31 empty] | OVERDUE
Identify vision, mission, goals |  |  |  | 0 | [31 empty] | IN PROGRESS
Estimate data asset value and costs |  |  |  | 0 | [31 empty] | NOT STARTED
Build a case for change |  |  |  | 0 | [31 empty] | ON HOLD
BASELINE
Assess data governance maturity level |  |  |  | 0
Establish data governance target maturity level |  |  |  | 0
Review data architecture |  |  |  | 0
0
TARGET
Define policies |  |  |  | 0
Define organizational structure and roles |  |  |  | 0
Define governance process |  |  |  | 0
Identify required tools |  |  |  | 0
PLAN / ROADMAP
Gap analysis |  |  |  | 0
Identify / prioritize activities |  |  |  | 0
Develop data management roadmap |  |  |  | 0
0
EXECUTION
Fill roles |  |  |  | 0
Develop policies |  |  |  | 0
Communicate with stakeholders |  |  |  | 0
Measure performance and monitor feedback |  |  |  | 0
LAUNCH
CLICK HERE TO CREATE IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.