## Mktg Proj Mgmt Workflow & Schd
MARKETING PROJECT MANAGEMENT WORKFLOW AND SCHEDULE TEMPLATE
| PROJECT TITLE |  | START DATE
|  |  | 2024-01-02 |  |  | PROJECT DURATION
| MARKETING PROJECT MANAGER |  | END DATE |  |  | in days
|  |  | 2024-03-26 |  |  | 85
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION | Complete |  | 2024-01-02 | 2024-02-09 | 40 |  | Not Started
1.1 | Define Goals and KPIs | Complete |  | 2024-01-02 | 2024-01-11 | 10 |  | In Progress
1.2 | – Research | Complete |  | 2024-01-10 | 2024-02-23 | 45 |  | On Hold
1.3 | – Prioritize | Complete |  | 2024-01-10 | 2024-01-20 | 11
1.4 | – Clarify Project Requirements | Complete |  | 2024-01-16 | 2024-01-29 | 14
1.5 | – Guidelines | In Progress |  | 2024-01-19 | 2024-02-01 | 14
2 | PROJECT DEFINITION AND PLANNING | In Progress |  | 2024-01-28 | 2024-02-14 | 18
2.1 | – Assess Resources | On Hold |  | 2024-01-28 | 2024-02-06 | 10
2.2 | – Budget | In Progress |  | 2024-01-31 | 2024-02-02 | 3
2.3 | – Task Breakdown and Milestones | In Progress |  | 2024-02-04 | 2024-02-12 | 9
2.4 | – Select and Prep Team | Complete |  | 2024-02-06 | 2024-02-14 | 9
3 | PROJECT LAUNCH & EXECUTION | Complete |  | 2024-02-18 | 2024-03-26 | 39
3.1 | – Create Content | In Progress |  | 2024-02-18 | 2024-02-20 | 3
3.2 | – Team Communication | In Progress |  | 2024-02-18 | 2024-02-23 | 6
3.2.1 | –– Check and Approve | In Progress |  | 2024-02-18 | 2024-02-26 | 9
3.2.2 | –– Review | Not Started |  | 2024-02-21 | 2024-02-23 | 3
3.3 | – Publish Content | Not Started |  | 2024-02-22 | 2024-02-23 | 2
4 | PROJECT CLOSING AND LEARNING | In Progress |  | 2024-02-25 | 2024-03-26 | 31
4.1 | – Measure and Assess | In Progress |  | 2024-02-25 | 2024-02-28 | 4
4.2 | – Team Post-Mortem | On Hold |  | 2024-02-26 | 2024-03-03 | 7
4.3 | – Action Plan | Not Started |  | 2024-02-25 | 2024-03-06 | 11
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Mktg Proj Mgmt Workflow
Marketing Project Management Workflow and Schedule Template
| PROJECT TITLE |  | START DATE
PROJECT DURATION
| MARKETING PROJECT MANAGER |  |  |  |  | in days
1
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION |  |  |  |  | 1 |  | Not Started
1.1 | [5 empty] | 1 |  | In Progress
1.1.1 | [5 empty] | 1 |  | Complete
1.2 | [5 empty] | 1 |  | On Hold
1.3 | [5 empty] | 1
1.4 | [5 empty] | 1
1.5 | [5 empty] | 1
1.6 | [5 empty] | 1
2 | PROJECT DEFINITION AND PLANNING |  |  |  |  | 1
2.1 | [5 empty] | 1
2.2 | [5 empty] | 1
2.3 | [5 empty] | 1
2.4 | [5 empty] | 1
3 | PROJECT LAUNCH & EXECUTION |  |  |  |  | 1
3.1 | [5 empty] | 1
3.2 | [5 empty] | 1
3.2.1 | [5 empty] | 1
3.2.2 | [5 empty] | 1
3.3 | [5 empty] | 1
3.3.1 | [5 empty] | 1
4 | PROJECT CLOSING AND LEARNING |  |  |  |  | 1
4.1 | [5 empty] | 1
4.2 | [5 empty] | 1
4.3 | [5 empty] | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.