## Multiple Product Gantt
MULTIPLE PRODUCT GANTT CHART WITH DEPENDENCIES
[8 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
ID | PORTFOLIO | STATUS | OWNER | DEPENDENCIES | START DATE | END DATE | DURATION | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | STATUS
1 | PRODUCT ID |  |  |  | 2025-01-20 | 2025-09-27 | 180 | [12 empty] | Not Started
1A | Release 1 | Complete |  |  | 2025-01-20 | 2025-04-12 | 60 | [12 empty] | In Progress
1B | Release 2 | In Progress |  |  | 2025-02-25 | 2025-06-30 | 90 | [12 empty] | Complete
1C | Release 3 | On Hold |  |  | 2025-05-15 | 2025-08-11 | 63 | [12 empty] | On Hold
1D | Release 4 | Needs Review |  |  | 2025-06-15 | 2025-09-27 | 75 | [12 empty] | Overdue
2 | PRODUCT ID |  |  |  | 2025-02-25 | 2025-11-05 | 182 | [12 empty] | Needs Review
2A | Release 1 | Overdue |  | 1A | 2025-02-25 | 2025-05-20 | 61 | [12 empty] | Canceled
2B | Release 2 | Not Started |  |  | 2025-04-01 | 2025-08-03 | 89
2C | Release 3 | Not Started |  |  | 2025-06-25 | 2025-09-20 | 63
2D | Release 4 | Not Started |  |  | 2025-07-21 | 2025-11-05 | 78
3 | PRODUCT ID |  |  |  | 2025-04-12 | 2025-11-30 | 165
3A | Release 1 |  |  | 1D | 2025-04-12 | 2025-07-13 | 65
3B | Release 2 |  |  |  | 2025-05-23 | 2025-09-27 | 91
3C | Release 3 |  |  |  | 2025-08-15 | 2025-11-12 | 64
3D | Release 4 |  |  |  | 2025-09-08 | 2025-11-30 | 60
4 | PRODUCT ID |  |  |  | 2025-06-01 | 2025-12-22 | 146
4A | Release 1 |  |  | 1A, 2A | 2025-06-01 | 2025-07-29 | 42
4B | Release 2 |  |  |  | 2025-07-08 | 2025-11-14 | 94
4C | Release 3 |  |  |  | 2025-09-20 | 2025-11-14 | 40
4D | Release 4 |  |  |  | 2025-09-22 | 2025-12-22 | 66
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
DURATION = NETWORKDAYS([START DATE],[END DATE])

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.