## Release Plan Gantt Chart
RELEASE PLAN GANTT CHART TEMPLATE
TASK NAME | START DATE | END DATE | DURATION in days | % COMPLETE
Research and Analysis | 2025-10-01 | 2025-10-24 | 24 | 100%
Requirements | 2025-10-25 | 2025-10-29 | 5 | 20%
Design | 2025-11-01 | 2025-11-13 | 13 | 30%
Review | 2025-11-13 | 2025-11-15 | 3 | 40%
Development | 2025-10-25 | 2025-12-20 | 57 | 0%
Feature A | 2025-10-29 | 2025-12-09 | 42 | 0%
Feature B | 2025-11-19 | 2025-12-10 | 22 | 0%
Feature C | 2025-11-22 | 2025-12-15 | 24 | 0%
Feature D | 2025-11-29 | 2025-12-20 | 22 | 0%
Testing | 2025-12-10 | 2025-12-22 | 13 | 0%
Marketing | 2025-12-10 | 2025-12-15 | 6 | 0%
Technical Support / Sales Training | 2025-12-27 | 2025-12-30 | 4 | 0%
Launch | 2026-01-02 | 2026-01-02 | 1 | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Release Plan Gantt Chart
RELEASE PLAN GANTT CHART TEMPLATE
TASK NAME | START DATE | END DATE | DURATION in days | % COMPLETE
Research and Analysis |  |  | 1 | 0%
Requirements |  |  | 1 | 0%
Design |  |  | 1 | 0%
Review |  |  | 1 | 0%
Development |  |  | 1 | 0%
Feature A |  |  | 1 | 0%
Feature B |  |  | 1 | 0%
Feature C |  |  | 1 | 0%
Feature D |  |  | 1 | 0%
Testing |  |  | 1 | 0%
Marketing |  |  | 1 | 0%
Technical Support / Sales Training |  |  | 1 | 0%
Launch |  |  | 1 | 0%
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.