## Business Planning Checklist
BUSINESS PLANNING CHECKLIST WITH TIMELINE
COMPANY NAME |  |  | START DATE
2025-09-02
[6 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7
DONE | TASKS | TASK OWNER | START | END | DAYS | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | DONE
X | Phase 1: Assess the Need |  | 2025-09-02 | 2025-09-05 | 4 | [35 empty] | X | bar: 2025-09-01 to 2025-10-17
X | Clearly identify the problem and solution |  | 2025-09-02 | 2025-09-02 | 1 | bar: 2025-09-02
X | Research existing alternatives |  | 2025-09-02 | 2025-09-02 | 1 | bar: 2025-09-02
X | Pinpoint gaps in existing products or services |  | 2025-09-03 | 2025-09-03 | 1 | bar: 2025-09-03
X | Determine skills, equipment, and materials needed |  | 2025-09-04 | 2025-09-04 | 1 | bar: 2025-09-04
X | Decide whether to proceed |  | 2025-09-05 | 2025-09-05 | 1 | bar: 2025-09-05
| Phase 2: Find Opportunity and Check Viability |  | 2025-09-05 | 2025-09-19 | 11 | bar: 2025-09-01 to 2025-10-17
X | Define your mission |  | 2025-09-05 | 2025-09-05 | 1 | bar: 2025-09-05
X | Research market |  | 2025-09-05 | 2025-09-05 | 1 | bar: 2025-09-05
X | Conduct interviews with stakeholders and SMEs |  | 2025-09-08 | 2025-09-12 | 5 | bar: 2025-09-08 to 2025-09-12
| Identify needed resources |  | 2025-09-11 | 2025-09-15 | 3 | bar: 2025-09-11 to 2025-09-15
| Identify startup costs |  | 2025-09-15 | 2025-09-16 | 2 | bar: 2025-09-15 to 2025-09-16
| Identify operating costs |  | 2025-09-15 | 2025-09-16 | 2 | bar: 2025-09-15 to 2025-09-16
| Determine sources of funding |  | 2025-09-17 | 2025-09-17 | 1 | bar: 2025-09-17
| Assess profitability |  | 2025-09-18 | 2025-09-19 | 2 | bar: 2025-09-18 to 2025-09-19
| Phase 3: Evaluate Potential Risks |  | 2025-09-15 | 2025-09-25 | 9 | bar: 2025-09-01 to 2025-10-17
| Assess market size |  | 2025-09-15 | 2025-09-17 | 3 | bar: 2025-09-15 to 2025-09-17
| Estimate competition |  | 2025-09-17 | 2025-09-18 | 2 | bar: 2025-09-17 to 2025-09-18
| Conduct SWOT analysis |  | 2025-09-18 | 2025-09-19 | 2 | bar: 2025-09-18 to 2025-09-19
| Assess economic climate |  | 2025-09-19 | 2025-09-23 | 3 | bar: 2025-09-19 to 2025-09-23
| Develop strategic plan |  | 2025-09-24 | 2025-09-25 | 2 | bar: 2025-09-24 to 2025-09-25
| Phase 4: Attract Stakeholders |  | 2025-09-25 | 2025-10-07 | 9 | bar: 2025-09-01 to 2025-10-17
| Establish management team |  | 2025-09-25 | 2025-09-29 | 3 | bar: 2025-09-25 to 2025-09-29
| Seek strategic partnerships |  | 2025-09-30 | 2025-10-03 | 4 | bar: 2025-09-30 to 2025-10-03
| Develop outreach plan |  | 2025-10-03 | 2025-10-07 | 3 | bar: 2025-10-03 to 2025-10-07
| Phase 5: Prepare and Pitch Business Plan |  | 2025-09-25 | 2025-10-07 | 9 | bar: 2025-09-01 to 2025-10-17
| Create business plan outline |  | 2025-09-25 | 2025-09-29 | 3 | bar: 2025-09-25 to 2025-09-29
| Fill in each section of business plan |  | 2025-09-30 | 2025-10-03 | 4 | bar: 2025-09-30 to 2025-10-03
| Develop investor pitch deck |  | 2025-10-03 | 2025-10-07 | 3 | bar: 2025-10-03 to 2025-10-07
| Phase 6: Establish Supporting Systems |  | 2025-10-07 | 2025-10-14 | 6 | bar: 2025-09-01 to 2025-10-17
| Create bookkeeping systems |  | 2025-10-07 | 2025-10-08 | 2 | bar: 2025-10-07 to 2025-10-08
| Create manuals and policies |  | 2025-10-08 | 2025-10-10 | 3 | bar: 2025-10-08 to 2025-10-10
| Create company portal to store key documents |  | 2025-10-10 | 2025-10-14 | 3 | bar: 2025-10-10 to 2025-10-14
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Bus. Planning Checklist
BUSINESS PLANNING CHECKLIST WITH TIMELINE
COMPANY NAME |  |  | START DATE
|  |  | 2025-09-02 |  |  | <-- Enter initial Start Date to populate Timeline dates.
[6 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
DONE | TASKS | TASK OWNER | START DATE | END DATE | DAYS | [100 empty] | DONE | time axis 2025-09-01 to 2026-01-16
X | Phase 1: Assess the Need |  | 0 | 0 | 0 | [100 empty] | X
X | Clearly identify the problem and solution |  |  |  | 0
X | Research existing alternatives |  |  |  | 0
X | Pinpoint gaps in existing products or services |  |  |  | 0
X | Determine skills, equipment, and materials needed |  |  |  | 0
X | Decide whether to proceed |  |  |  | 0
| Phase 2: Find Opportunity and Check Viability |  | 0 | 0 | 0
X | Define your mission |  |  |  | 0
X | Research market |  |  |  | 0
X | Conduct interviews with stakeholders and SMEs |  |  |  | 0
| Identify needed resources |  |  |  | 0
| Identify startup costs |  |  |  | 0
| Identify operating costs |  |  |  | 0
| Determine sources of funding |  |  |  | 0
| Assess profitability |  |  |  | 0
| Phase 3: Evaluate Potential Risks |  | 0 | 0 | 0
| Assess market size |  |  |  | 0
| Estimate competition |  |  |  | 0
| Conduct SWOT Analysis |  |  |  | 0
| Assess economic climate |  |  |  | 0
| Develop strategic plan |  |  |  | 0
| Phase 4: Attract Stakeholders |  | 0 | 0 | 0
| Establish management team |  |  |  | 0
| Seek strategic partnerships |  |  |  | 0
| Develop outreach plan |  |  |  | 0
| Phase 5: Prepare and Pitch Business Plan |  | 0 | 0 | 0
| Create business plan outline |  |  |  | 0
| Fill in each section of business plan |  |  |  | 0
| Develop investor pitch deck |  |  |  | 0
| Phase 6: Establish Supporting Systems |  | 0 | 0 | 0
| Create bookkeeping systems |  |  |  | 0
| Create manuals and policies |  |  |  | 0
| Create company portal to store key documents |  |  |  | 0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.