## ISO 9001
GET READY TO GET CERTIFIED FOR ISO 9001 TEMPLATE
TASK ID | TASK TITLE | START DATE | DUE DATE | DURATION
1 | ISO 9001:2015 Implementation | 2021-11-02 | 2022-05-03 | 183
2 | Prepare your organization | 2021-11-02 | 2021-11-08 | 7
3 | Understand your organization and its context | 2021-11-02 | 2021-11-08 | 7
4 | Understand the needs and expectations of interested parties | 2021-11-03 | 2021-11-08 | 6
5 | Achieve management commitment and leadership | 2021-11-02 | 2021-11-02 | 1
6 | Map your business processes | 2021-11-03 | 2021-11-08 | 6
7 | Purchase materials | 2021-11-05 | 2021-11-05 | 1
8 | Perform gap analysis | 2021-11-09 | 2021-11-15 | 7
9 | Read "What Is Gap Analysis?" | 2021-11-09 | 2021-11-09 | 1
10 | Review gap checklist for road map | 2021-11-10 | 2021-11-15 | 6
11 | Create a project plan | 2021-11-16 | 2021-11-22 | 7
12 | Do you need a team? | 2021-11-16 | 2021-11-16 | 1
13 | Will you hire outside contractors, audits, etc.? | 2021-11-16 | 2021-11-16 | 1
14 | Interview registrars | 2021-11-18 | 2021-11-22 | 5
15 | Train your organization | 2021-11-23 | 2021-11-30 | 8
16 | Train your internal auditors | 2021-11-23 | 2021-11-27 | 5
17 | Employee overview | 2021-11-30 | 2021-11-30 | 1
18 | Develop the documented information for the QMS | 2021-11-30 | 2022-02-10 | 73
19 | Redesign your existing processes to match the requirements of ISO 9001 | 2021-11-30 | 2022-01-19 | 51
20 | Planning for the QMS | 2021-11-30 | 2021-12-06 | 7
21 | Actions to address risks and opportunities - do risk management exercise | 2021-11-30 | 2021-12-06 | 7
22 | Management of resources | 2021-12-07 | 2021-12-20 | 14
23 | Control of monitoring and measuring resources | 2021-12-07 | 2021-12-20 | 14
24 | Competence, awareness, communication, organizational knowledge | 2021-12-07 | 2021-12-20 | 14
25 | Control of documented information | 2021-12-07 | 2021-12-20 | 14
26 | Operations | 2021-12-21 | 2022-01-19 | 30
27 | Customer-related processes | 2021-12-21 | 2021-12-23 | 3
28 | Design and development | 2021-12-28 | 2022-01-03 | 7
29 | Control of external providers | 2022-01-04 | 2022-01-10 | 7
30 | Control of production and service provision | 2022-01-07 | 2022-01-11 | 5
31 | Identification and traceability | 2022-01-11 | 2022-01-14 | 4
32 | Preservation | 2022-01-18 | 2022-01-19 | 2
33 | Control of nonconforming outputs | 2022-01-15 | 2022-01-17 | 3
34 | Performance evaluation | 2022-01-20 | 2022-01-31 | 12
35 | Monitoring, measurement, analysis, and evaluation | 2022-01-20 | 2022-01-29 | 10
36 | Customer satisfaction | 2022-01-20 | 2022-01-20 | 1
37 | Internal audits | 2022-01-20 | 2022-01-28 | 9
38 | Management review | 2022-01-28 | 2022-01-31 | 4
39 | Improvement | 2022-02-08 | 2022-02-10 | 3
40 | Nonconformity and corrective action | 2022-02-08 | 2022-02-10 | 3
41 | Continual improvement | 2022-02-08 | 2022-02-08 | 1
42 | Implement the QMS in your organization | 2022-02-08 | 2022-03-27 | 48
43 | Train staff on procedures/instructions | 2022-02-08 | 2022-03-27 | 48
44 | Make use of the documented information | 2022-02-08 | 2022-03-27 | 48
45 | Create work instructions where necessary | 2022-02-08 | 2022-03-27 | 48
46 | Receive orders / ship product while following QMS | 2022-02-08 | 2022-03-27 | 48
47 | Conduct internal audit of every process | 2022-03-28 | 2022-04-03 | 7
48 | Ensure people are following the QMS | 2022-03-28 | 2022-03-31 | 4
49 | Take corrective action | 2022-01-01 | 2022-04-03 | 93
50 | Hold management reviews | 2022-04-04 | 2022-04-17 | 14
51 | Decide on areas that need improvement | 2022-04-04 | 2022-04-13 | 10
52 | Evaluate actions taken to address risks and opportunities | 2022-04-14 | 2022-04-17 | 4
53 | Registration audit | 2022-04-18 | 2022-05-01 | 14
54 | Submit QMS documentation and audit records for stage 1 | 2022-04-18 | 2022-04-19 | 2
55 | Auditor visits your organization | 2022-04-21 | 2022-05-01 | 11
56 | Achieve ISO 9001 registration | 2022-05-03 | 2022-05-03 | 1
CLICK HERE TO CREATE IN SMARTSHEET

## Gantt Chart - BLANK
GANTT CHART
TASK ID | TASK TITLE | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
1 |  |  |  | 1 | 0%
2 |  |  |  | 1 | 0%
3 |  |  |  | 1 | 0%
4 |  |  |  | 1 | 0%
5 |  |  |  | 1 | 0%
6 |  |  |  | 1 | 0%
7 |  |  |  | 1 | 0%
8 |  |  |  | 1 | 0%
9 |  |  |  | 1 | 0%
10 |  |  |  | 1 | 0%
11 |  |  |  | 1 | 0%
12 |  |  |  | 1 | 0%
13 |  |  |  | 1 | 0%
14 |  |  |  | 1 | 0%
15 |  |  |  | 1 | 0%
16 |  |  |  | 1 | 0%
17 |  |  |  | 1 | 0%
18 |  |  |  | 1 | 0%
19 |  |  |  | 1 | 0%
20 |  |  |  | 1 | 0%
21 |  |  |  | 1 | 0%
22 |  |  |  | 1 | 0%
23 |  |  |  | 1 | 0%
24 |  |  |  | 1 | 0%
25 |  |  |  | 1 | 0%
26 |  |  |  | 1 | 0%
27 |  |  |  | 1 | 0%
28 |  |  |  | 1 | 0%
29 |  |  |  | 1 | 0%
30 |  |  |  | 1 | 0%
31 |  |  |  | 1 | 0%
32 |  |  |  | 1 | 0%
33 |  |  |  | 1 | 0%
34 |  |  |  | 1 | 0%
35 |  |  |  | 1 | 0%
36 |  |  |  | 1 | 0%
37 |  |  |  | 1 | 0%
38 |  |  |  | 1 | 0%
39 |  |  |  | 1 | 0%
40 |  |  |  | 1 | 0%
41 |  |  |  | 1 | 0%
42 |  |  |  | 1 | 0%
43 |  |  |  | 1 | 0%
44 |  |  |  | 1 | 0%
45 |  |  |  | 1 | 0%
46 |  |  |  | 1 | 0%
47 |  |  |  | 1 | 0%
48 |  |  |  | 1 | 0%
49 |  |  |  | 1 | 0%
50 |  |  |  | 1 | 0%
51 |  |  |  | 1 | 0%
52 |  |  |  | 1 | 0%
53 |  |  |  | 1 | 0%
54 |  |  |  | 1 | 0%
55 |  |  |  | 1 | 0%
56 |  |  |  | 1 | 0%
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.