## Day 1 – 30
SAMPLE 30-60-90-DAY BUSINESS PLAN FOR STARTUP TEMPLATE
PLAN TITLE |  |  |  | PREPARED BY
Startup Company 30-60-90-Day Business Plan |  |  |  | Miguel Sanchez
PURPOSE |  |  |  | DATE
To establish our business goals and deliverables and to create a 90-day plan of action to develop our business plan |  |  |  | 2025-05-26
|  |  | FIRST 30 DAYS START | FIRST 30 DAYS END
FIRST 30 DAYS |  |  | 2025-06-01 | 2025-06-30
MAIN GOALS |  |  | DELIVERABLES
• Clearly define the problem to solve. • Clearly define the solution to the problem. • Decide whether to proceed with the business idea. |  |  | • Problem / Opportunity Statement • Market Research Report
DAY 1 – 30 PLAN
ID | TASK | DESCRIPTION | ASSIGNED TO | DATE DUE | START DATE | END DATE | DURATION in days
1 | Write down a summary of the problem. |  |  | 2025-06-01 | 2025-06-01 | 2025-06-01 | 1
2 | Research the problem to identify factors that contribute to or worsen it. |  |  | 2025-06-04 | 2025-06-01 | 2025-06-04 | 4
3 | Write down facts and statistics related to the problem. |  |  | 2025-06-05 | 2025-06-05 | 2025-06-05 | 1
M1 | Milestone - Goal 1 | Define the problem you are solving. |  | 2025-06-05 | 2025-06-04 | 2025-06-05 | 2
4 | Brainstorm and list ideas. |  |  | 2025-06-14 | 2025-06-08 | 2025-06-14 | 7
5 | Evaluate and refine your list of ideas. |  |  | 2025-06-17 | 2025-06-15 | 2025-06-17 | 3
6 | Decide which ideas are most feasible. | Interview relevant experts and determine business scenarios. |  | 2025-06-21 | 2025-06-18 | 2025-06-21 | 4
7 | Conduct formal assessments of your concept. | Pre-feasibility study |  | 2025-06-21 | 2025-06-18 | 2025-06-21 | 4
8 | Narrow down your ideas by process of elimination. |  |  | 2025-06-22 | 2025-06-22 | 2025-06-22 | 1
M2 | Milestone – Goal 2 | Define the solution to the problem. |  | 2025-06-23 | 2025-06-21 | 2025-06-23 | 3
9 | Conduct research on existing solutions to the problem. |  |  | 2025-06-26 | 2025-06-23 | 2025-06-26 | 4
10 | Conduct research on competitors. |  |  | 2025-06-26 | 2025-06-23 | 2025-06-26 | 4
11 | Identify gaps or opportunities that make your solution better. |  |  | 2025-06-26 | 2025-06-23 | 2025-06-26 | 4
12 | Define who is impacted by the problem. |  |  | 2025-06-26 | 2025-06-23 | 2025-06-26 | 4
13 | Gather information on the customers of competitors. | Conduct interviews, send surveys, observe customers. |  | 2025-06-29 | 2025-06-26 | 2025-06-29 | 4
14 | Get feedback from customers on your business idea. |  |  | 2025-06-29 | 2025-06-26 | 2025-06-29 | 4
M3 | Milestone – Goal 3 | Decide whether to proceed. |  | 2025-06-30 | 2025-06-29 | 2025-06-30 | 2
CLICK HERE TO CREATE IN SMARTSHEET
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Day 30 – 60
SAMPLE 30-60-90-DAY BUSINESS PLAN FOR STARTUP TEMPLATE
|  |  | FIRST 30 DAYS START | FIRST 30 DAYS END
DAYS 30 – 60 |  |  | 2025-07-01 | 2025-07-30
MAIN GOALS |  |  | DELIVERABLES
• Pinpoint the target buyer. • Develop a business model. • Seek strategic partnerships. |  |  | • SWOT Analysis • Marketing Plan • Operational Plan • Business Model
DAY 30 – 60 PLAN
ID | TASK | DESCRIPTION | ASSIGNED TO | DATE DUE | START DATE | END DATE | DURATION in days
1 | Conduct market research. | Get an in-depth view of the competitive landscape. |  | 2025-07-05 | 2025-07-01 | 2025-07-05 | 5
2 | Determine the niche market to target. |  |  | 2025-07-07 | 2025-07-01 | 2025-07-07 | 7
3 | Identify the buyer pain points. |  |  | 2025-07-07 | 2025-07-02 | 2025-07-07 | 6
4 | Develop your competitive advantage. | Determine how you will set yourself apart from competitors. |  | 2025-07-09 | 2025-07-05 | 2025-07-09 | 5
5 | Research target market segments. | Demographics, psychographics, problems they are facing |  | 2025-07-10 | 2025-07-06 | 2025-07-10 | 5
6 | Research industry reports related to your product and industry. |  |  | 2025-07-10 | 2025-07-07 | 2025-07-10 | 4
M1 | Milestone - Goal 1 | Pinpoint the target buyer. |  | 2025-07-10 | 2025-07-08 | 2025-07-10 | 3
7 | Determine the key business activities. |  |  | 2025-07-13 | 2025-07-11 | 2025-07-13 | 3
8 | Identify the business resources you need. | Capital, intellectual property, office space, equipment, talent |  | 2025-07-17 | 2025-07-12 | 2025-07-17 | 6
9 | Conduct a SWOT Analysis. |  |  | 2025-07-13 | 2025-07-13 | 2025-07-13 | 1
10 | Determine the process to manufacture the product. |  |  | 2025-07-17 | 2025-07-14 | 2025-07-17 | 4
11 | Determine the process to get the product to the customer. |  |  | 2025-07-17 | 2025-07-15 | 2025-07-17 | 3
12 | Develop your unique value proposition. | Bring lasting value to customers. |  | 2025-07-19 | 2025-07-16 | 2025-07-19 | 4
M2 | Milestone – Goal 2 | Develop a business model. |  | 2025-07-21 | 2025-07-17 | 2025-07-21 | 5
13 | Research local retailers that align with your brand and product. |  |  | 2025-07-22 | 2025-07-18 | 2025-07-22 | 5
14 | Research advertising partners. |  |  | 2025-07-24 | 2025-07-20 | 2025-07-24 | 5
15 | Evaluate the costs and benefits of partnerships. |  |  | 2025-07-25 | 2025-07-22 | 2025-07-25 | 4
M3 | Milestone – Goal 3 | Seek strategic partnerships. |  | 2025-07-30 | 2025-07-25 | 2025-07-30 | 6
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Day 60 – 90
SAMPLE 30-60-90-DAY BUSINESS PLAN FOR STARTUP TEMPLATE
|  |  | FIRST 30 DAYS START | FIRST 30 DAYS END
DAYS 60 – 90 |  |  | 2025-07-31 | 2025-08-29
MAIN GOALS |  |  | DELIVERABLES
• Develop a sales plan. • Develop a financial plan. • Finalize your business plan. |  |  | • Sales Plan • Financial Plan • Business Plan • Investor Pitch Deck
DAY 60 – 90 PLAN
ID | TASK | DESCRIPTION | ASSIGNED TO | DATE DUE | START DATE | END DATE | DURATION in days
1 | Define the sales targets for your business. | Align your goals and strategies with the needs of the target market. |  | 2025-08-02 | 2025-07-31 | 2025-08-02 | 3
2 | Outline the steps to take to achieve your sales goals. |  |  | 2025-08-04 | 2025-08-03 | 2025-08-04 | 2
3 | Develop a sales enablement strategy. |  |  | 2025-08-06 | 2025-08-05 | 2025-08-06 | 2
4 | Create a forecast of sales you expect to reach. | 1-3 year sales forecast |  | 2025-08-07 | 2025-08-06 | 2025-08-07 | 2
5 | Determine the systems to put in place to support your product sales. |  |  | 2025-08-08 | 2025-08-06 | 2025-08-08 | 3
M1 | Milestone - Goal 1 | Develop your sales plan. |  | 2025-08-09 | 2025-08-08 | 2025-08-09 | 2
6 | Identify your input costs. |  |  | 2025-08-11 | 2025-08-10 | 2025-08-11 | 2
7 | Establish the selling price of your product. |  |  | 2025-08-12 | 2025-08-11 | 2025-08-12 | 2
8 | Conduct a break-even-point analysis. |  |  | 2025-08-13 | 2025-08-12 | 2025-08-13 | 2
9 | Prepare a startup budget. |  |  | 2025-08-14 | 2025-08-13 | 2025-08-14 | 2
10 | Prepare a pro forma balance sheet. |  |  | 2025-08-15 | 2025-08-14 | 2025-08-15 | 2
11 | Prepare a pro forma income statement. |  |  | 2025-08-16 | 2025-08-15 | 2025-08-16 | 2
12 | Prepare a pro forma cash flow statement. |  |  | 2025-08-17 | 2025-08-16 | 2025-08-17 | 2
13 | Prepare a sources and uses of funds statement. |  |  | 2025-08-18 | 2025-08-17 | 2025-08-18 | 2
M2 | Milestone – Goal 2 | Develop your financial plan. |  | 2025-08-22 | 2025-08-18 | 2025-08-22 | 5
14 | Document your current and future business goals. | Determine SMART goals for the next 1-3 years. |  | 2025-08-25 | 2025-08-23 | 2025-08-25 | 3
15 | Develop your mission and vision statement. |  |  | 2025-08-26 | 2025-08-25 | 2025-08-26 | 2
16 | Document your management team. | Brief bio, including relevant experience that brings value |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | 1
17 | Detail your product and service offerings. | Convey how they meet the needs of buyers, and provide details on future offerings. |  | 2025-08-29 | 2025-08-27 | 2025-08-29 | 3
18 | Define the structure of your company. |  |  | 2025-08-29 | 2025-08-27 | 2025-08-29 | 3
19 | Summarize the company history. | When the business started and key milestones |  | 2025-08-29 | 2025-08-27 | 2025-08-29 | 3
M3 | Milestone – Goal 3 | Finalize your business plan. |  | 2025-08-29 | 2025-08-29 | 2025-08-29 | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.