## Product Launch Template
PRODUCT LAUNCH TEMPLATE
PRODUCT LAUNCH PLAN |  |  |  | START DATE
2025-03-31
Use "BLANK" version tab for additional Task listings and weeks. | [6 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7
TASK NAME | STATUS | PRIORITY | TASK OWNER | START DATE | END DATE | # of Days | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | STATUS | PRIORITY
PLANNING PHASE | In Progress | HIGH |  | 2025-03-31 | 2025-04-17 | 14 | [35 empty] | Not Started | LOW | bar: 2025-03-31 to 2025-05-16
Market Requirements Definition | In Progress | MED |  | 2025-03-31 | 2025-04-03 | 4 | [35 empty] | In Progress | MED | bar: 2025-03-31 to 2025-04-03
Business Case | On Hold | MED |  | 2025-04-02 | 2025-04-13 | 8 | [35 empty] | Complete | HIGH | bar: 2025-04-02 to 2025-04-11
Launch Plan | Overdue | HIGH |  | 2025-04-13 | 2025-04-17 | 4 | [35 empty] | On Hold | bar: 2025-04-14 to 2025-04-17
Target Metrics | Needs Review | LOW |  | 2025-04-11 | 2025-04-11 | 1 | [35 empty] | Overdue | bar: 2025-04-11
SALES TOOLS | In Progress | MED |  | 2025-04-17 | 2025-04-25 | 7 | [35 empty] | Needs Review | bar: 2025-03-31 to 2025-05-16
Prospect Presentation | Needs Update | LOW |  | 2025-04-17 | 2025-04-23 | 5 | [35 empty] | Needs Update | bar: 2025-04-17 to 2025-04-23
Demo | In Progress | HIGH |  | 2025-04-24 | 2025-04-25 | 2 | bar: 2025-04-24 to 2025-04-25
Competitive Positioning | Not Started | MED |  | 2025-04-23 | 2025-04-25 | 3 | bar: 2025-04-23 to 2025-04-25
– FAQ Sheet | Not Started | MED |  | 2025-04-23 | 2025-04-25 | 3 | bar: 2025-04-23 to 2025-04-25
PRODUCT MARKETING | Overdue | LOW |  | 2025-04-14 | 2025-04-30 | 13 | bar: 2025-03-31 to 2025-05-16
Pricing Strategy | On Hold | MED |  | 2025-04-14 | 2025-04-18 | 5 | bar: 2025-04-14 to 2025-04-18
Product Positioning | Complete | HIGH |  | 2025-04-15 | 2025-04-16 | 2 | bar: 2025-04-15 to 2025-04-16
– Define Audience | In Progress | LOW |  | 2025-04-17 | 2025-04-17 | 1 | bar: 2025-04-17
– Core Messaging | Overdue | LOW |  | 2025-04-21 | 2025-04-24 | 4 | bar: 2025-04-21 to 2025-04-24
– Executive Approval | Complete | LOW |  | 2025-04-25 | 2025-04-30 | 4 | bar: 2025-04-25 to 2025-04-30
SOCIAL | In Progress | MED |  | 2025-04-28 | 2025-05-01 | 4 | bar: 2025-03-31 to 2025-05-16
Define Social Media Strategy | Overdue | MED |  | 2025-04-28 | 2025-04-30 | 3 | bar: 2025-04-28 to 2025-04-30
Schedule Social Media Posts | Needs Review | MED |  | 2025-04-29 | 2025-05-01 | 3 | bar: 2025-04-29 to 2025-05-01
PRODUCT RELEASE | In Progress | HIGH |  | 2025-05-01 | 2025-05-16 | 12 | bar: 2025-03-31 to 2025-05-16
Alpha Release | In Progress | HIGH |  | 2025-05-01 | 2025-05-01 | 1 | bar: 2025-05-01
Beta Release | In Progress | MED |  | 2025-05-05 | 2025-05-05 | 1 | bar: 2025-05-05
V1 General Availability | In Progress | LOW |  | 2025-05-12 | 2025-05-12 | 1 | bar: 2025-05-12
R2 Press Event | In Progress | LOW |  | 2025-05-16 | 2025-05-16 | 1 | bar: 2025-05-16
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Product Launch
PRODUCT LAUNCH TEMPLATE
PRODUCT LAUNCH PLAN |  |  |  | START DATE
|  |  |  | 2025-03-31 |  |  | <-- Enter initial Start Date to populate Timeline dates.
User to complete non-shaded cells only. | [6 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
TASK NAME | STATUS | PRIORITY | TASK OWNER | START DATE | END DATE | # of Days | [100 empty] | STATUS | PRIORITY | time axis 2025-03-31 to 2025-08-15
PLANNING PHASE |  |  |  | 0 | 0 | 0 | [100 empty] | Not Started | LOW
Market Requirements Definition | [5 empty] | 0 | [100 empty] | In Progress | MED
Business Case | [5 empty] | 0 | [100 empty] | Complete | HIGH
Launch Plan | [5 empty] | 0 | [100 empty] | On Hold
Target Metrics | [5 empty] | 0 | [100 empty] | Overdue
[6 empty] | 0 | [100 empty] | Needs Review
[6 empty] | 0 | [100 empty] | Needs Update
SALES TOOLS |  |  |  | 0 | 0 | 0
Prospect Presentation | [5 empty] | 0
Demo | [5 empty] | 0
Competitive Positioning | [5 empty] | 0
– FAQ Sheet | [5 empty] | 0
0
0
PRODUCT MARKETING |  |  |  | 0 | 0 | 0
Pricing Strategy | [5 empty] | 0
Product Positioning | [5 empty] | 0
– Define Audience | [5 empty] | 0
– Core Messaging | [5 empty] | 0
– Executive Approval | [5 empty] | 0
0
SOCIAL |  |  |  | 0 | 0 | 0
Define Social Media Strategy | [5 empty] | 0
Schedule Social Media Posts | [5 empty] | 0
0
0
0
0
PRODUCT RELEASE |  |  |  | 0 | 0 | 0
Alpha Release | [5 empty] | 0
Beta Release | [5 empty] | 0
V1 General Availability | [5 empty] | 0
R2 Press Event | [5 empty] | 0
0
0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.