## EXAMPLE - Equipment Schedule
EQUIPMENT SCHEDULE TEMPLATE
TASK ID | TASK NAME | LOCATION | STAGE | RESPONSIBLE | PREDECESSORS | START | FINISH | DURATION in days | STATUS | NOTES | STATUS
1 | Moving to Site | Location 1 | Moving | Alex B. |  | 2025-09-03 | 2025-09-13 | 11 | Complete |  | Complete
2 | Active Equipment | Location 1 | In Use | Frank C. |  | 2025-09-03 | 2025-09-07 | 5 | Complete |  | Overdue
3 | Moving Equipment | Location 1 | Moving | Jacob S. | 2 | 2025-09-07 | 2025-09-12 | 6 | Complete |  | In Progress
4 | Maintenance | Location 1 | Inactive | Jacob S. | 3 | 2025-09-09 | 2025-09-13 | 5 | Complete |  | Not Started
5 | Maintenance | Location 1 | Moving | Jacob S. | 4 | 2025-09-16 | 2025-09-24 | 9 | In Progress |  | On Hold
6 | Maintenance | Location 2 | Inactive | Alex B. |  | 2025-09-16 | 2025-09-17 | 2 | In Progress
7 | Maintenance | Location 2 | Inactive | Frank C. |  | 2025-09-17 | 2025-09-21 | 5 | Overdue
8 | Active Equipment | Location 2 | In Use | Shari W. | 7 | 2025-09-22 | 2025-09-24 | 3 | On Hold
9 | Active Equipment | Location 2 | In Use | Shari W. | 8 | 2025-09-25 | 2025-10-05 | 11 | Not Started
10 | Active Equipment | Location 2 | In Use | Alex B. | 9 | 2025-09-25 | 2025-09-29 | 5 | Not Started
11 | Moving to Site | Location 2 | Moving | Kennedy K. | 10 | 2025-09-27 | 2025-10-02 | 6 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Equipment Schedule
EQUIPMENT SCHEDULE TEMPLATE
TASK ID | TASK NAME | LOCATION | STAGE | RESPONSIBLE | PREDECESSORS | START | FINISH | DURATION in days | STATUS | NOTES | STATUS
1 | [10 empty] | Complete
2 | [10 empty] | Overdue
3 | [10 empty] | In Progress
4 | [10 empty] | Not Started
5 | [10 empty] | On Hold
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
Double click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.