## Earned Value Management
EARNED VALUE MANAGEMENT TEMPLATE
PROJECT TITLE | Project Title Here |  |  |  | PREPARED BY | Name of PM or Other Preparer |  |  | DATE OF REPORT | 00/00/0000 |  | TIME PERIOD | 4
PLANNED VALUE – WBS IDs and Task Titles listed here will automatically populate on worksheet tabs.
WORK BRKDWN STRUCTURE | TASK TITLE | TOTAL BUDGETED COST | PERIOD
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | Task 1.1 | 1258 | 300 | 500 | 400 | 50 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.2 | Task 1.2 | 350 | 200 | 80 | 30 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Task 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | Task 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Task 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Task 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 | Task 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4 | Task 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | Task 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | Task 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 | Task 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3 | Task 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4 | Task 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5 | Task 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.6 | Task 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7 | Task 3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Task 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2 | Task 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 | Task 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Task 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TBC | TOTAL BUDGETED COST | 1608 | 500 | 580 | 430 | 90 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PV | CUMLATIVE PLANNED VALUE |  | 500 | 1080 | 1510 | 1600 | 1601 | 1602 | 1603 | 1604 | 1605 | 1606 | 1607 | 1608
ACTUAL COST
AC | CUMULATIVE ACTUAL COST |  | 900 | 1220 | 1480 | 1620 | 1621 | 1622 | 1623 | 1624 | 1625 | 1626 | 1627 | 1628
EARNED VALUE
EV | CUMULATIVE EARNED VALUE |  | 1356.4 | 1230.6 | 1363 | 520.7 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8
PROJECT PERFORMANCE METRICS
CV | COST VARIANCE | ( EV – AC ) | 456.4 | 10.6 | -117 | -1099.3 | -1495.2 | -1496.2 | -1497.2 | -1498.2 | -1499.2 | -1500.2 | -1501.2 | -1502.2
SV | SCHEDULE VARIANCE | ( EV – PV ) | 856.4 | 150.6 | -147 | -1079.3 | -1475.2 | -1476.2 | -1477.2 | -1478.2 | -1479.2 | -1480.2 | -1481.2 | -1482.2
CPI | COST PERFORMANCE INDEX | ( EV / AC ) | 1.5071 | 1.0087 | 0.92095 | 0.32142 | 0.077606 | 0.077559 | 0.077511 | 0.077463 | 0.077415 | 0.077368 | 0.07732 | 0.077273
SPI | SCHEDULE PERFORMANCE INDEX | ( EV / PV ) | 2.7128 | 1.1394 | 0.90265 | 0.32544 | 0.078576 | 0.078527 | 0.078478 | 0.078429 | 0.07838 | 0.078331 | 0.078283 | 0.078234
EAC | ESTIMATED COST AT COMPLETION |  | 1066.9419 | 1594.1492 | 1746.0308 | 5002.8039 | 20719.9364 | 20732.7186 | 20745.5008 | 20758.283 | 20771.0652 | 20783.8474 | 20796.6296 | 20809.4118
CLICK HERE TO CREATE IN SMARTSHEET

## Actual Cost Worksheet
EARNED VALUE MANAGEMENT TEMPLATE
PROJECT TITLE | Project Title Here |  |  |  | PREPARED BY | Name of PM or Other Preparer |  |  | DATE OF REPORT | 00/00/0000 |  | TIME PERIOD | 4
ACTUAL COST – Enter amount of actual costs incurred for each task per period.
WORK BRKDWN STRUCTURE | TASK TITLE | TOTAL BUDGETED COST | PERIOD
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | Task 1.1 | 1258 | 100 | 300 | 200 | 100 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.2 | Task 1.2 | 350 | 800 | 20 | 60 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Task 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | Task 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Task 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Task 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 | Task 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4 | Task 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | Task 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | Task 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 | Task 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3 | Task 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4 | Task 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5 | Task 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.6 | Task 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7 | Task 3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Task 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2 | Task 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 | Task 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Task 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AC | ACTUAL COST |  | 900 | 320 | 260 | 140 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CUMULATIVE ACTUAL COST |  | 900 | 1220 | 1480 | 1620 | 1621 | 1622 | 1623 | 1624 | 1625 | 1626 | 1627 | 1628

## Earned Value Worksheet
EARNED VALUE MANAGEMENT TEMPLATE
PROJECT TITLE | Project Title Here |  |  |  | PREPARED BY | Name of PM or Other Preparer |  |  | DATE OF REPORT | 00/00/0000 |  | TIME PERIOD | 4
CUMULATIVE EARNED VALUE – For each Task per Period, enter the Percentage Complete.
WORK BRKDWN STRUCTURE | TASK TITLE | TOTAL BUDGETED COST | PERIOD
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | Task 1.1 | 1258 | 80% | 70% | 100% | 40% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
1.2 | Task 1.2 | 350 | 100% | 100% | 30% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.3 | Task 1.3 | 0 | bar: PERIOD 1 to PERIOD 12
1.4 | Task 1.4 | 0 | bar: PERIOD 1 to PERIOD 12
2.1 | Task 2.1 | 0 | bar: PERIOD 1 to PERIOD 12
2.2 | Task 2.2 | 0 | bar: PERIOD 1 to PERIOD 12
2.3 | Task 2.3 | 0 | bar: PERIOD 1 to PERIOD 12
2.4 | Task 2.4 | 0 | bar: PERIOD 1 to PERIOD 12
2.5 | Task 2.5 | 0 | bar: PERIOD 1 to PERIOD 12
3.1 | Task 3.1 | 0 | bar: PERIOD 1 to PERIOD 12
3.2 | Task 3.2 | 0 | bar: PERIOD 1 to PERIOD 12
3.3 | Task 3.3 | 0 | bar: PERIOD 1 to PERIOD 12
3.4 | Task 3.4 | 0 | bar: PERIOD 1 to PERIOD 12
3.5 | Task 3.5 | 0 | bar: PERIOD 1 to PERIOD 12
3.6 | Task 3.6 | 0 | bar: PERIOD 1 to PERIOD 12
3.7 | Task 3.7 | 0 | bar: PERIOD 1 to PERIOD 12
4.1 | Task 4.1 | 0 | bar: PERIOD 1 to PERIOD 12
4.2 | Task 4.2 | 0 | bar: PERIOD 1 to PERIOD 12
4.3 | Task 4.3 | 0 | bar: PERIOD 1 to PERIOD 12
4.4 | Task 4.4 | 0 | bar: PERIOD 1 to PERIOD 12
EV | CUMULATIVE EARNED VALUE |  | 1356.4 | 1230.6 | 1363 | 520.7 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.