## Project Execution Plan
ENGINEERING PROJECT EXECUTION PLAN TEMPLATE
PROJECT NAME | [5 empty] | PROJECT MANAGER
PROJECT DELIVERABLE | [5 empty] | START DATE
00/00/0000
SCOPE STATEMENT | [5 empty] | END DATE
00/00/0000
OVERALL PROGRESS
15%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | COMMENTS | STATUS KEY
Set Kickoff Meeting | Alex B. | 2026-09-02 | 2026-09-03 | 2 | Complete |  | Not Started
Agree on Objectives | Frank C. | 2026-09-03 | 2026-09-07 | 5 | In Progress |  | In Progress
Detailed Requirements | Jacob S. | 2026-09-07 | 2026-09-12 | 6 | Overdue |  | Complete
Hardware Requirements | Jacob S. | 2026-09-09 | 2026-09-11 | 3 | Not Started |  | On Hold
Final Resource Plan | Jacob S. | 2026-09-11 | 2026-09-15 | 5 | On Hold |  | Overdue
Staffing | Alex B. | 2026-09-16 | 2026-09-17 | 2 | Needs Review |  | Needs Review
Technical Requirements | Frank C. | 2026-09-17 | 2026-09-21 | 5
DB Development | Shari W. | 2026-09-22 | 2026-09-24 | 3
API Development | Shari W. | 2026-09-23 | 2026-09-27 | 5
UI Client | Alex B. | 2026-09-25 | 2026-09-29 | 5
Testing | Kennedy K. | 2026-09-24 | 2026-10-02 | 9
Development Complete | Jacob S. | 2026-10-02 | 2026-10-05 | 4
Hardware Configuration | Alex B. | 2026-10-05 | 2026-10-07 | 3
System Testing | Kennedy K. | 2026-10-06 | 2026-10-09 | 4
Launch |  | 2026-10-10 | 2026-10-10 | 1
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Execution Plan
ENGINEERING PROJECT EXECUTION PLAN
PROJECT NAME | [5 empty] | PROJECT MANAGER
PROJECT DELIVERABLE | [5 empty] | START DATE
SCOPE STATEMENT
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | COMMENTS | STATUS KEY
Not Started
In Progress
Complete
On Hold
Overdue
Needs Review

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.