## Project Management Roadmap
PROJECT MANAGEMENT ROADMAP TEMPLATE
CAMPAIGN NAME |  |  | DATE | STATUS | % COMPLETE
|  |  | 00/00/00 | ON TRACK | 72%
WORKSTREAM TIMELINE
DASHBOARD DATA
WORKSTREAMS
DESCRIPTION | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS | STATUS | PRIORITY
WORKSTREAM 1 | 2024-01-02 | 2024-01-20 | 18 | On Schedule | High |  | On Schedule | High
W1 Task 1 | 2024-01-04 | 2024-01-11 | 7 | On Schedule | Medium |  | Needs Attention | Medium
W1 Task 2 | 2024-01-07 | 2024-01-11 | 4 | On Schedule | Low |  | Delayed | Low
W1 Task 3 | 2024-01-10 | 2024-01-15 | 5 | On Schedule | Low
W1 Task 4 | 2024-01-13 | 2024-01-20 | 7 | On Schedule | Low
WORKSTREAM 2 | 2024-01-16 | 2024-02-05 | 20 | Needs Attention | High
W2 Task 1 | 2024-01-19 | 2024-02-01 | 13 | Needs Attention | High
W2 Task 2 | 2024-01-22 | 2024-02-03 | 12 | On Schedule | High
W2 Task 3 | 2024-01-25 | 2024-02-05 | 11 | Delayed | High
WORKSTREAM 3 | 2024-01-28 | 2024-02-02 | 5 | Delayed | High
WORKSTREAM 4 | 2024-01-31 | 2024-02-06 | 6 | On Schedule | Medium
STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PROJECTED | 80000
On Schedule | 7 | 63.64% |  | USED | 50000
Needs Attention | 2 | 18.18% |  | REMAINING | 30000
Delayed | 2 | 18.18%
TOTAL | 11 | 100%
PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 6 | 54.55% |  | Actions | 2
Medium | 2 | 18.18% |  | Change Requests | 4
Low | 3 | 27.27%
| 0 | 0%
TOTAL | 11 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Mgmt Roadmap
PROJECT MANAGEMENT ROADMAP TEMPLATE
CAMPAIGN NAME |  |  | DATE | STATUS | % COMPLETE
|  |  | 00/00/00 | ON TRACK | 100% | Enter ROADMAP DATA in the tables beginning at row 8. Dashboard graphics will automatically populate.
WORKSTREAM TIMELINE
ROADMAP DATA
WORKSTREAMS
DESCRIPTION | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS | STATUS | PRIORITY
WORKSTREAM 1 |  |  | 0 |  |  |  | On Schedule | High
W1 Task 1 |  |  | 0 |  |  |  | Needs Attention | Medium
W1 Task 2 |  |  | 0 |  |  |  | Delayed | Low
W1 Task 3 |  |  | 0
W1 Task 4 |  |  | 0
WORKSTREAM 2 |  |  | 0
W2 Task 1 |  |  | 0
W2 Task 2 |  |  | 0
W2 Task 3 |  |  | 0
WORKSTREAM 3 |  |  | 0
WORKSTREAM 4 |  |  | 0
STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PROJECTED | 0
On Schedule | 0 |  |  | USED | 0
Needs Attention | 0 |  |  | REMAINING | 0
Delayed | 0
TOTAL | 0 | 0%
PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 0
High | 0 |  |  | Actions | 0
Medium | 0 |  |  | Change Requests | 0
Low | 0
0
TOTAL | 0 | 0%
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.