## Project Portfolio Proj. Track
PROJECT PORTFOLIO BUDGET TRACKING TEMPLATE
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIP. / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
1.0 | PROJECT 1
1.1 | Task | Not Started |  |  |  | 5 | 50 | 250 | 5000 | 0.03 | 150 |  |  |  |  | 0 | 800 | 400 | 400
1.2 | Task | In Progress |  |  |  | 25 | 35 | 875 |  |  | 0 |  |  |  |  | 0 | 1000 | 875 | 125
1.3 | Task | Complete |  |  |  | 40 | 75 | 3000 | 1 | 2600 | 2600 |  |  |  |  | 0 | 6000 | 5600 | 400
1.3a | Subtask | On Hold | [5 empty] | 0 |  |  | 0 |  | 5200 |  |  | 5200 | 5000 | 5200 | -200
1.3b | Subtask | Overdue | [5 empty] | 0 |  |  | 0 |  |  | 4000 |  | 4000 | 4000 | 4000 | 0
1.3c | Subtask | In Progress | [5 empty] | 0 |  |  | 0 |  |  |  | 1600 | 1600 | 500 | 1600 | -1100
1.3d | Subtask | In Progress | [5 empty] | 0 |  |  | 0 |  | 3200 |  |  | 3200 | 2500 | 3200 | -700
1.4 | Task | In Progress | [5 empty] | 0 | 5 | 350 | 1750 |  |  |  |  | 0 | 1500 | 1750 | -250
1.5 | Task | Not Started |  |  |  | 17 | 85 | 1445 |  |  | 0 |  |  |  |  | 0 | 2000 | 1445 | 555
[8 empty] | 5570 |  |  | 4500 | 0 | 8400 | 4000 | 1600 | 14000 | 23300 | 24070 | -770
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIP. / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
2.0 | PROJECT 2
2.1 | Task | Complete | [5 empty] | 0 | 15 | 480 | 7200 |  |  |  |  | 0 | 8500 | 7200 | 1300
2.2 | Task | On Hold | [5 empty] | 0 |  |  | 0 | 1800 |  |  |  | 1800 | 2200 | 1800 | 400
2.3 | Task | Overdue |  |  |  | 72 | 150 | 10800 |  |  | 0 |  |  |  |  | 0 | 14000 | 10800 | 3200
2.4 | Task | In Progress | [5 empty] | 0 |  |  | 0 |  |  |  | 1650 | 1650 | 2000 | 1650 | 350
2.5 | Task | Not Started | [5 empty] | 0 | 2 | 8000 | 16000 |  |  |  |  | 0 | 10000 | 16000 | -6000
2.6 | Task | Not Started | [5 empty] | 0 |  |  | 0 |  |  | 8600 |  | 8600 | 8600 | 8600 | 0
2.7 | Task | Not Started |  |  |  | 40 | 50 | 2000 |  |  | 0 |  |  |  |  | 0 | 3000 | 2000 | 1000
2.8 | Task | Not Started |  |  |  | 160 | 40 | 6400 |  |  | 0 |  |  |  |  | 0 | 7500 | 6400 | 1100
2.9 | Task | Not Started | [5 empty] | 0 |  |  | 0 |  | 14000 |  |  | 14000 | 18000 | 14000 | 4000
[8 empty] | 19200 |  |  | 23200 | 1800 | 14000 | 8600 | 1650 | 26050 | 73800 | 68450 | 5350
CLICK HERE TO CREATE IN SMARTSHEET
STATUS KEY
Not Started
In Progress
Complete
On Hold
Overdue

## Project Port. Proj. Trk - BLANK
MULTIPLE PROJECT BUDGET TRACKING TEMPLATE
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIPMENT / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
1.0 | PROJECT 1
1.1 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.2 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.3 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.3a | Subtask | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.3b | Subtask | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.3c | Subtask | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.3d | Subtask | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.4 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.5 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIPMENT / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
2.0 | PROJECT 2
2.1 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.2 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.3 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.4 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.5 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.6 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.7 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.8 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.9 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
STATUS KEY
Not Started
In Progress
Complete
On Hold
Overdue

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.