## EX - Project Communication Plan
SAMPLE PROJECT COMMUNICATION PLAN TEMPLATE
PROJECT TITLE |  |  |  | PROJECT MANAGER
Training System Overhaul |  |  |  | Isabelle
TEAM MEMBERS |  |  |  | START DATE
Daniel • Sam • Melissa • Nicole |  |  |  | 00/00/0000
KEY STAKEHOLDERS
NAME | TITLE |  | PREFERRED COMMUNICATION | ADDITIONAL INFORMATION
Tom | Client CEO |  | Email and Phone
Sarah | Internal CEO |  | Email and Slack
Devin | Internal CFO |  | Email
Wendy | Client COO |  | Email and Phone
COMMUNICATION GOALS
• Keep stakeholders informed of ongoing progress and any changes • Identify any roadblocks and resolve them early • Create opportunities for feedback from stakeholders and team
COMMUNICATION PLAN
ACTIVITY | TYPE | FREQUENCY | ATTENDING | PURPOSE
Project Planning Meeting | Video Conference | Once | Team members, key stakeholders, and project manager | Outline client goals, establish budget and timeline, and assign first milestone tasks
Team Touch Base | In Person | Daily | Team members and project manager | Set daily goals and update project manager on milestone status
Team Status Report | Email | Weekly | Team members and project manager | Summarize touch bases and outline achievements for week and goals for following week
Stakeholder Status Report | Email | Biweekly | Project manager and key stakeholders | Summarize progress and next steps and update timeline
Review Meeting | Video Conference | As needed and/or upon completion of milestones | Team members, key stakeholders, and project manager | Update client on progress, assign subsequent milestone tasks, and assess overall timeline
Post-Mortem Meeting / Lessons Learned Meeting | In Person | End of Project | Team members and project manager | Assess successes and failures of project processes and collect input for improvement of subsequent projects
CLICK HERE TO CREATE IN SMARTSHEET

## Project Communication Plan
PROJECT COMMUNICATION PLAN TEMPLATE
PROJECT TITLE |  |  |  | PROJECT MANAGER
TEAM MEMBERS |  |  |  | START DATE
KEY STAKEHOLDERS
NAME | TITLE |  | PREFERRED COMMUNICATION | ADDITIONAL INFORMATION
COMMUNICATION GOALS
COMMUNICATION PLAN
ACTIVITY | TYPE | FREQUENCY | ATTENDING | PURPOSE

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.