## WBS with Gantt Chart
Example WBS to Gantt Conversion
PROJECT TITLE | Galvin Residence - 1405 Maplewood Dr.
PROJECT MANAGER | Lucinda Evans
COMPANY NAME | CustomRight Homes
DATE | 2022-02-15 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
4 | Finishes
4.2 | Flooring | Sweeney Bros | 2022-03-12 | 2022-03-15 | 12 | 35%
4.2.2 | Living Room Flooring | Hardwoods Inc | 2022-04-15 | 2022-04-24 | 9 | 60%
4.2.2.1 | Lay subfloor | Hardwoods Inc | 2023-04-15 | 2022-04-16 | 1
4.2.2.2 | Install hardwood floor | Hardwoods Inc | 2022-04-15 | 2022-04-16 | 1
4.2.2.3 | Sand floor | Hardwoods Inc | 2022-04-16 | 2022-04-16 | 1
4.2.2.4 | Seal floor | Hardwoods Inc | 2022-04-17 | 2022-04-17 | 1
4.2.2.5 | Dry time | Hardwoods Inc | 2022-04-18 | 2022-04-19 | 2
4.2.2.6 | Top coat | Hardwoods Inc | 2022-04-20 | 2022-04-20 | 1
4.2.2.7 | Dry time | Hardwoods Inc | 2022-04-21 | 2022-04-22 | 2
4.2.1 | Kitchen Flooring | Sweeney Bros | 2022-04-15 | 2022-04-16 | 1 | 0%
4.1 | Painting | PaintBoys | 2022-04-20 | 2022-05-03 | 13 | 40%
4.1.2 | Living Room Painting | Allen W | 2022-03-17 | 2022-03-22 | 2 | 0%
4.1.2 | Kitchen Painting | Malik M | 2022-03-18 | 2022-03-22 | 4 | 60%
1.6 | Upstairs Painting | Malik M | 2022-03-23 | 2022-03-23 | 0 | 50%
2 | Foundation | Brent Concrete
2.1 |  |  |  |  | 0 | 0%
2.2 |  |  |  |  | 0 | 0%
2.3 |  |  |  |  | 0 | 0%
2.4 |  |  |  |  | 0 | 0%
3 | Roof | A+ Roofing
3.1 |  |  |  |  | 0 | 0%
3.2 |  |  |  |  | 0 | 0%
3.2.1 |  |  |  |  | 0 | 0%
3.2.2 |  |  |  |  | 0 | 0%
3.3 |  |  |  |  | 0 | 0%
3.3.1 |  |  |  |  | 0 | 0%
4 | Electrical | Aloha Electrical
4.1 |  |  |  |  | 0 | 0%
4.2 |  |  |  |  | 0 | 0%
4.3 |  |  |  |  | 0 | 0%
4.4 |  |  |  |  | 0 | 0%
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])

## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.