## Moving Inventory Checklist
MOVING INVENTORY CHECKLIST TEMPLATE
MOVE CHECKLIST / TIMELINE
X | EIGHT WEEKS BEFORE | DATE DUE | STATUS | DATE COMPLETE | ASSIGNED TO | NOTES | STATUS KEY
X | Approve new furniture layout for private offices | 07/15/20XX | Complete | 07/15/20XX | Brent |  | Not Started
| Approve new furniture layout for common areas | 07/15/20XX | In Progress |  | Lori | Need to send layout for approval | In Progress
| Confirm delivery dates for new furniture | 07/15/20XX | Not Started |  | Brent |  | Complete
| Issue RFP to potential movers | 07/15/20XX | Overdue |  | Lori |  | On Hold
| Select move team / department coordinators | 07/15/20XX | On Hold |  | Lori |  | Overdue
X | Recommendation to Award to mover | 07/15/20XX | Complete | 07/15/20XX | Lori | 1 - United Movers, 2 - All Star Movers | Needs Review
| Approve new furniture layout for outdoor areas | 07/15/20XX | Needs Review |  | Brent
X | SIX WEEKS BEFORE | DATE DUE | STATUS | DATE COMPLETE | ASSIGNED TO | NOTES
| Meet with team and assign responsibilities | 08/02/20XX | In Progress
| Select mover | 08/02/20XX | In Progress
| Identify insurance requirements-move weekend | 08/02/20XX | Not Started
| Obtain insurance certificate from mover | 08/02/20XX | Overdue
| Finalize seat assignments | 08/02/20XX | On Hold
| Confirm incoming new extension numbers | 08/02/20XX | On Hold
| Assign extensions / direct dials | 08/02/20XX | In Progress
| Notify insurance carrier of relocation | 08/02/20XX | In Progress
| Issue insurance certificate to new landlord | 08/02/20XX | In Progress
| Order new services (cleaning, landscaping) | 08/02/20XX | Needs Review
X | FOUR WEEKS BEFORE | DATE DUE | STATUS | DATE COMPLETE | ASSIGNED TO | NOTES
Present to employees
Present building information to employees
Notify vendors
Copier
Coffee Service
Water Service
Postage meter
Plants
Magazines / newspapers
Vendors with standing orders & pick-ups
Notify post office of address change
Order change of address cards
Develop list for change of address cards
Order stationery and business cards
Confirm date with movers
Reserve loading dock & elevators
Freeze changes on seat assignments
Assign move codes
Identify locations for printers / fax machines
X | THREE WEEKS BEFORE | DATE DUE | STATUS | DATE COMPLETE | ASSIGNED TO | NOTES
Schedule wiring according to the construction timeline for newly-built or renovated space
Identify the telephone and data cabling close/room within the space
Test all power outlets using a tester as well as by plugging something in
Map the locations of the desks and use a mapping tool to estimate cable sizes
Plan for extra wiring drops.
Verify all backup batteries for phone switches and servers are installed according to schedule
If using an 800 phone number, confirm plans with vendor for cutover date and time.
Test new telephone line several days before the move
Review programming/routing on voicemail system for required changes.
Disconnect all leased lines, such as T1s at old location
If company web address is hosted internally, verify if change to DNS resolution is required.
X | ONE WEEK BEFORE | DATE DUE | STATUS | DATE COMPLETE | ASSIGNED TO | NOTES
Deliver boxes and labels
Distribute access cards / IDs
Prepare emergency contact list
Phone training for employees
X | TWO DAYS BEFORE | DATE DUE | STATUS | DATE COMPLETE | ASSIGNED TO | NOTES
Deliver additional boxes and labels
Label origin and destination for movers
Confirm all vendors and times
X | MOVE IN DAY / SETTLE IN | DATE DUE | STATUS | DATE COMPLETE | ASSIGNED TO | NOTES
Place orientation packages at destination
Hang whiteboards / artwork
Remove excess furniture
Remove crates & packing materials
CLICK HERE TO CREATE IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.