## Construction Project Budget
CONSTRUCTION PROJECT BUDGET TEMPLATE
[7 empty] | BUDGET | ACTUAL | UNDER/OVER
[7 empty] | 0 | 0 | 0
|  | LABOR |  | MATERIALS |  | FIXED COST
TASK | VENDOR / CONTRACTOR | HRS | RATE | UNITS | $/UNIT | AMOUNT | BUDGET | ACTUAL | UNDER/OVER
GENERAL REQUIREMENTS
Plans & Specifications | Vendor Name | [5 empty] | 0 |  | 0
Plan Review | [6 empty] | 0 |  | 0
Permits: Zoning, Building, Environmental, Other | [6 empty] | 0 |  | 0
Survey | [6 empty] | 0 |  | 0
Impact Fee | [6 empty] | 0 |  | 0
Administrative Costs | [6 empty] | 0 |  | 0
Financing Costs | [6 empty] | 0 |  | 0
Legal Fees | [6 empty] | 0 |  | 0
Engineering Fees | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
SITE PREP
Demolition (Remodel) | [6 empty] | 0 |  | 0
Jacking & Shoring (Remodel) | [6 empty] | 0 |  | 0
Dust Control, Surface Protection | [6 empty] | 0 |  | 0
Job-Site Access | [6 empty] | 0 |  | 0
Job-Site Security | [6 empty] | 0 |  | 0
Dumpster & Removal | [6 empty] | 0 |  | 0
Clear Lot | [6 empty] | 0 |  | 0
Storage On Site | [6 empty] | 0 |  | 0
Portable Toilet | [6 empty] | 0 |  | 0
Temporary Power | [6 empty] | 0 |  | 0
Temporary Heat | [6 empty] | 0 |  | 0
Scaffolding Rental | [6 empty] | 0 |  | 0
Tool/Equipment Rental | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
ON-SITE WATER/SEWER
Soil & Perc Tests | [6 empty] | 0 |  | 0
Septic System Design | [6 empty] | 0 |  | 0
Septic Permits, Inspections, Fees | [6 empty] | 0 |  | 0
Septic System Installation, Tie in to House | [6 empty] | 0 |  | 0
Dewatering (High-Water Table) | [6 empty] | 0 |  | 0
Well, Pump, Trenching, Plumbing to House | [6 empty] | 0 |  | 0
Well Permits & Fees | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
UTILITIES
Town Water: Tap Fees & Hookup | [6 empty] | 0 |  | 0
Town Sewer: Tap Fees & Hookup | [6 empty] | 0 |  | 0
Electrical: Permit, Connection Fee, Installation | [6 empty] | 0 |  | 0
Gas: Permit, Connection Fee, Installation | [6 empty] | 0 |  | 0
LPN: Tank installation, Hookup | [6 empty] | 0 |  | 0
Oil Tank Installation | [6 empty] | 0 |  | 0
Telecom Hookup | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
EXCAVATION & EARTHWORK
Cut & Fill | [6 empty] | 0 |  | 0
Blasting | [6 empty] | 0 |  | 0
Removal of Stone/Dirt | [6 empty] | 0 |  | 0
Rough Grading | [6 empty] | 0 |  | 0
Trenching for Utility Hookups | [6 empty] | 0 |  | 0
Foundation Excavation | [6 empty] | 0 |  | 0
Foundation Footing Drains | [6 empty] | 0 |  | 0
Curtain Drains | [6 empty] | 0 |  | 0
Culverts | [6 empty] | 0 |  | 0
Swales | [6 empty] | 0 |  | 0
Retaining Walls | [6 empty] | 0 |  | 0
Ponds | [6 empty] | 0 |  | 0
Other Site Drainage | [6 empty] | 0 |  | 0
Backfill | [6 empty] | 0 |  | 0
Compaction | [6 empty] | 0 |  | 0
Top Soil | [6 empty] | 0 |  | 0
Finish Grading | [6 empty] | 0 |  | 0
Seeding/Sod | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
FOUNDATION
Footings/Pads | [6 empty] | 0 |  | 0
Foundation Walls/Stem Walls/Grade Beams | [6 empty] | 0 |  | 0
Piers | [6 empty] | 0 |  | 0
Slabs - Foundation, Basement, Garage | [6 empty] | 0 |  | 0
Steel Reinforcing | [6 empty] | 0 |  | 0
Anchor Bolts, Hold Downs | [6 empty] | 0 |  | 0
Bulkheads | [6 empty] | 0 |  | 0
Sub-Slab Vapor Barrier | [6 empty] | 0 |  | 0
Sump Pump | [6 empty] | 0 |  | 0
Crawlspace Vapor Barrier | [6 empty] | 0 |  | 0
Crawlspace Vents | [6 empty] | 0 |  | 0
Foundation Windows | [6 empty] | 0 |  | 0
Damproofing, Waterproofing | [6 empty] | 0 |  | 0
Foundation Drain Board | [6 empty] | 0 |  | 0
Slab insulation: Edge/Blow | [6 empty] | 0 |  | 0
Exterior Foundation Insulation | [6 empty] | 0 |  | 0
Exterior Insulation Coating/ Protection | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
OTHER MASONRY/PAVING
Patios | [6 empty] | 0 |  | 0
Exterior Stairs | [6 empty] | 0 |  | 0
Masonry Chimneys | [6 empty] | 0 |  | 0
Fireplaces/Hearths | [6 empty] | 0 |  | 0
Driveway | [6 empty] | 0 |  | 0
Walkways | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
ROUGH FRAMING
Sill & Seal | [6 empty] | 0 |  | 0
Steel/Wood Carrying Beam, Lally Columns | [6 empty] | 0 |  | 0
Floor Framing | [6 empty] | 0 |  | 0
Exterior & Interior Walls, Rough Stairs | [6 empty] | 0 |  | 0
Sheathing, Subflooring | [6 empty] | 0 |  | 0
Roof Framing/Trusses | [6 empty] | 0 |  | 0
Subfascia | [6 empty] | 0 |  | 0
Steel Framing Connectors | [6 empty] | 0 |  | 0
Nails, Screws, Fasteners | [6 empty] | 0 |  | 0
Prep for Plaster, Drywall | [6 empty] | 0 |  | 0
Rough Framing - Labor Only | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
EXTERIOR
Exterior Foam Sheathing | [6 empty] | 0 |  | 0
Weather Barrier (Tyvek, etc.) | [6 empty] | 0 |  | 0
Membrane & Flashing | [6 empty] | 0 |  | 0
Vinyl or Composite Siding | [6 empty] | 0 |  | 0
Wood Siding | [6 empty] | 0 |  | 0
Brick Veneer | [6 empty] | 0 |  | 0
Stone Veneer | [6 empty] | 0 |  | 0
Stucco | [6 empty] | 0 |  | 0
Fascia, Frieze, Corner Boards, Water Table | [6 empty] | 0 |  | 0
Soffit/Gable Vents | [6 empty] | 0 |  | 0
Window/Door Trim | [6 empty] | 0 |  | 0
Other Exterior Trim | [6 empty] | 0 |  | 0
Exterior Paint, Stain, Caulk | [6 empty] | 0 |  | 0
Exterior, Labor Only | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
WINDOWS/EXTERIOR DOORS
Membrane & Flashing | [6 empty] | 0 |  | 0
Exterior doors, prehung | [6 empty] | 0 |  | 0
Exterior Door Slabs | [6 empty] | 0 |  | 0
Exterior Door Frames, Sills | [6 empty] | 0 |  | 0
Sidelights, Transoms | [6 empty] | 0 |  | 0
Locksets, Knobs, Door Hardware | [6 empty] | 0 |  | 0
Patio Doors: Sliding or Hinged | [6 empty] | 0 |  | 0
Windows | [6 empty] | 0 |  | 0
Garage Doors & Opener | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
PLUMBING
Drain/Waste/Vent | [6 empty] | 0 |  | 0
Water Supply Piping | [6 empty] | 0 |  | 0
Gas Piping | [6 empty] | 0 |  | 0
Water Treatment | [6 empty] | 0 |  | 0
Water Heater | [6 empty] | 0 |  | 0
Fixtures: Toilets, Tubs, Sinks, Showers | [6 empty] | 0 |  | 0
Faucets, Mixing Valves, Shower Heads | [6 empty] | 0 |  | 0
Disposal | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
ELECTRICAL
Service, Panel, Sub-Panels | [6 empty] | 0 |  | 0
Rough Wiring | [6 empty] | 0 |  | 0
Phone, Cable, Internet Wiring | [6 empty] | 0 |  | 0
Lighting Fixtures | [6 empty] | 0 |  | 0
Low-Voltage Fixtures/Transformers | [6 empty] | 0 |  | 0
Exterior Lighting | [6 empty] | 0 |  | 0
Devices: Outlets, Switches, Dimmers | [6 empty] | 0 |  | 0
Lighting Control System | [6 empty] | 0 |  | 0
Doorbell System | [6 empty] | 0 |  | 0
Smoke, CO2 Alarms | [6 empty] | 0 |  | 0
Intercom System | [6 empty] | 0 |  | 0
Security System | [6 empty] | 0 |  | 0
Home Theater/Entertainment | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
HVAC
Furnace/Heat Pump | [6 empty] | 0 |  | 0
Central AC | [6 empty] | 0 |  | 0
Air Handler | [6 empty] | 0 |  | 0
Ductwork, Grilles, Registers | [6 empty] | 0 |  | 0
Air Filter | [6 empty] | 0 |  | 0
Boiler, Piping | [6 empty] | 0 |  | 0
Radiators | [6 empty] | 0 |  | 0
Whole-House Ventilation (HRV, ERV, Exhaust Only, Other) | [6 empty] | 0 |  | 0
HVAC Controls | [6 empty] | 0 |  | 0
Solar Hot Water | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
INSULATION & AIR-SEALING
Roof/Attic Insulation | [6 empty] | 0 |  | 0
Roof/Eave Baffles | [6 empty] | 0 |  | 0
Wall Cavity Insulation | [6 empty] | 0 |  | 0
Foam Board Insulation | [6 empty] | 0 |  | 0
Spray Foam Insulation | [6 empty] | 0 |  | 0
Basement Insulation | [6 empty] | 0 |  | 0
Crawlspace Insulation | [6 empty] | 0 |  | 0
Air Sealing | [6 empty] | 0 |  | 0
Energy Diagnostics (Blower Door, Infrared) | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
DRYWALL/PLASTER
Walls | [6 empty] | 0 |  | 0
Ceilings, Soffits | [6 empty] | 0 |  | 0
Decorative Plaster | [6 empty] | 0 |  | 0
Drywall Labor Only | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
INTERIOR FINISH
Interior Doors, Prehung | [6 empty] | 0 |  | 0
Interior Door Slabs | [6 empty] | 0 |  | 0
Interior Door Frames, Thresholds | [6 empty] | 0 |  | 0
Door Knobs, Hardware | [6 empty] | 0 |  | 0
Chair Rail, Other | [6 empty] | 0 |  | 0
Wainscotting, Paneling | [6 empty] | 0 |  | 0
Built-In Shelving, Cabinets | [6 empty] | 0 |  | 0
Closet Shelving, Hardware | [6 empty] | 0 |  | 0
Stairs, Railings, Newels | [6 empty] | 0 |  | 0
Interior Painting, Staining | [6 empty] | 0 |  | 0
Wood Flooring | [6 empty] | 0 |  | 0
Carpeting | [6 empty] | 0 |  | 0
Resilient/Vinyl Flooring | [6 empty] | 0 |  | 0
Other Flooring | [6 empty] | 0 |  | 0
Acoustical, Metal, Decorative Ceilings | [6 empty] | 0 |  | 0
Interior Carpentry Labor Only | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
KITCHEN & BATH
Kitchen Cabinets | [6 empty] | 0 |  | 0
Bath Cabinets | [6 empty] | 0 |  | 0
Cabinet Pulls, Hardware | [6 empty] | 0 |  | 0
Countertop, Backsplash | [6 empty] | 0 |  | 0
Ceramic Tile, Stone | [6 empty] | 0 |  | 0
Raised Tub Platform | [6 empty] | 0 |  | 0
Tub Enclosure | [6 empty] | 0 |  | 0
Shower Enclosure/Doors | [6 empty] | 0 |  | 0
Medicine Cabinets | [6 empty] | 0 |  | 0
Mirrors | [6 empty] | 0 |  | 0
Towel Hangers, Toilet Paper Holders, Accessories | [6 empty] | 0 |  | 0
K&B Labor Only | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
PORCHES & DECKS
Open Porch | [6 empty] | 0 |  | 0
Screen Porch | [6 empty] | 0 |  | 0
Wood or Composite Deck | [6 empty] | 0 |  | 0
Fencing | [6 empty] | 0 |  | 0
Other Outdoor Structures | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
APPLIANCES
Refrigerator | [6 empty] | 0 |  | 0
Range, Cooktop | [6 empty] | 0 |  | 0
Microwave | [6 empty] | 0 |  | 0
Range Hood | [6 empty] | 0 |  | 0
Dishwasher | [6 empty] | 0 |  | 0
Washer/Dryer | [6 empty] | 0 |  | 0
Other | [6 empty] | 0 |  | 0
[7 empty] | 0 | 0
TOTAL | [6 empty] | 0 | 0
CLICK HERE TO CREATE IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.