## EXAMPLE - PMO Scorecard
PMO SCORECARD TEMPLATE
PROJECT MANAGEMENT OFFICE | PRIORITY | STATUS | PLANNED | ACTUAL | PLANNED LESS ACTUAL | OWNER | COMMENTARY | OUTCOMES OF RISK ANALYSIS | BUDGET IMPACT | COST BENEFIT ANALYSIS | DATE MODIFIED | PRIORITY KEY | STATUS KEY
PROJECTS COMPLETE # |  |  | 6 | 6 | 0 | Chris K. | We've completed the six projects planned through Q3. |  |  |  |  | HIGH | GREEN
TIME TO MOBILIZE IN DAYS |  |  | 7 | 6 | 1 | Chris K. | Mobilization is occurring one day faster than planned through Q3. |  |  |  |  | MEDIUM | YELLOW
TOTAL PORTFOLIO COST SAVINGS |  |  | 263000 | 181000 | 82000 | Greta L. | The additional benefits gained in Project Alpha more than offset the overruns in Project Beta. |  |  |  |  | LOW | RED
[12 empty] | ON HOLD | GREY
KEY PERFORMANCE INDICATOR (KPI) | PRIORITY | STATUS | PLANNED | ACTUAL | PLANNED LESS ACTUAL | OWNER | COMMENTARY | OUTCOMES OF RISK ANALYSIS | BUDGET IMPACT | COST BENEFIT ANALYSIS | DATE MODIFIED
PROJECT ALPHA | HIGH | YELLOW
Costs/Savings Realized ($) | LOW | YELLOW | 195000 | 100000 | 95000 | Chris K. | The cost savings continue to come in more than planned.
Scheduled Hours (hours) | ON HOLD | RED | 600 | 240 | 360 | Chris K. | The effort is less than budgeted.
Quality Index (1-100) | HIGH | GREY | 97 | 7 | 90 | Greta L. | #1 in sight by EOY on current growth trend
0
PROJECT BETA
Costs/Savings Realized ($) | MEDIUM | RED | 68000 | 81000 | -13000 | Jeffrey L. | Cost overruns are because the work is more complex than anticipated.
Scheduled Hours (hours) | MEDIUM | GREEN | 580 | 180 | 400 | Mark D. | The effort involved in Project Beta continues to be more than planned.
Quality Index (1-100) | LOW | YELLOW | 72 | 18 | 54 | John J. | Our QA processes are currently under review.
(add a key performance measure) |  |  |  |  | 0 | John J.
(Project Name)
(add a key performance measure) |  |  |  |  | 0 | Name
(Project Name)
(add a key performance measure) |  |  |  |  | 0
0
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - PMO Scorecard
PMO SCORECARD TEMPLATE
PROJECT MANAGEMENT OFFICE | PRIORITY | STATUS | PLANNED | ACTUAL | PLANNED LESS ACTUAL | OWNER | COMMENTARY | OUTCOMES OF RISK ANALYSIS | BUDGET IMPACT | COST BENEFIT ANALYSIS | DATE MODIFIED | PRIORITY KEY | STATUS KEY
PROJECTS COMPLETE # |  |  |  |  | 0 | [6 empty] | HIGH | GREEN
TIME TO MOBILIZE IN DAYS |  |  |  |  | 0 | [6 empty] | MEDIUM | YELLOW
TOTAL PORTFOLIO COST SAVINGS (add all projects) |  |  | 0 | 0 | 0 | [6 empty] | LOW | RED
[12 empty] | ON HOLD | GREY
KEY PERFORMANCE INDICATOR (KPI) | PRIORITY | STATUS | PLANNED | ACTUAL | PLANNED LESS ACTUAL | OWNER | COMMENTARY | OUTCOMES OF RISK ANALYSIS | BUDGET IMPACT | COST BENEFIT ANALYSIS | DATE MODIFIED
PROJECT NAME
Costs/Savings Realized ($) |  |  | 0 | 0 | 0
Scheduled Hours (hours) |  |  | 0 | 0 | 0
Quality Index (1-100) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
PROJECT NAME
Costs/Savings Realized ($) |  |  | 0 | 0 | 0
Scheduled Hours (hours) |  |  | 0 | 0 | 0
Quality Index (1-100) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
PROJECT NAME
Costs/Savings Realized ($) |  |  | 0 | 0 | 0
Scheduled Hours (hours) |  |  | 0 | 0 | 0
Quality Index (1-100) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
PROJECT NAME
Costs/Savings Realized ($) |  |  | 0 | 0 | 0
Scheduled Hours (hours) |  |  | 0 | 0 | 0
Quality Index (1-100) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.