## Project Definition Checklist
PROJECT DEFINITION CHECKLIST
X | PROJECT PURPOSE | DUE DATE
X | Articulate the need for the project. | 00/00/0000
Identify the root problem the project will solve.
Align the project’s purpose with the business’s goals.
Work with the sponsor to confirm the purpose.
| PROJECT GOAL | DUE DATE
Articulate what the project will achieve upon completion.
Write a clear, short goal statement (elevator pitch).
| BENEFITS | DUE DATE
List the opportunities you gain by solving this root problem.
Outline the ways in which the project will benefit the business.
Collaborate with the sponsor to define and agree on the benefits.
Conduct a cost-benefit analysis.
| OBJECTIVES | DUE DATE
Determine how you will achieve the project's goal.
Identify the necessary time, budget, quality, and stakeholder requirements.
Use clear goals (like SMART) to develop metrics and evaluation criteria for each objective. Make sure that the objectives are reasonable given the constraints.
Keep the objectives on a high level to avoid getting bogged down in the details.
| SCOPE | DUE DATE
Describe the work necessary to accomplish the objectives.
Determine the exclusions (i.e., that which is not necessary) with stakeholders.
Determine the primary deliverables that the project will produce.
With the stakeholders, sponsor, or client, rank the following in order of importance: time, budget, quality, stakeholder satisfaction, and scope.
Confirm this ranking with clients/stakeholders.
Use example scenarios to make sure all stakeholders understand that the objective prioritization is subject to change.
| DEPENDENCIES AND CONSTRAINTS | DUE DATE
Identify the constraints (i.e., the factors that will limit your ability to accomplish tasks throughout the project). Consider all the external standards, regulations, policies, procedures, conditions, and deadlines that can impact the project.
Identify the dependencies (i.e., the factors on which the project depends in order to progress). Include the project's dependence on internal factors (e.g., cross-team interdependence) and external ones (e.g., the availability of resources).
| RISKS AND ASSUMPTIONS | DUE DATE
Perform a realistic assessment of the uncertainties.
Add contingencies for unexpected costs, time delays, resource issues, etc.
Discuss potential risks and assumptions with the stakeholders and sponsor.
Create a risk management plan.
Define any unclear boundaries concerning project assumptions.
| STAKEHOLDERS AND SPONSOR | DUE DATE
List all stakeholders who have a connection to the project.
Prioritize stakeholders by labeling each as primary, secondary, tertiary, etc.
Review the priorities of each stakeholder. Meet with each stakeholder to begin building individual relationships.
Develop an engagement plan for each stakeholder/stakeholder group.
Determine governance between stakeholders if necessary.
Meet with the sponsor to define roles and expectations.
Negotiate the terms with stakeholders.
Make sure that the stakeholders and sponsor sign off on the agreed-upon terms.
| DECISIONS / APPROVAL | DUE DATE
Perform a final review of the project definition to catch any oversights.
Communicate your final decisions to employees and stakeholders.
Collect input from the project team before requesting final approval.
Before signing off, confirm that there is a total consensus among all stakeholders.
CLICK HERE TO CREATE IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.