## Agile Project Summary
AGILE PROJECT SUMMARY TEMPLATE
PROJECT NAME |  | PROJECT MANAGER | START DATE | END DATE | OVERALL PROGRESS |  | PROJECT DELIVERABLE |  | SCOPE STATEMENT
Product Release |  | Alex B. | 2026-09-02 | 2026-10-10 | 20%
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2026-09-03 | 2026-09-13 | 10 | Complete
| Feature 1 |  | Frank C. |  | 2026-09-03 | 2026-09-07 | 4 | Complete
| Feature 2 |  | Jacob S. |  | 2026-09-07 | 2026-09-12 | 5 | Complete
| Feature 3 |  | Jacob S. |  | 2026-09-09 | 2026-09-13 | 4 | Overdue
| Sprint 2 |  | Jacob S. |  | 2026-09-16 | 2026-09-24 | 8 | In Progress
| Feature 4 |  | Alex B. |  | 2026-09-16 | 2026-09-17 | 1 | In Progress
| Feature 5 |  | Frank C. |  | 2026-09-17 | 2026-09-21 | 4 | Not Started
| Feature 6 |  | Shari W. |  | 2026-09-22 | 2026-09-24 | 2 | Not Started
| Sprint 3 |  | Shari W. |  | 2026-09-25 | 2026-10-05 | 10 | Not Started
| Feature 7 |  | Alex B. |  | 2026-09-25 | 2026-09-29 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2026-09-24 | 2026-10-02 | 8 | Not Started
| Feature 9 |  | Jacob S. |  | 2026-10-02 | 2026-10-05 | 3 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Agile Project Summary
AGILE PROJECT SUMMARY TEMPLATE
PROJECT NAME |  | PROJECT MANAGER | START DATE | END DATE | OVERALL PROGRESS |  | PROJECT DELIVERABLE |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.