## Construction Dashboard
CONSTRUCTION PROJECT DASHBOARD TEMPLATE
PROJECT NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
|  |  |  | 00/00/0000 | In Progress | 72%
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS | STATUS | PRIORITY
Demo Prep |  | 2027-09-02 | 2027-09-03 | 2 | Complete | High |  | Not Started | High
Demolition |  | 2027-09-03 | 2027-09-07 | 5 | Complete | Medium |  | In Progress | Medium
Excavation |  | 2027-09-07 | 2027-09-12 | 6 | Complete | Low |  | Complete | Low
Concrete |  | 2027-09-09 | 2027-09-11 | 3 | Complete | Low |  | Overdue
Pre backfill |  | 2027-09-11 | 2027-09-15 | 5 | Complete | Low |  | On Hold
Framing |  | 2027-09-16 | 2027-09-17 | 2 | Overdue | High
Roof |  | 2027-09-17 | 2027-09-21 | 5 | In Progress | High
Plumbing |  | 2027-09-24 | 2027-10-02 | 9 | In Progress | High
Windows |  | 2027-10-02 | 2027-10-05 | 4 | In Progress | High
HVAC |  | 2027-10-05 | 2027-10-07 | 3 | On Hold | High
Electrical |  | 2027-10-06 | 2027-10-09 | 4 | Not Started | High
Launch |  | 2027-10-10 | 2027-10-10 | 1 | Not Started | Medium
TASK STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 80000
Not Started | 2 | 16.67% |  | ACTUAL | 50000
In Progress | 3 | 25%
Complete | 5 | 41.67%
Overdue | 1 | 8.333%
On Hold | 1 | 8.333%
TOTAL | 12 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 7 | 58.33% |  | Actions | 2
Medium | 2 | 16.67% |  | Change Requests | 4
Low | 3 | 25%
TOTAL | 12 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Construction Dashboard
CONSTRUCTION PROJECT DASHBOARD TEMPLATE
PROJECT NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
|  |  |  | 00/00/0000 |  | 72% | Enter DASHBOARD DATA in the tables beginning at row 8. Dashboard graphics will automatically populate. User to complete non-shaded cells only.
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS | STATUS | PRIORITY
Demo Prep |  |  |  | 0 |  |  |  | Not Started | High
Demolition |  |  |  | 0 |  |  |  | In Progress | Medium
Excavation |  |  |  | 0 |  |  |  | Complete | Low
Concrete |  |  |  | 0 |  |  |  | Overdue
Pre backfill |  |  |  | 0 |  |  |  | On Hold
Framing |  |  |  | 0
Roof |  |  |  | 0
Plumbing |  |  |  | 0
Windows |  |  |  | 0
HVAC |  |  |  | 0
Electrical |  |  |  | 0
Launch |  |  |  | 0
TASK STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 0
Not Started | 0 |  |  | ACTUAL | 0
In Progress | 0
Complete | 0
Overdue | 0
On Hold | 0
TOTAL | 0 | 0%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 0
High | 0 |  |  | Actions | 0
Medium | 0 |  |  | Change Requests | 0
Low | 0
TOTAL | 0 | 0%
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.