## Daily Project Timeline
DAILY PROJECT TIMELINE TEMPLATE
PROJECT NAME | Product Release
PROJECT MANAGER | Alex B.
PROJECT DELIVERABLE
Start Date | 2026-09-02
End Date | 2026-10-09
Overall Progress | 20%
TASKS | RESPONSIBLE | Start | End | Days | Status | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | STATUS
COMPLETE
Set kick-off meeting | Alex B. | 2026-09-02 | 2026-10-02 | 30 | COMPLETE | [38 empty] | IN PROGRESS
Agree on objectives | Frank C. | 2026-09-03 | 2026-09-07 | 4 | IN PROGRESS | [38 empty] | OVERDUE
Initiation |  |  |  |  | OVERDUE | [38 empty] | NOT STARTED
Detailed Reqs. | Jacob S. | 2026-09-07 | 2026-09-09 | 2 | IN PROGRESS
Hardward Reqs. | Jacob S. | 2026-09-09 | 2026-09-11 | 2 | OVERDUE
Final Resource Plan | Jacob S. | 2026-09-11 | 2026-09-15 | 4 | IN PROGRESS
Staffing | Alex B. | 2026-09-15 | 2026-09-17 | 2 | IN PROGRESS
Development |  |  |  |  | OVERDUE
Techincal Reqs. | Frank C. | 2026-09-17 | 2026-09-21 | 4 | NOT STARTED
DB Development | Shari W. | 2026-09-21 | 2026-09-23 | 2 | NOT STARTED
API Development | Shari W. | 2026-09-23 | 2026-09-25 | 2 | NOT STARTED
UI Client | Alex B. | 2026-09-25 | 2026-09-29 | 4 | NOT STARTED
Testing | Kennedy K. | 2026-09-29 | 2026-10-02 | 3 | NOT STARTED
Dev. Complete | Jacob S. | 2026-10-02 | 2026-10-05 | 3 | COMPLETE
Operations |  |  |  |  | IN PROGRESS
Hardware Config. | Alex B. | 2026-10-05 | 2026-10-07 | 2 | IN PROGRESS
System Testing | Kennedy K. | 2026-10-07 | 2026-10-09 | 2 | OVERDUE
Launch |  | 2026-10-09 | 2026-10-09 |  | IN PROGRESS
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Daily Project Timeline
DAILY PROJECT TIMELINE TEMPLATE
PROJECT NAME
PROJECT MANAGER
PROJECT DELIVERABLE
Start Date
End Date
Overall Progress
TASKS | RESPONSIBLE | Start | End | Days | Status | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | STATUS
COMPLETE
|  |  |  | 0 | [39 empty] | IN PROGRESS
|  |  |  | 0 | [39 empty] | OVERDUE
NOT STARTED
0
0
0
0
0
0
0
0
0
0
0
0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.