## Restaurant Startup Checklist
RESTAURANT STARTUP CHECKLIST TEMPLATE
ACTION | PRIORITY | % of PROGRESS | PROGRESS STATUS | APPROVAL STATUS | DATE DESIRED | DATE COMPLETED
Begin business and marketing plans | HIGH | 100% | Complete | Approved | 00/00/0000 | 00/00/0000
Obtain requirements from Department of Health | HIGH | 100% | Complete | Approved | 00/00/0000 | 00/00/0000
Examine and analyze possible locations | MED | 65% | In Progress | Submit for Approval | 00/00/0000
Determine start-up costs and necessary funding | LOW | 25% | In Progress | Submitted | 00/00/0000
Find funding sources | HIGH | 0% | Not Started | Needs Review | 00/00/0000
Hire attorney and accountant or bookkeeper |  |  | On Hold | Submit for Approval | 00/00/0000
Finalize location. Check zoning, parking, and other local restrictions |  |  | Overdue | Submitted | 00/00/0000
Finalize business name. |  |  | Needs Review | Needs review | 00/00/0000
Obtain Internet domain for business name
Complete business and marketing plans
Procure final financing or capital
Resolve business legal entity
Finalize business legal structure and file appropriate paperwork
Apply for FEIN and submit tax information to IRS
Apply for licenses and permits with health department, liquor board, and any others
Start bank account in business name
Select credit card POS system
Determine lease parameters with landlord.
Set up utilities, including phone, electrical, gas, and internet as needed
Deposit funds from financing or investors in business bank account
Finalize necessary insurance
Purchase or lease kitchen and bar equipment
Finalize business license
Produce employee handbook
Hire employees and complete all needed human resources paperwork
Obtain required employment notices and posters from state or municipality
Design logo
Implement marketing plan for opening
Soft opening
Schedule grand opening
Launch business/Grand opening
Review procedures and adjust for regular business
CLICK HERE TO CREATE IN SMARTSHEET

## KEYS - Do Not Delete
CHECKLIST KEYS – do not delete –
PROGRESS STATUS | PRIORITY | APPROVAL STATUS
Not Started | LOW | Submit for Approval
In Progress | MED | Submitted
Complete | HIGH | Approved
On Hold |  | Needs Review
Overdue
Needs Review

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.