## Sample Project Request Form
SAMPLE PROJECT REQUEST FORM TEMPLATE
PROJECT NAME | Positive Charge EV Charging Stations - California
JOB LOCATION | Mountain View, CA
EST. START DATE | 2024-11-23 | EST. FINISH DATE | 2025-09-02
PROJECT LEADER | Jane DeHart | COMPANY | Positive Charge
CONTACT NAME | John Steele | ADDRESS | 1123 4th Pl Monterey, CA 9394
PHONE | (415) 567-3245
EMAIL | j.steele27@positivechargeev.com
SUMMARY | This project is based on Positive Charge’s goal of being the world's largest EV-charging provider and to reduce the environmental impact of fossil-fuel cars through our services. The project requires 56 new EV-charging stations in the Mountain View, CA area by September of 2025. (Please see attached documents for further technical details.)
DESIRED OUTCOME | 56 fully functional Positive Charge EV charging stations in the Mountain View, CA area by September 2025.
ACTION TO COMPLETION | Account management to work with field engineers on logistics, timeline, detailed product plan (attached) for rollout of 56 EV-charging stations.
BENEFITS OF PROJECT | 56 Positive Charge EV-charging stations for EV car owners. Positive environmental impact (reduction in fossil-fuel emissions). Increase of sales for N. CA Sales Team, and significant revenue for Positive Charge.
PROJECTED SCHEDULE | ● 10/15/15 - contract signed ● 11/1/24 - Product provides project requirements to field engineers ● 11/14/24 - Sales engineering receives sign-off from Mountain View City Council for implementation of project. ● 12/30/24 - Project implementation begins ● 9/15/25 - Project successfully implemented
PROJECTED BUDGET | (Please see attached SOW with all relevant costs associated.)
PROJECTED TEAM AND RESOURCE REQUIREMENTS | Jane DeHart - Project Manager John Steel - Chief Sales Engineer Martha Goodwin - Operations VP Frida Kafta - Mountain View City Planning Coordinator Jim Bears - Positive Charge Project Sponsor (sign-off, etc.)
PROPOSAL MAY BE WITHDRAWN IF NOT ACCEPTED BY DATE OF
ACCEPTANCE OF PROPOSAL
AUTHORIZED CLIENT SIGNATURE |  | DATE OF ACCEPTANCE
CLICK HERE TO CREATE IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.