## Three Month Project Roadmap
THREE MONTH PROJECT ROADMAP TEMPLATE
CAMPAIGN NAME |  |  | STARTING DATE | ENDING DATE | % COMPLETE
|  |  | 2024-01-01 | 2024-03-31 | 72%
WORKSTREAM TIMELINE
DASHBOARD DATA
WORKSTREAMS
DESCRIPTION | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS | STATUS | PRIORITY
JAN | 2024-01-01 | 2024-01-31 | 30 | On Schedule | High |  | On Schedule | High
M1 Task 1 | 2024-01-04 | 2024-01-11 | 7 | On Schedule | Medium |  | Needs Attention | Medium
M1 Task 2 | 2024-01-07 | 2024-01-11 | 4 | On Schedule | Low |  | Delayed | Low
M1 Task 3 | 2024-01-10 | 2024-01-15 | 5 | On Schedule | Low
M1 Task 4 | 2024-01-13 | 2024-01-20 | 7 | On Schedule | Low
FEB | 2024-02-01 | 2024-02-29 | 28 | Needs Attention | High
M2 Task 1 | 2024-02-01 | 2024-02-10 | 9 | Needs Attention | High
M2 Task 2 | 2024-02-02 | 2024-02-11 | 9 | On Schedule | High
M2 Task 3 | 2024-02-15 | 2024-02-25 | 10 | Delayed | Low
M2 Task 4 | 2024-02-20 | 2024-02-27 | 7 | Delayed | High
MAR | 2024-03-01 | 2024-03-31 | 30 | Delayed | High
M3 Task 1 | 2024-03-01 | 2024-03-05 | 4 | On Schedule | Medium
M3 Task 2 | 2024-03-05 | 2024-03-11 | 6 | On Schedule | High
M3 Task 3 | 2024-03-11 | 2024-03-19 | 8 | Needs Attention | High
M3 Task 4 | 2024-03-20 | 2024-03-31 | 11 | Delayed | High
STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PROJECTED | 80000
On Schedule | 8 | 53.33% |  | USED | 50000
Needs Attention | 3 | 20% |  | REMAINING | 30000
Delayed | 4 | 26.67%
TOTAL | 15 | 100%
PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 9 | 60% |  | Actions | 2
Medium | 2 | 13.33% |  | Change Requests | 4
Low | 4 | 26.67%
| 0 | 0%
TOTAL | 15 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - 3 Month Project Roadmap
THREE MONTH PROJECT ROADMAP TEMPLATE
CAMPAIGN NAME |  |  | STARTING DATE | ENDING DATE | % COMPLETE
Enter ROADMAP DATA in the tables beginning at row 8. Dashboard graphics will automatically populate.
WORKSTREAM TIMELINE
DASHBOARD DATA
WORKSTREAMS
DESCRIPTION | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS | STATUS | PRIORITY
[MONTH] |  |  | 0 |  |  |  | On Schedule | High
M1 Task 1 |  |  | 0 |  |  |  | Needs Attention | Medium
M1 Task 2 |  |  | 0 |  |  |  | Delayed | Low
M1 Task 3 |  |  | 0
M1 Task 4 |  |  | 0
[MONTH] |  |  | 0
M2 Task 1 |  |  | 0
M2 Task 2 |  |  | 0
M2 Task 3 |  |  | 0
M2 Task 4 |  |  | 0
[MONTH] |  |  | 0
M3 Task 1 |  |  | 0
M3 Task 2 |  |  | 0
M3 Task 3 |  |  | 0
M3 Task 4 |  |  | 0
STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PROJECTED
On Schedule | 0 |  |  | USED
Needs Attention | 0 |  |  | REMAINING | 0
Delayed | 0
TOTAL | 0 | 0%
PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions
High | 0 |  |  | Actions
Medium | 0 |  |  | Change Requests
Low | 0
0
TOTAL | 0 | 0%
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.