## Workflow Plan Example
WORKFLOW PLAN TEMPLATE
PROJECT TITLE | [7 empty] | PROJECT MANAGER
* End Dates that have passed and are not "Complete" are highlighted in red.
You can use the custom columns to include additional information, such as the location, the tools you need, the supplies you need, or related documentation.
WORK ITEM | ASSIGNED TO | START DATE | END DATE | STATUS | CUSTOM 1 | CUSTOM 2 | CUSTOM 3 | COMMENTS | STATUS
PHASE: DEFINITION + IDEATION | [8 empty] | Not Started
Creative brief |  | 2021-05-01 | 2021-05-05 | Complete |  |  |  |  | In Progress
PHASE: CREATION | [8 empty] | Complete
Generate ideas |  | 2021-05-01 | 2021-05-07 | Complete |  |  |  |  | Ready for Approval
Record and share ideas |  | 2021-05-08 | 2021-05-10 | Complete |  |  |  |  | Approved
Review of similar products |  | 2021-05-09 | 2021-05-11 | In Progress |  |  |  |  | On Hold
Develop collaborative work environment |  | 2021-05-11 | 2021-05-15 | Ready for Approval
Pick collaboration tools |  | 2021-05-11 | 2021-05-15 | Approved
Communication plan |  | 2021-05-12 | 2021-05-17 | Not Started
Status report plan |  | 2021-05-14 | 2021-05-20 | On Hold
Time tracking plan |  | 2021-05-15 | 2021-05-21 | Not Started
PHASE: REVIEW + APPROVAL
Gather internal feedback |  | 2021-05-20 | 2021-06-01
Implement internal feedback |  | 2021-06-02 | 2021-06-04
Gather client feedback |  | 2021-05-25 | 2021-06-07
Implement client feedback |  | 2021-06-10 | 2021-06-11
Get internal approval |  | 2021-06-15 | 2021-06-15
Get client approval |  | 2021-06-16 | 2021-06-16
PHASE: PRODUCT LAUNCH
Distribution of materials |  | 2021-06-21 | 2021-06-21
Send invoices |  | 2021-06-26 | 2021-06-26
Manage client questions |  | 2021-06-28 | 2021-06-28
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Workflow Plan
WORKFLOW PLAN TEMPLATE
PROJECT TITLE | [7 empty] | PROJECT MANAGER
* End Dates that have passed and are not "Complete" are highlighted in red.
The custom columns can be used to include additional information such as location, tools needed, supplies needed, or related documentation.
WORK ITEM | ASSIGNED TO | START DATE | END DATE | STATUS | CUSTOM 1 | CUSTOM 2 | CUSTOM 3 | COMMENTS | STATUS
Not Started
In Progress
Complete
Ready for Approval
Approved
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.