## EXAMPLE Con Handover Checklist
CONSTRUCTION PROJECT HANDOVER CHECKLIST TEMPLATE
DONE | CATEGORY | DESCRIPTION | DATE DUE | DATE COMPLETED | PRIORITY | STATUS | QUANTITY REQUESTED | COMMENTS | DONE | PRIORITY | STATUS
| CLOSEOUT PER SPECIFICATION | [7 empty] | ✔ | Low | Not Started
| Contract Closeout | Submit warranties | 2028-02-02 | 2028-02-01 | Low | Not Started |  | Check with QC |  | Medium | In Progress
| Contract Closeout | Submit workmanship bonds |  |  | Medium | In Progress |  |  |  | High | Complete
✔ | Contract Closeout | Submit maintenance agreements |  |  | High | Complete |  |  |  |  | Needs Review
| Contract Closeout | Obtain certificate of conditional occupancy |  |  |  | Needs Review |  |  |  |  | Overdue
| Contract Closeout | Submit final project photos |  |  |  | On Hold |  |  |  |  | On Hold
| Contract Closeout | Submit damage or settlements surveys |  |  |  | Overdue
✔ | Contract Closeout | Submit property surveys |  |  |  | Complete
✔ | Contract Closeout | Submit final record information |  |  |  | Complete
REQUIRED TESTING
| Structural Steel | Inspect or test shop-bolted connections
WARRANTIES / GUARANTEES
| Wood Doors | Manufacturer's standard warranty
| Sprinkler Systems | Mfg warranty w/ forms completed in owner's name
CERTIFICATES
| Structural Steel | Mill certificates
| Hoist / Trolley | Load tested
FINAL SUBMITTAL
Punch list - Signed off
Mfg warranty w/ forms completed in owner's name
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Con Handover Checklist
CONSTRUCTION PROJECT HANDOVER CHECKLIST TEMPLATE
DONE | CATEGORY | DESCRIPTION | DATE DUE | DATE COMPLETED | PRIORITY | STATUS | QUANTITY REQUESTED | COMMENTS | DONE | PRIORITY | STATUS
| CLOSEOUT PER SPECIFICATION | [7 empty] | ✔ | Low | Not Started
[5 empty] | Low | Not Started |  | Check with QC |  | Medium | In Progress
[5 empty] | Medium | In Progress |  |  |  | High | Complete
✔ |  |  |  |  | High | Complete |  |  |  |  | Needs Review
[6 empty] | Needs Review |  |  |  |  | Overdue
[6 empty] | On Hold |  |  |  |  | On Hold
Overdue
✔ | [5 empty] | Complete
✔ | [5 empty] | Complete
REQUIRED TESTING
WARRANTIES / GUARANTEES
CERTIFICATES
FINAL SUBMITTAL

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.