## EXAMPLE - Agile RACI Matrix
EXAMPLE AGILE RACI MATRIX
|  |  | R | Responsible |  |  |  | A | Accountable |  |  |  | C | Consulted |  |  |  | I | Informed
| Executive Sponsor | Project Sponsor | Steering Committee | Advisory Committee | Role 5 | Project Manager | Tech Lead | Functional Lead | SME | Project Team Manager | Developer | Administrative Support | Business Analyst | Role 4 | Role 5 | Consultant | PMO | Role 3 | Role 4 | Role 5
| Project Leadership |  |  |  |  | Project Team Members |  |  |  |  | Project Sub-Teams |  |  |  |  | External Resources
Initiate Phase Activities
Request Review by PMO | A / C | R / A |  |  |  | R / A | A / C |  | C
Submit Project Request | [5 empty] | R | [10 empty] | A
Research Solution | I |  |  |  |  | R / A | A / C | A / C | C |  |  |  | C |  |  | C
Develop Business Case | I | A / C | I | I |  | R / A | C | C | C |  |  |  | C |  |  | C | C
Plan Phase Activities
Create Project Charter | C | C |  |  |  | R / A | C | C | C |  |  |  | C |  |  | C
Create Schedule | I | I | I | I |  | R / A | C | C | C | C | C | C | C |  |  | C | I
Create Additional Plans as Required | I | I | I |  |  | R / A |  |  |  | I | I | I | I |  |  | C | I
Execute Phase Activities
Build Deliverables | C / I | C / I | C / I | C / I |  |  | R / A | R / A | R / A | R / A | R / A |  |  |  |  | A / C
Create Status Report | I | I | I | I |  | R / A | R / A | R / A | R / A | [6 empty] | C | I
Control Phase Activities
Perform Change Management |  | C | C | C |  | R | A | A | A | [6 empty] | C | I
Close Phase Activities
Create Lessons Learned | C | C | C | C |  | R / A | C | C | C | C | C | C | C |  |  | C | C
Create Project Closure Report | I | I | I | I |  | R / A | I | I | I | I | I | I | I |  |  |  | I
CLICK HERE TO CREATE IN SMARTSHEET
Project
Deliverable
or Activity

## BLANK - Agile RACI Matrix
AGILE RACI MATRIX
|  |  | R | Responsible |  |  |  | A | Accountable |  |  |  | C | Consulted |  |  |  | I | Informed
| Executive Sponsor | Project Sponsor | Steering Committee | Advisory Committee | Role 5 | Project Manager | Tech Lead | Functional Lead | SME | Project Team Manager | Developer | Administrative Support | Business Analyst | Role 4 | Role 5 | Consultant | PMO | Role 3 | Role 4 | Role 5
| Project Leadership |  |  |  |  | Project Team Members |  |  |  |  | Project Sub-Teams |  |  |  |  | External Resources
INITIATE PHASE ACTIVITIES
Request Review by PMO
Submit Project Request
Research Solution
Develop Business Case
PLAN PHASE ACTIVITIES
Create Project Charter
Create Schedule
Create Additional Plans as Required
EXECUTE PHASE ACTIVITIES
Build Deliverables
Create Status Report
CONTROL PHASE ACTIVITIES
Perform Change Management
CLOSE PHASE ACTIVITIES
Create Lessons Learned
Create Project Closure Report

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.