## Project Work Schedule
PROJECT WORK SCHEDULE TEMPLATE
Project Name | Product Release
Project Manager | Alex B.
Project Deliverable
Start Date | 2015-09-02
End Date | 2015-10-09
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status | 2015-09-02 | 2015-09-03 | 2015-09-04 | 2015-09-05 | 2015-09-06 | 2015-09-07 | 2015-09-08 | 2015-09-09 | 2015-09-10 | 2015-09-11 | 2015-09-12 | 2015-09-13 | 2015-09-14 | 2015-09-15 | 2015-09-16 | 2015-09-17 | 2015-09-18 | 2015-09-19 | 2015-09-20 | 2015-09-21 | 2015-09-22 | 2015-09-23 | 2015-09-24 | 2015-09-25 | 2015-09-26 | 2015-09-27 | 2015-09-28 | 2015-09-29 | 2015-09-30 | 2015-10-01 | 2015-10-02 | 2015-10-03 | 2015-10-04 | 2015-10-05 | 2015-10-06 | 2015-10-07 | 2015-10-08 | 2015-10-09
2016-03-16
Set kick-off meeting | Alex B. | 2015-09-02 | 2015-09-02 | 0 | Complete
Agree on objectives | Frank C. | 2015-09-03 | 2015-09-07 | 4 | Complete
Initiation
Detailed Reqs. | Jacob S. | 2015-09-07 | 2015-09-09 | 2 | Complete
Hardward Reqs. | Jacob S. | 2015-09-09 | 2015-09-11 | 2 | Overdue
Final Resource Plan | Jacob S. | 2015-09-11 | 2015-09-15 | 4 | In progress
Staffing | Alex B. | 2015-09-15 | 2015-09-17 | 2 | In progress
Development
Techincal Reqs. | Frank C. | 2015-09-17 | 2015-09-21 | 4 | Not started
DB Development | Shari W. | 2015-09-21 | 2015-09-23 | 2 | Not started
API Development | Shari W. | 2015-09-23 | 2015-09-25 | 2 | Not started
UI Client | Alex B. | 2015-09-25 | 2015-09-29 | 4 | Not started
Testing | Kennedy K. | 2015-09-29 | 2015-10-02 | 3 | Not started
Dev. Complete | Jacob S. | 2015-10-02 | 2015-10-05 | 3 | Not started
Operations
Hardware Config. | Alex B. | 2015-10-05 | 2015-10-07 | 2 | Not started
System Testing | Kennedy K. | 2015-10-07 | 2015-10-09 | 2 | Not started
Launch |  | 2015-10-09 | 2015-10-09
CLICK HERE TO CREATE IN SMARTSHEET

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.