## Sample Project Schedule
SAMPLE PROJECT SCHEDULE TEMPLATE
PROJECT NAME |  |  |  | START DATE
Positive Charge EMV Station Installations |  |  |  | 2025-05-05
PROJECT MANAGER |  |  |  | END DATE
Jane Matthews |  |  |  | 2026-02-10
| TIMELINE |  |  | PROJECT NOTES
PROJECT PHASES | START DATE | END DATE | DURATION in days | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
CONCEPTION AND INITIATION | 2025-05-05 | 2025-08-10 | 95
Project Charter | 2025-05-05 | 2025-07-01 | 58 | Defined/Driven by Project Management |  | Operations and Sales Engineers
Project Initiation | 2025-05-10 | 2025-08-10 | 93
DEFINITION AND PLANNING | 2025-06-10 | 2026-03-01 | 265
Scope and Budget | 2025-06-22 | 2025-08-04 | 44 |  | 2,345,123.00 for all 126 EV location installations |  | Going over budget could risk installations in the SW
Work Breakdown Schedule (WBS) | 2025-07-14 | 2025-11-01 | 111
Communication Plan | 2025-07-14 | 2026-01-20 | 191 | Defined/Driven by Marketing
Risk Management | 2025-08-01 | 2025-10-01 | 62
LAUNCH / EXECUTION | 2025-08-14 | 2025-08-30 | 17
Status and Tracking | 2025-09-01 | 2025-12-10 | 101
Key Performance Indicators (KPIs) | 2025-10-01 | 2025-11-15 | 46
Quality | 2025-10-01 | 2025-12-01 | 62
Forecasts | 2025-11-01 | 2025-12-01 | 31
PERFORMANCE AND CONTROL | 2025-11-10 | 2026-12-10 | 396
Objectives | 2025-12-01 | 2026-02-10 | 72
Quality Deliverables | 2026-02-01 | 2026-02-28 | 28
Effort and Cost Tracking | 2026-03-01 | 2026-03-30 | 30
Performance | 2026-04-01 | 2026-04-30 | 30
PROJECT CLOSE | 2026-05-01 | 2026-05-21 | 21
Post mortem | 2026-05-01 | 2026-05-08 | 7
Project punchlist | 2026-05-08 | 2026-05-15 | 7
Reporting | 2026-05-15 | 2026-05-21 | 7
DELIVERY TIMELINE
CLICK HERE TO CREATE IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.