## Weekly Project Status Report Ex
WEEKLY PROJECT STATUS REPORT EXAMPLE
PROJECT NAME | Booth Fabrication for Expo | PROJECT CODE | EXPO | STATUS KEY | BUDGET KEY
PROJECT MANAGER | Joe Maroco | DATE OF STATUS ENTRY | 2026-03-11 | ROADBLOCK / OVERAGE | OVER
PERIOD COVERED | 3/5/26-3/11/26 | PROJECTED DATE OF COMPLETION | 2026-04-01 | POTENTIAL RISKS / DELAYS | ON
|  |  |  | ON TRACK | UNDER
PROJECT STATUS THIS WEEK
OVERALL PROJECT STATUS | ON TRACK | SUMMARY | Received final shipment of materials, began construction on overhead signage and completed mobile countertops
MILESTONES | Completed construction of mobile countertops for espresso machines
Applied vinyl logos to counters
Received prefabricated signage, can now begin construction of overhead logo display
PROJECT COMPONENTS
COMPONENT | STATUS | OWNER / TEAM | NOTES
BUDGET | ON | Joe | No outstanding budget notes at this time
RESOURCES | ON TRACK | Joe | Received prefabricated logo signage this week
TIMELINE | POTENTIAL RISKS / DELAYS | Joe | Logo signage shipment was expected last week, beginning of construction of overhead signage pushed back a week as a result
SCOPE | ON TRACK | Joe | No major changes to original design
WORK ACCOMPLISHED
TASK NUMBER | DESCRIPTION | OWNER / TEAM | RECEPTION
4 | Completed construction of mobile countertops | Dan | Counters are structurally sound and look great!
5 | Applied vinyl logos to counters | Dan | Logos are in place and level
RISKS AND ROADBLOCKS
RISK NUMBER | DESCRIPTION | OWNER / TEAM | FIX
1 | Late shipment of prefabricated signage | Joe | Mobile countertop construction moved up to accommodate for this gap
HIGHLIGHTS AND KEY TAKEAWAYS
Dan made an excellent pivot to countertop construction when overhead signage was not received on time!
UPCOMING WORK
WEEK NUMBER | STATUS | DETAILS
3 | POTENTIAL RISKS / DELAYS | Begin and complete construction of overhead signage
4 | ON TRACK | Complete construction and vinyl laminate of backdrops
5 | ON TRACK | Package all units for pickup by customer
OVERALL PROJECT PROGRESS TIMELINE
CLICK HERE TO CREATE IN SMARTSHEET
MILESTONE 1
Finalize details of design and produce rendering
MILESTONE 2
Sourced and ordered materials for overhead sign display
MILESTONE 3
Complete construction on mobile counters
MILESTONE 4
Complete construction on overhead signage
MILESTONE 5
All units packed and waiting for pickup by customer
CURRENT TIMELINE POSITION
3/11/2026
ROADBLOCK 1
Late arrival of prefabricated overhead signage
PROJECT START DATE
2/14/2026
PROJECT END DATE
00/00/0000

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.