## EX - Iterative Project Plan
ITERATIVE PROJECT PLAN EXAMPLE TEMPLATE
COMPANY NAME |  |  |  |  | START DATE
2025-03-31
|  | PHASES | [5 empty] | DELIVERABLES |  | COST / HOURS |  |  | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
STATUS | PRIORITY | PHASE | TASK DESCRIPTION | OWNER | START DATE | END DATE | # of Days | DELIVERABLES | % COMPLETE | FIXED COST | EST. HOURS | ACTUAL HRS | time axis 2025-03-31 to 2025-08-15
In Progress | HIGH | INCEPTION |  |  | 2025-03-31 | 2025-04-21 | 16 |  | 74.33% | 22530 | 306 | 298 | bar: 2025-03-31 to 2025-08-15
In Progress | MED | Product Requirements | Record and develop requirements | John | 2025-03-31 | 2025-04-03 | 4 | All requirements | 33% | 8500 | 32 | 36 | bar: 2025-03-31 to 2025-04-03
On Hold | MED | Business Case | Establish the business case | Ellen | 2025-04-02 | 2025-04-18 | 13 | Business case | 100% | 2500 | 104 | 100 | bar: 2025-04-02 to 2025-04-18
Overdue | HIGH | Software Plan | Develop a high-level plan/roadmap | DeShaun | 2025-04-13 | 2025-04-18 | 5 | Software roadmap | 90% | 3200 | 40 | 40 | bar: 2025-04-14 to 2025-04-18
Needs Review | LOW | Use Case | Develop the use case | Ellen | 2025-04-03 | 2025-04-12 | 7 | All use cases | 33% | 750 | 50 | 56 | bar: 2025-04-03 to 2025-04-11
Complete | MED | Business Case Review | Review the business case | Matthew | 2025-04-09 | 2025-04-20 | 8 | Business case final document | 100% | 6380 | 64 | 56 | bar: 2025-04-09 to 2025-04-18
Needs Update | HIGH | Approval/Non-Approval | Determine whether or not to proceed based on the use case | Matthew | 2025-04-18 | 2025-04-21 | 2 | Approval | 90% | 1200 | 16 | 10 | bar: 2025-04-18 to 2025-04-21
In Progress | MED | ELABORATION |  |  | 2025-04-11 | 2025-06-21 | 51 |  | 26% | 16700 | 792 | 367 | bar: 2025-03-31 to 2025-08-15
Needs Update | LOW | Requirements | Analyze the requirements | Samir | 2025-04-11 | 2025-06-21 | 51 | Requirements analysis document | 70% | 2200 | 350 | 356 | bar: 2025-04-11 to 2025-06-20
In Progress | HIGH | Architectural Prototype | Develop the prototype |  | 2025-04-30 | 2025-05-02 | 3 | Prototype | 60% | 14500 | 20 | 11 | bar: 2025-04-30 to 2025-05-02
Not Started | LOW | Use Case | Complete the analysis and design for all use cases | Ellen | 2025-05-05 | 2025-06-19 | 34 | Use case analysis document | 0% |  | 272 | bar: 2025-05-05 to 2025-06-19
Not Started | LOW | Test | Test the architecture feasibility and performance |  | 2025-05-06 | 2025-06-03 | 21 | Test feedback | 0% |  | 150 | bar: 2025-05-06 to 2025-06-03
|  | Final Architectural Prototype | Verify all major architectural release components |  |  |  | 0 | Final prototype | 0%
Overdue | LOW | CONSTRUCTION |  |  | 2025-04-14 | 2025-04-24 | 9 |  | 71.2% | 8350 | 107 | 91 | bar: 2025-03-31 to 2025-08-15
On Hold | MED | Use Case | Analyze and design any remaining use cases |  | 2025-04-14 | 2025-04-18 | 5 | Use case analysis document | 33% | 6500 | 40 | 36 | bar: 2025-04-14 to 2025-04-18
Complete | HIGH | Beta Version | Develop and distribute the beta version for release |  | 2025-04-15 | 2025-04-16 | 2 | Beta version | 100% |  | 16 | 12 | bar: 2025-04-15 to 2025-04-16
In Progress | LOW | Implementation | Complete implementation activities |  | 2025-04-17 | 2025-04-17 | 1 | Beta implementation | 90% |  | 5 | 5 | bar: 2025-04-17
Overdue | LOW | Test | Complete test activities |  | 2025-04-21 | 2025-04-24 | 4 | Testing results | 33% |  | 32 | 22 | bar: 2025-04-21 to 2025-04-24
Complete | LOW | Operational Capability | Prepare release for packaging |  | 2025-04-22 | 2025-04-23 | 2 | Final release package activities | 100% | 1850 | 14 | 16 | bar: 2025-04-22 to 2025-04-23
|  | TRANSITION |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | Distribution | Prepare release for distribution |  |  |  | 0 | Product ready to ship | 0%
|  | Support | Provide any installation support necessary |  |  |  | 0 | Support channels | 0%
|  | User Training | Provide user training |  |  |  | 0 | Develop and share training | 0%
|  | Final Release | Install all capabilities and make available to users |  |  |  | 0 | Product shipped | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Iterative Project Plan
ITERATIVE PROJECT PLAN TEMPLATE
COMPANY NAME |  |  |  |  | START DATE
[5 empty] | 2025-03-31 |  |  | <-- Enter initial Start Date to populate Timeline dates.
|  | PHASES | [5 empty] | DELIVERABLES |  | COST / HOURS |  |  | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
STATUS | PRIORITY | PHASE | TASK DESCRIPTION | TASK OWNER | START DATE | END DATE | # of Days | DELIVERABLE | % COMPLETE | FIXED COST | EST. HOURS | ACTUAL HOURS | time axis 2025-03-31 to 2025-08-15
|  | ITERATION 1 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | Planning & Requirements |  |  |  |  | 0 |  | 0%
|  | Analysis & Design |  |  |  |  | 0 |  | 0%
|  | Implementation |  |  |  |  | 0 |  | 0%
|  | Testing |  |  |  |  | 0 |  | 0%
|  | Evaluation & Review |  |  |  |  | 0 |  | 0%
[7 empty] | 0 |  | 0%
|  | ITERATION 2 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | Planning & Requirements |  |  |  |  | 0 |  | 0%
|  | Analysis & Design |  |  |  |  | 0 |  | 0%
|  | Implementation |  |  |  |  | 0 |  | 0%
|  | Testing |  |  |  |  | 0 |  | 0%
|  | Evaluation & Review |  |  |  |  | 0 |  | 0%
[7 empty] | 0 |  | 0%
|  | ITERATION 3 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | Planning & Requirements |  |  |  |  | 0 |  | 0%
|  | Analysis & Design |  |  |  |  | 0 |  | 0%
|  | Implementation |  |  |  |  | 0 |  | 0%
|  | Testing |  |  |  |  | 0 |  | 0%
|  | Evaluation & Review |  |  |  |  | 0 |  | 0%
[7 empty] | 0 |  | 0%
|  | ITERATION 4 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | Planning & Requirements |  |  |  |  | 0 |  | 0%
|  | Analysis & Design |  |  |  |  | 0 |  | 0%
|  | Implementation |  |  |  |  | 0 |  | 0%
|  | Testing |  |  |  |  | 0 |  | 0%
|  | Evaluation & Review |  |  |  |  | 0 |  | 0%
[7 empty] | 0 |  | 0%
|  | ITERATION 5 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | Task 1 |  |  |  |  | 0 |  | 0%
|  | Task 2 |  |  |  |  | 0 |  | 0%
|  | Task 3 |  |  |  |  | 0 |  | 0%
|  | Task 4 |  |  |  |  | 0 |  | 0%
|  | Task 5 |  |  |  |  | 0 |  | 0%
|  | Task 6 |  |  |  |  | 0 |  | 0%

## Dropdown Keys - do not delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | LOW | Not Started
No | MED | In Progress
| HIGH | Complete
On Hold
Overdue
Needs Review
Needs Update

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.