## SAMPLE Project Intake Dashboard
PROJECT INTAKE DASHBOARD TEMPLATE
Sample data displayed on current tab. Blank version available on second tab: BLANK Project Intake Dashboard. Enter DASHBOARD DATA in the tables beginning on row 27. Enter PROJECT TYPES in the Dropdown Keys tab. Dashboard graphics will automatically populate.
COST vs. BENEFIT
TOTAL EST. COST
9599865
TOTAL EST. BENEFIT
16060831
TOTAL OPEN REQUESTS |  | COST vs. BENEFIT
18
AVG. DAYS TO COMPLETION
65.7778
DASHBOARD DATA
PROJECT TABLE
PROJECT ID | PROJECT TITLE | PROJECT TYPE | PRIORITY | STATUS | EST. START DATE | EST. END DATE | DURATION in days | EST. COST | EST. BENEFIT
P502462A | Alpha | Type A | Low | Initial Request | 2033-01-02 | 2033-01-31 | 30 | 50000 | 285000
P502477V | Beta | Type A | Moderate | First Review | 2033-01-04 | 2033-02-11 | 39 | 2000000 | 3500000
P502489D | Gamma | Type F | Low | Second Review | 2033-01-07 | 2033-02-11 | 36 | 500000 | 350000
P502498W | Delta | Type C | Low | Pending Final Approval | 2033-01-10 | 2033-02-15 | 37 | 200000 | 575000
P502504F | Epsilon | Type E | Low | First Review | 2033-01-13 | 2033-03-20 | 67 | 485000 | 500000
P502516X | Zeta | Type B | Critical | Initial Request | 2033-01-16 | 2033-03-21 | 65 | 389000 | 120000
P502529S | Eta | Type G | High | Initial Request | 2033-01-19 | 2033-04-01 | 73 | 1200000 | 1850000
P502535Z | Theta | Type B | Moderate | Initial Request | 2033-01-22 | 2033-03-09 | 47 | 185000 | 685000
P502544D | Iota | Type E | High | Second Review | 2033-01-25 | 2033-04-05 | 71 | 567000 | 345000
P502554R | Kappa | Type B | High | Pending Final Approval | 2033-01-28 | 2033-05-06 | 99 | 654800 | 438700
P502566J | Lambda | Type D | Critical | Pending Final Approval | 2033-01-31 | 2033-04-28 | 88 | 465000 | 1850000
P502516X | Mu | Type B | Critical | Initial Request | 2033-01-16 | 2033-03-21 | 65 | 43500 | 0
P502529S | Nu | Type G | High | Initial Request | 2033-01-19 | 2033-04-01 | 73 | 454480 | 462047
P502535Z | Xi | Type B | Moderate | Initial Request | 2033-01-22 | 2033-03-09 | 47 | 854000 | 645000
P502544D | Omicron | Type E | High | Second Review | 2033-01-25 | 2033-04-05 | 71 | 123000 | 456000
P502554R | Pi | Type B | High | Pending Final Approval | 2033-01-28 | 2033-05-06 | 99 | 850000 | 3345000
P502566J | Rho | Type D | Critical | Pending Final Approval | 2033-01-31 | 2033-04-28 | 88 | 454085 | 454084
P502577Y | Sigma | Type G | Critical | Pending Final Approval | 2033-02-03 | 2033-05-02 | 89 | 125000 | 200000
| PROJECT TYPE |  |  | PROJECT STATUS |  |  |  | COST / BENEFIT TOTAL
| TYPE | COUNT |  | STATUS | COUNT | % |  | EST. COST | 9599865
| Type A | 2 |  | Initial Request | 7 | 38.89% |  | EST. BENEFIT | 16060831
| Type B | 6 |  | First Review | 2 | 11.11%
| Type C | 1 |  | Second Review | 3 | 16.67% |  | TOTAL OPEN REQUESTS
| Type D | 2 |  | Pending Final Approval | 6 | 33.33%
| Type E | 3 |  | TOTAL | 18 | 100% |  | 18
| Type F | 1
| Type G | 3 |  | PROJECT PRIORITY |  |  |  | AVG. DAYS TO COMPLETION
| Type H | 0 |  | PRIORITY | COUNT | %
| Type I | 0 |  | Critical | 5 | 27.78% |  | 65.7778
| Type J | 0 |  | High | 6 | 33.33%
|  |  |  | Moderate | 3 | 16.67%
|  |  |  | Low | 4 | 22.22%
|  |  |  | TOTAL | 18 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Project Intake Dashboard
PROJECT INTAKE DASHBOARD TEMPLATE
Enter DASHBOARD DATA in the tables beginning on row 26. Enter PROJECT TYPES in the Dropdown Keys tab. Dashboard graphics will automatically populate.
COST vs. BENEFIT
TOTAL EST. COST
0
TOTAL EST. BENEFIT
0
TOTAL OPEN REQUESTS |  | COST vs. BENEFIT
0
AVG. DAYS TO COMPLETION
0
DASHBOARD DATA
PROJECT TABLE
PROJECT ID | PROJECT TITLE | PROJECT TYPE | PRIORITY | STATUS | EST. START DATE | EST. END DATE | DURATION in days | EST. COST | EST. BENEFIT
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| PROJECT TYPE |  |  | PROJECT STATUS |  |  |  | COST / BENEFIT TOTAL
| TYPE | COUNT |  | STATUS | COUNT | % |  | EST. COST | 0
| Type A | 0 |  | Initial Request | 0 |  |  | EST. BENEFIT | 0
| Type B | 0 |  | First Review | 0
| Type C | 0 |  | Second Review | 0 |  |  | TOTAL OPEN REQUESTS
| Type D | 0 |  | Pending Final Approval | 0
| Type E | 0 |  | TOTAL | 0 | 0% |  | 0
| Type F | 0
| Type G | 0 |  | PROJECT PRIORITY |  |  |  | AVG. DAYS TO COMPLETION
| Type H | 0 |  | PRIORITY | COUNT | %
| Type I | 0 |  | Critical | 0 |  |  | 0
| Type J | 0 |  | High | 0
|  |  |  | Moderate | 0
|  |  |  | Low | 0
|  |  |  | TOTAL | 0 | 0%

## Dropdown Keys - do not delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS | PROJECT TYPE
Yes | Critical | Initial Request | Type A
No | High | First Review | Type B
| Moderate | Second Review | Type C
| Low | Pending Final Approval | Type D
Type E
Type F
Type G
Type H
Type I
Type J

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.