## EX - Weekly Agile Sprint Report
WEEKLY AGILE SPRINT STATUS REPORT TEMPLATE
PROJECT NAME |  | STARTING DATE | ENDING DATE |  |  | PROGRAM STATUS | PERCENT COMPLETED
[ name ] |  | 2028-10-06 | 2028-12-23 |  |  | On Track | 16.67%
|  | ––––––––––––––– Number of Story Points ––––––––––––––– |  |  | AVERAGE COMPLETIONS | TOTAL NUMBER OF WEEKS
|  | TOTAL | COMPLETE | INCOMPLETE
|  | 54 | 4 | 50 | 1 | 12
TASK NAME | ASSIGNED TO | STORY POINTS | START | FINISH | PLANNED DAYS | ACTUAL DAYS | STATUS
Sprint 1 | Mitch A. |  | 2028-10-06 | 2028-10-25 | 20
Part A | Alex B. | 3 | 2028-10-06 | 2028-10-07 | 2 |  | COMPLETE
Part B | Frank C. | 6 | 2028-10-07 | 2028-10-10 | 4 |  | ON TRACK
Part C | Jacob S. | 9 | 2028-10-10 | 2028-10-25 | 16 |  | ON TRACK
Sprint 2 | Dawn P. |  | 2028-10-25 | 2028-11-20 | 27
Part A | Jacob S. | 1 | 2028-10-25 | 2028-11-02 | 9 |  | COMPLETE
Part B | Jacob S. | 5 | 2028-11-02 | 2028-11-15 | 14 |  | ON TRACK
Part C | Alex B. | 6 | 2028-11-15 | 2028-11-20 | 6 |  | DELAYED
Sprint 3 |  |  | 2028-11-20 | 2028-12-10 | 21
Part A | Frank C. | 3 | 2028-11-20 | 2028-11-30 | 11 |  | NOT STARTED
Part B | Kennedy K. | 1 | 2028-11-30 | 2028-12-06 | 7 |  | ON TRACK
Part C | Jacob S. | 4 | 2028-12-06 | 2028-12-10 | 5 |  | NOT STARTED
Sprint 4 |  |  | 2028-12-10 | 2028-12-23 | 14
Part A | Alex B. | 6 | 2028-12-10 | 2028-12-12 | 3 |  | DELAYED
Part B | Kennedy K. | 2 | 2028-12-12 | 2028-12-15 | 4 |  | NOT STARTED
Part C | Mitch A. | 8 | 2028-12-15 | 2028-12-23 | 9 |  | NOT STARTED
OVERALL PROJECT STATUS |  |  | WEEKLY BURNDOWN CHART
REVIEW
WHAT DID WE DO WELL THIS WEEK?
WHAT CAN WE DO BETTER NEXT WEEK?
RISKS AND ROADBLOCKS
RISK/ROADBLOCK | DATE REPORTED | DATE RESOLVED | RESOLUTION
Risk Description 1 | 00/00/0000 | 00/00/0000 | Resolution 1
Risk Description 2 | 00/00/0000 | 00/00/0000 | Resolution 2
Risk Description 3 | 00/00/0001 | 00/00/0001 | Resolution 3
Risk Description 4 | 00/00/0002 | 00/00/0002 | Resolution 4
STATUS BREAKDOWN | – calculates automatically – | [7 empty] | BURNDOWN DATA ***DO NOT DELETE***
NOT STARTED | 4 | 33.33% | [6 empty] | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | TOTAL
ON TRACK | 4 | 33.33% | [5 empty] | STORY POINTS | 18 | 0 | 1 | 5 | 0 | 6 | 3 | 1 | 4 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54
COMPLETE | 2 | 16.67% | [5 empty] | COMPLETE | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
DELAYED | 2 | 16.67% | [5 empty] | DELAYED | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
TOTAL | 12 | 100% | [5 empty] | NOT STARTED | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
[8 empty] | ON TRACK | 15 | 0 | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
CLICK HERE TO CREATE IN SMARTSHEET | [7 empty] | EFFORT REMAINING | 15 | 0 | 0 | 5 | 0 | 6 | 3 | 1 | 4 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
[8 empty] | IDEAL BURNDOWN | 54 | 49.5 | 45 | 40.5 | 36 | 31.5 | 27 | 22.5 | 18 | 13.5 | 9 | 4.5 | 0 | 0 | 0 | 0 | 0
4.5
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Weekly Agile Sprint Rpt
WEEKLY AGILE SPRINT STATUS REPORT TEMPLATE
PROJECT NAME |  | STARTING DATE | ENDING DATE |  |  | PROGRAM STATUS | PERCENT COMPLETED
[ name ] |  | 2028-10-06 | 2028-12-23 |  |  | On Track | #DIV/0!
|  | ––––––––––––––– Number of Story Points ––––––––––––––– |  |  | AVERAGE COMPLETIONS | TOTAL NUMBER OF WEEKS
|  | TOTAL | COMPLETE | INCOMPLETE
|  | 0 | 0 | 0 | 0 | 12
TASK NAME | ASSIGNED TO | STORY POINTS | START | FINISH | PLANNED DAYS | ACTUAL DAYS | STATUS
OVERALL PROJECT STATUS |  |  | WEEKLY BURNDOWN CHART
REVIEW
WHAT DID WE DO WELL THIS WEEK?
WHAT CAN WE DO BETTER NEXT WEEK?
RISKS AND ROADBLOCKS
RISK/ROADBLOCK | DATE REPORTED | DATE RESOLVED | RESOLUTION
Risk Description 1 | 00/00/0000 | 00/00/0000 | Resolution 1
Risk Description 2 | 00/00/0000 | 00/00/0000 | Resolution 2
Risk Description 3 | 00/00/0001 | 00/00/0001 | Resolution 3
Risk Description 4 | 00/00/0002 | 00/00/0002 | Resolution 4
STATUS BREAKDOWN | – calculates automatically – | [7 empty] | BURNDOWN DATA ***DO NOT DELETE***
NOT STARTED | 0 | #DIV/0! | [6 empty] | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | TOTAL
ON TRACK | 0 | #DIV/0! | [5 empty] | STORY POINTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMPLETE | 0 | #DIV/0! | [5 empty] | COMPLETE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DELAYED | 0 | #DIV/0! | [5 empty] | DELAYED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | #DIV/0! | [5 empty] | NOT STARTED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | ON TRACK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | EFFORT REMAINING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | IDEAL BURNDOWN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
CLICK HERE TO CREATE IN SMARTSHEET

## Dropdown Keys
PMO DASHBOARD TEMPLATE
DROPDOWN KEYS
PRIORITY | STATUS
Low | NOT STARTED
Medium | ON TRACK
High | COMPLETE
DELAYED

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.